Infectious Disease Emergence and Economics of Altered Landscapes (IDEEAL)

In response to USAID-RDMA-RFA-486-13-000001

May 24, 2013.

EcoHealth Alliance

460 West 34th Street,

New York, NY 10001

U.S.A.

Administrative Point of Contact:

Evelyn Luciano

Luciano@ecohealthalliance.org

+1-212-380-4490/4477

- Table of Contents

| - Title Page | 1 |
| --- | --- |
| - Table of Contents | 2 |
| - Executive Summary | 3 |
| - Goal and Objectives | 4 |
| - Narrative | 5 |
| - Technical Approach | 5 |
| - Table of partner organizations in Sabah | 14 |
| - References | 17 |
| - Proposed Outcomes/Results | 17 |
| - Management Plan and Key Personnel | 20 |
| - Annex A | 24 |
| - Implementation Work Plan and Time Line | 25 |
| - Monitoring and Evaluation Plan | 42 |
| - Annex B: Resumes for Key Personnel and Long-term Professional Staff | 50 |
| - Peter Daszak | 51 |
| - Tom Hughes | 55 |
| - Jonathan H. Epstein | 59 |
| - William B. Karesh | 63 |
| - Sarma B. Aralas | 67 |
| - Zakariya Belkhamza | 71 |
| - Datuk Dr Laurentius N. Ambu | 74 |
| - Sarah E. Elwood | 77 |
| - Elizabeth Loh | 80 |
| - Kris Murray | 83 |
| - Carlos Zambrana-Torrelio | 86 |
| - Catherine Machalaba | 90 |
| - Evelyn Luciano | 93 |
| - Elizabeth I. Eckel | 95 |
| - Signed Letters of Commitment from Key Personnel | 97 |
| - References for Key Personnel | 104 |
| - Annex C: Institutional Capabilities and Partnerships | 108 |
| - Letter from Malaysian Palm Oil Council | 121 |
| - Letter from Hospital Queen Elizabeth | 122 |
| - Letter from HUTAN | 124 |
| - Letter from LEAP | 125 |
| - Letter from Danau Girang Field Center | 127 |
| - Letter from Department of Veterinary Services Malaysia | 129 |
| - Annex D: Relevant Past Performance Information | 131 |
| - PREDICT - Wildlife SMART Surveillance | 131 |
| - Risk of Viral Emergence from Bats | 133 |
| - HSD: Collaborative Research: Human Related Factors Affecting Emerging Infectious Diseases | 135 |
| - EcoHealthNet: Ecology, Environmental Science and Health Research Network | 136 |
| - The Ecology, Emergence and Pandemic Potential of Nipah Virus in Bangladesh | 137 |

- Executive Summary

Disease emergence is driven by complex socioeconomic and environmental changes, which include land use changes due to deforestation, agricultural expansion and habitat degradation.  EcoHealth Alliance (EHA) has spent the last 40 years addressing these complex environmental and social challenges through multidisciplinary collaborative international networks. These include long-term partnerships within Malaysia, such as our 15-year old partnership with the Malaysian Government to tackle Nipah virus (the Henipavirus Ecology Research Group) which has now been formalized at the Ministerial level by an MOU among EHA, and the Malaysian Ministry of Health, Dept. of Veterinary Services, and Wildlife and National Parks (PERHILITAN).  For the IDEEAL project, we will leverage our experience building successful partnerships, developing outreach programs, and our specific expertise in modeling disease emergence and its economic implications to address the challenge in this RFA.

Our modeling strategy will draw on existing datasets curated by EHA, datasets identified through partners and government agencies in Malaysia, and new data collected through the DEEP FOREST project, managed by EHA.  Using a Bayesian statistical framework, we will examine how changes in land cover and land-use has affected the incidence of disease over the last few decades. We will calculate the value of damages from past disease outbreaks, and construct a model for expected damages under different land use scenarios, and different severity of outbreaks.  We will parameterize our models with data that explicitly measure the different rates of exposure to disease by men and women (of all ages) attributable to gender-specific roles in society. To address gender issues effectively, we will solicit the direct participation of women and children in our behavioral surveys to clarify the implications of gender-specific roles.

We will develop a center of excellence for economic analysis of land use change and health outcomes.  The Center for Development and Health (CDH) will be an international resource for the science and policy of land use change and the cost of disease emergence and will be based at the School of Business and Economics at the Universiti Malaysia Sabah (UMS).  The CDH will be a forum for a state-of-the-art multi-disciplinary think tank composed of experts from the fields of economics, disease ecology, agriculture, forestry, wildlife conservation, and health as well as industry experts involved in land development in Sabah.  We will collaborate with these experts to develop outreach materials and strategies, and the CDH will serve as a platform from which   we will disseminate information and toolkits that provide all relevant stakeholders—community members, private industries, researchers, government officials, and policy makers—the ability to translate the science into action, with particular consideration for gender sensitive issues.

At the end of the project period, we will have produced four main deliverables that satisfy the proposed IRs and sub-IRs. They are: 1) quantitative models of land use change and disease emergence to use in local and regional decision making and that can be generalized or modified for other applications 2) the Center for Development and Health at UMS to serve as a permanent Center of Excellence and platform for continued research and training, stakeholder engagement, and as a regional and national source of information on the economic relationships of land use change, disease emergence, and subject area gender-related issues, 3) gender-sensitive health impacts toolkits for promoting best practice approaches and translate project findings to ensure gender equality benefits, and 4) scientific translation communications toolkits that translate research and modeling results to be useful for policy makers, private companies and government organizations, and civil society stakeholders.

IV. Goal and Objectives

Overall aim:  In partnership with the Universiti Malaysia Sabah School of Business and Economics, the Sabah Wildlife Department, and other governmental and non-governmental stakeholders, we will develop a functional, field-trialed, quantitative set of models which capture gender sensitive emerging infectious disease-related health savings as a function of land use; produce actionable model outputs and analyses to help promote reduced-impact land utilization by governments, private sector stakeholders and civil society; build alliances amongst a diverse range of stakeholders; integrate cross-disciplinary approaches in gathering, analyzing and disseminating information; and establish a training, learning, and resource sharing platform in Sabah to sustain program impacts after the project.

Models will be parameterized using empirical data from our extensive collection of datasets as well as other existing datasets and new data generated by USAID investments including EPT PREDICT and our DEEP FOREST project.  We will create a Center of Excellence in Sabah to act as an outreach resource for key stakeholders in Sabah, Malaysia, and USAID.  The Center will disseminate our findings and actively communicate them to local stakeholders including women’s groups and indigenous communities who may be directly impacted by land use change.  We will work directly with government partners in Sabah and industry stakeholders to translate the outputs of our models into policy-level actions and corporate sustainability strategies that will reduce the risk and mitigate the impact of land-use and climate associated zoonotic disease outbreaks, with particular attention to reducing gender-based adverse health events. This project will be scalable and will serve as a prototype for similar national and regional initiatives in other parts of Asia or the world that are particularly vulnerable to EIDs.

V.  Narrative:   Section A - Technical Approach

Disease emergence is driven by socioeconomic, demographic and environmental changes which include deforestation, agricultural expansion, habitat degradation and other land use changes. These changes are particularly important for zoonotic diseases, which account for ~60% of all EIDs, and almost all recent pandemics (Taylor et al., 2001; Woolhouse & Gowtage-Sequeria, 2005). Land use change is the most significant driver of disease emergence.  Analysis of our database of all known EIDs (from Jones et al., 2008) shows that around one-fifth of EID events, an even higher proportion of zoonotic diseases, and most emerging pandemics were associated with land use changes, including agricultural conversion, deforestation and activities associated with the extractive industries (e.g., mining, logging). The importance of land use change in the process of disease emergence make it a key target for control strategies (Patz, Daszak et al., 2004; Jones et al., 2008; Keesing et al., 2010; Burnside et al., 2012).  However, to create effective control measures requires: 1) a detailed mechanistic understanding, supported by field data, of how land use change drives disease risk; and 2) a strategy to control this problem that will be supported by local stakeholders (industry, government and local communities) because these stakeholders play a role in promoting, legislating or engaging in activities that lead to land use change, and are vulnerable to their adverse consequences, including disease emergence.

Our extensive previous work on modeling EID dynamics; on the emergence Nipah virus, West Nile virus, SARS and avian influenza; and our current work in USAID EPT PREDICT (including the DEEP FOREST project) provide strategic direction for this proposed.  We have shown that land use change leads to disease emergence by increasing opportunities for contact and pathogen spillover between wildlife and humans and by perturbing host-pathogen ecological dynamics that promote cross species transmission (Patz, Daszak et al., 2004; Murray & Daszak, 2013) (Figure on right). These factors act either together or independently, and because of the diversity of reservoir hosts, vectors, and human behavior in a region, they create a complex, dynamic system.

To understand this complexity requires collection and analysis of data on all of the processes involved in land use change that affect disease risk.  For example, road building or other economic development activities in intact forests usually involve movement of people into previously uninhabited areas, which increases their contact with wildlife and their exposure to the novel pathogens they carry, as well as vectors such as mosquitoes. Different sectors of the community tend to have different types and degrees of contact with wildlife, and this also varies with age and gender.  In addition, land use change modifies existing habitat with often dramatic impacts on the abundance of disease reservoirs and vectors (Norris, 2004; Patz & Olson, 2006; Olson et al., 2010).  All of these factors can alter disease risk. Once a pathogen has spilled over into a single person, or established itself in a community, the risk of spread depends on the amount and type of contact among people, and their movement into and out of the interface where spillover happened.  Finally, assessing the role of disease emergence in the economic cost/benefit analysis of land use change requires specific information on the frequency of disease emergence and outbreaks, and their impact on individuals, on communities and on production, trade and travel. Our approach for the IDEEAL Project brings together these components to produce actionable information to local and regional stakeholders for informed decision-making.

Cross-Disciplinary Approaches

EcoHealth Alliance (EHA) has spent the last 40 years addressing complex environmental and social challenges by building multidisciplinary teams via collaborative international networks. These include long-term partnerships within the region, such as our 15-year old partnership with the Malaysian Government to tackle Nipah virus (the Henipavirus Ecology Research Group) which has now been formalized at the Ministerial level by an MOU among EHA, and the Malaysian Ministry of Health, Dept. of Veterinary Services, and Wildlife and National Parks (PERHILITAN).  Our team has provided multi-disciplinary training, research support, and policy guidance to Sabah Wildlife Department since 1988.  Our work in the region includes consortia that we founded such as the One Health Alliance of South Asia, a partnership of SAARC country government agencies for health, agriculture and the environment, and the Consortium for Conservation Medicine, set up in 1997 to link leading US institutions of public health, wildlife health, environmental sciences, medicine and veterinary medicine. Official affiliated partners of EHA (www.ecohealthalliance.org/partners/all_partners) include key government departments in the USA (e.g. CDC, NIH, USDA), in Malaysia (e.g. Dept. Veterinary Services, Sabah Wildlife Dept.) and globally (e.g. OIE, FAO, WHO, and IUCN).  We work closely with leading corporations involved in agricultural development in the region (e.g. Cargill, Mars, PepsiCo) and leaders of industry globally (e.g. Bayer, Exxon). Our economics research includes partnership in the NIH-NIGMS MASpread project which analyzes the economic impacts of disease on trade.  Our outreach programs include multidisciplinary training programs such as EcoHealthNet, which provides disease ecology training in more than 10 countries. Finally, EHA is one of four partners in USAID EPT PREDICT, with specific responsibility for zoonotic disease surveillance in Malaysia, leadership in all PREDICT modeling activities, and the DEEP FOREST project.

For this project, we will leverage our experience building successful collaborative programs, in public outreach, and our expertise in modeling disease emergence and their economic implications to address the challenge in this RFA.  We have already established close working partnerships with experts from the fields of wildlife health, economics, conservation biology, public health, and social advocacy in Sabah, including the Sabah Wildlife Department’s Wildlife Health Unit (our DEEP FOREST team), The Danau Girang Field Centre, HUTAN, the Sabah Department of Health, the Malaysian Palm Oil Council,and the School of Business and Economics at the Universiti Malaysia Sabah (UMS).

We plan to create a center of excellence for land use change and health (the Center for Development & Health (CDH) based in the School of Business and Economics at UMS.  This will engage experts in agricultural science and policy from within UMS, including the Department of Sustainable Agriculture, and State government experts in economic planning and development from the Sabah Economic Development and Investment Authority (SEDIA) as well as several other local NGOs and government agencies.  The CDH will link key departments within the university to private and public institutions in Sabah whose members can provide real-world insight into the challenges of development.  It will create training and educational opportunities for men and women, which provides students with a multidisciplinary framework that links environmental and ecological science with economics, social science, and political science. This will provide long-term sustainability by producing a generation of graduates ready to address the challenges of responsible land development in Malaysia and the broader region.

Modeling strategy

We propose a 3-phase approach, with each phase informing the next: 1) model the relationship between land cover/land-use change and the likelihood of pathogen spillover, disease outbreaks and emergence, utilizing available data and novel data from DEEP FOREST; 2) develop an avoided damages model to understand the economic consequences of these linkages; and 3) examine potential for integration of these models into a total ecosystem value model. Although the focus of this proposal is #1 and #2, we will evaluate the potential to achieve #3 in the early stages of the project.  Progress in #3 will place the goals and results of the current RFA in broader context of ecosystem use and contribute to future policy and planning efforts.

1. Modeling the relationship between land-use change and disease outbreaks/emergence

This objective will be achieved by analyzing and modeling data from two domains: 1) A detailed analysis of available data; and 2) analysis of newly generated data primarily from DEEP FOREST.  The first domain uses a correlative approach and provides insight from a very broad range of data sources while the second focuses in on the mechanisms of disease emergence (primarily contact rate and host-pathogen ecology) to provide novel insights on the links between land-use change and disease emergence.

Available data: Our first step will be to examine how changes in land cover and land-use has affected the incidence of disease over the last few decades. We will focus on a range of disease outcomes, including localized spillover events, small outbreaks, larger scale outbreaks and pandemic emergence. We will assess how land use has changed from pristine conditions using historical data on land cover, and we will match this with recent historical data on disease outbreaks and emergence that we have already amassed as part of EHA’s modeling program, as well as from other sources.  For land use data, we will use our datasets on land cover/land use for natural systems, croplands, grasslands, urban areas and areas used for livestock, originally sourced from FAO, HYDE-IMAGE, GLOBIO3, European Commission, USGS, NASA and others, but that have undergone subsequent processing for our applications in studying disease emergence processes. Our spatial database also includes current state, forecasts (2050) and back-casts (1700) of land cover/land use. These datasets are highly variable in spatial resolution, ranging from country level to 500 m of resolution (e.g., classified land cover MODIS-Terra). We have access to downscaled scenarios of land use and climate change under various projected policy frameworks from Rio+20 (e.g., business as usual vs aggressive policy changes). We have also gathered, vetted and produced a series of socio-economic and ecological variables thought to drive disease outbreaks, including global human population density (GPW & GRUMP), gross domestic product (World Bank), mammal diversity (IUCN), human conflict (Political Instability Task Force), climate (WorldClim) and others. Currently we are in the process of designing methods to downscale some of the country level data to finer spatial resolution models, which in pilot analyses significantly enhances our ability to detect trends among noisy and biased datasets.

For disease data, we will use EHA’s online EID database (the ‘Sicki Project’ – www.ecohealthalliance.org/programs/35-the_sicki_project), which serves as a platform to enter information on EIDs, including standardized pathogen taxonomy, bibliographical references and spatial information.  We will build a database of outbreaks and other relevant information (e.g., drivers of outbreaks) relevant to this RFA. To do this, we will ingest data from public databases such as GIDEON, the WHO Disease Outbreak News reports and from reviewing the literature. In conjunction with our Malaysian partners and the Center of Excellence, we will also identify relevant local and regional datasets (e.g., government reports or articles in local languages, such as Bahasa-Melayu, Bahasa-Indonesia, Mandarin and Cantonese).

To account for temporal variability in emergence, we will perform analyses at different temporal and spatial scales. For the temporal analysis, 10-year intervals will be used. We will also investigate the possibility that there is a time lag between land cover/land use changes and the emergence of new infectious diseases.  In this scenario, a change in land use may gradually alter population dynamics of a wildlife reservoir, so that after a period of time, some wildlife become much more common, and their pathogens have an opportunity for spillover.  The spatial analysis will include a multi-scale analysis focused on regional (Southeast Asia) and local (within Sabah) spatial scales. This framework of analysis will allow us to separate drivers of EIDs operating at different scales.

New data: For the second component of this objective, we will leverage the theory, methodology and results of the DEEP FOREST project to bolster and support the current proposal. Spillover of pathogens due to land use change is an ecological process based on the community ecology of pathogens within wildlife populations, and their interactions and disease-relevant contact with people. Contact rates are notoriously difficult to acquire during disease outbreak situations.  However, the EHA-led DEEP FOREST project is tasked with specifically measuring disease-relevant contact among people, livestock and wildlife across an urban-to-rural gradient in Sabah.  It also will capture data on the community ecology of wildlife hosts over this gradient.

We will use data obtained by the DEEP FOREST team to inform the likelihood of EID spillover within specific regions undergoing land use change. In Borneo, the DEEP FOREST project sites are in the region of Sukau near one section of the Kinabatangan River. The sites are distributed along a disturbance gradient from highly disturbed (near the town of Sukau) to largely pristine and intact (Gomantong Forest Reserve). Here, wildlife sampling and surveys of human contact with wildlife are taking place at 9 sites along the gradient (3 sites in each of three levels of the gradient). These surveys provide samples that are being fed into our PREDICT pathogen discovery program to provide information on the prevalence/incidence of known pathogens and completely novel pathogens from viral families which are known to contain zoonotic agents. DEEP FOREST human contact surveys will provide critical information on how likely a person is to make contact with wildlife directly, indirectly or inadvertently, and depending on age, occupation and gender. This gender specificity may be critical because some occupations consist of mainly male workers (e.g. palm oil plantations, hunters), and we expect exposure rates to differ significantly both quantitatively and qualitatively between men and women.

These data will inform our model of the likelihood of pathogen spillover for a given contact pattern, corrected for the patterns we expect to see in the viral pool across the land-use change gradient. This means that we will be able to compare the likelihood of an individual hunted animal being positive for a pathogen at any site along the gradient, and of a specific risk behavior occurring there. Finally, to calibrate the likelihood of such a scenario leading to infection of a person, we will use data from published studies of zoonotic spillover for various model viruses. This level of predictive capacity has never been achieved before, and is uniquely possible by a group that brings together expertise in modeling EIDs and has access to the unique  datasets that DEEP FOREST will produce.

Statistical framework: We will evaluate and compare regression models used to analyze count data (e.g., negative binomial, Poisson, zero-inflated under a hierarchical Bayesian framework) while controlling for other factors (including research bias) that influence disease detections. We will make use of the following general Bayesian model:

Yi~Poisson(μi) or Yi~Binomial(μi)

gμ=β0+β1X1+β2X2+…+εi

εi~N(0,σε2)

where g(μ) is a link function (see below), β0, β1, etc., are parameters to be estimated and ε is an error term with a normal distribution. Link functions are used to indicate whether the predictor variable (Yi) represents a Poisson distribution (e.g., outbreak counts) or a Binomial distribution (e.g., presence or absence of a new disease). Links are defined as gμ=log⁡(μ) for count data (e.g., number of outbreaks) or as gμ=log⁡μ(1-μ) for presence/absence data (an EID event.

Bayesian analysis has the advantage over frequentist methods under some circumstances for its ability to specify prior probabilities to parameters (e.g., through literature reviews and consultation of experts). We will assign prior probabilities using two different approaches: 1) Uninformative prior: an inverse gamma distribution will be assigned for each parameter. An uninformative prior approach will help us develop a generalizable model and make it relevant for other parts of the world where disease-related data may be scarce. 2) Informative prior: to achieve greater specificity and regional relevance, we will investigate the use of additional sources of information for integration into this framework. For example, we may be able to leverage a range of data sources from the literature, from our DEEP FOREST project, and EID emergence and outbreak databases. Bayesian models with informative priors can help make the most of available data, narrow parameter estimates, reduce uncertainty in those estimates, and reduce new data requirements (i.e., sample sizes) in order to achieve equivalent statistical power for inference. For example, they will give us the advantage of being able to incorporate system-specific data that we have collected under our other programs in order to produce a tailored Bayesian model for regional and local conditions. Markov Chain Monte Carlo (MCMC) methods with a Gibbs sampler algorithm (i.e., each randomly sampled value is conditional to the previous value) will be used to estimate the posterior probability of the mean and percentiles.

2. Avoided damages modeling

Our preliminary analyses and other studies strongly suggest that deforestation and other land-use practices contribute to disease emergence and outbreaks. Intact forests can thus be considered a ‘public good’ from a disease emergence perspective – that is, they provide a service to society through protection against infectious disease outbreaks. Unlike harvesting natural products for use or profit, this service does not involve society’s direct use of the ecosystem, making the valuation of this public good a challenge. One way to measure the benefits of disease regulation from intact forests is to value the damages that are avoided by keeping the ecosystem intact (Groot et al., 2010). In practical terms, we expect that the costs of disease control will increase with deforestation, i.e. with decreasing forested area, and we will examine this relationship in the proposed work.

Calculating the Expected Damages of Disease Outbreaks

Our approach is based on work EHA has developed within our MASpread project in which we are examining the anthropogenic impacts that contribute to the spread of disease and their associated costs. This involves adapting the concept of hedonic pricing models (models that decompose the price of an item into separate components) to value EID damages.  We use a set of well-studied emerging diseases each with different characteristics representing typical impacts from disease emergence – i.e. those causing spillover vs. human-to-human transmission vs. pandemic outbreaks. Our damage functions are assessed by teasing apart the wide range of potential outcomes of these diseases into their morbidity, mortality, and impacts on travel and trade – i.e. factors that have already been valued in separate studies. Our strategy is to then use that function to predict the damages of other diseases that have similar characteristics to different members of this subset based on the same explanatory variables.

A general description of this model takes the form of:

Where:

Di=Damages from disease i in 2013 US dollars

X1i to Xni= Morbidity, mortality, loss of worker days, duration trade restrictions, etc.

β1 to βn are estimated parameters representing the effect size of each variable (X) on the damages

ε = error term

Our categorization of EIDs by type of economic damages, and derivation of a different damage function for each category make our estimates more robust. Using the results from the count data model (see 1 above), we will examine the expected damages under three different scenarios: 1) business-as-usual (current rate of land use conversion extrapolated forward), 2) increased rates of deforestation, and 3) no deforestation.  We will link these scenarios to the new Millennium Ecosystem Assessment policy scenarios.

We will tailor damages from the above formula (listed in 2013 US dollars) to the unit with the most impact for the system and stakeholders we are addressing (e.g., USD, Thai Baht or Malaysian Ringgit). Generally speaking damages will include the direct costs associated with human health impacts and mortalities, as well as other costs such as impacts on travel and trade.

Health impacts: We will quantify the ‘value’ of health, healthiness or the perception of healthiness using a value of statistical life (VSL) and value of a statistical life year (VSLY) framework, i.e. typical inputs into cost-benefit analyses (CBA). VSL is the marginal dollar value attributable to a human life, while VSLY is the annualized equivalent (value of a year of healthy life). VSLY will be particularly relevant here because damages are often non-fatal and this measure encapsulates loss due to disability or other reduction in quality of life over a fixed time period. As a starting point, we will work from previous estimates of these parameters. These exist mainly for high-GDP countries in Europe, North America and elsewhere and we will therefore adapt them to local conditions. A previous review (from Australia) suggests a mean VSL of ~A$9.4 million (median of $6.6M), and a mean VSLY of A$433,437 (median of A$119,589). These mean figures are also affected by sector, e.g. health (A$4.0 million), transport ($7.9 million), ‘other’ (consumer choice, crime and fire safety – $8.5/$6.0 million), environment ($11.2/$8.1 million) and occupational safety ($11.1/$7.4 million), highlighting the need to understand the human population in the area of study if we are to attribute economic values to disease emergence due to land use change.

Healthy life is a unique and valuable commodity, which does not fit easily into more traditional economic benefits frameworks. For this reason, several metrics have been developed that can attribute costs to specific subcategories (e.g., infectious diseases). These include fatalities averted/life-years saved (LYS), and several quality of life metrics (QoL e.g., DALY – disability adjusted life years, and QALY – quality adjusted life years). Both DALYs and QALYs incorporate mortality and morbidity components. DALY valuation is the preferred approach here due to its extensive use in previous studies and because a pre-existing framework based on expert weights of various health states is available. A DALY value of 0 equates to perfect health, such that DALYs are already in the form of something to be averted.

Other damages: The economic impact of a disease outbreak often extends beyond losses from morbidity and mortality. SARS claimed 774 lives out of 8,096 infected, but the majority of the economic burden (perhaps as high as US$30-50 Billion) resulted from losses in the travel and trade sectors (Keogh-Brown 2008). For each outbreak, depending on its scope (local, national, multi-country), we will gather data on a variety of other indicators that contribute to the overall economic burden of the disease. These may include treatment costs, the number and value of livestock culled in control measures, travel and trade restrictions and other relevant costs.

3. Total Ecosystem Value Modeling

Although the RFA does not call for quantification of the total ecosystem value (TEV), the avoided costs calculated in our model could be incorporated into other models to determine the economic and societal value of converting land  (adapted from Barbier, 2009).  This will have particular relevance to policy makers in Malaysia and elsewhere in Tropical regions under pressure for development.

maxc(t)V=0∞RD-Cc-BA-O(A)e-rtdt

Where:

R – rent from converted land

C – cost of conversion of intact land to developed land

B – benefit from intact ecosystem

D – developed land

c – area of land converted in each period

A – undeveloped/intact land

O – avoided cost of disease outbreaks

O'(A))<0, O''(A))<0  	as intact land decreases, the cost of an outbreak increases at an increasing rate.

Generalizability

We anticipate that the results generated from our approach will represent a significant addition to the state of the knowledge on the value of a specific ecosystem’s disease regulating services. The tools that we develop above will have the potential for widespread adoption, providing it is correlated to local conditions. We will therefore develop a checklist to accompany the tools that will contain information on how to tailor the models to different regions and different types of ecosystems based on our recent research on the spatial drivers of emerging diseases. For example, we have analyzed all previous 450 EID events to assess the relative role of land use change in driving their emergence, and how this varies in importance in different regions globally.  These data were published in our paper on biodiversity and health in Nature (Keesing et al., 2010) and will be made available with the tool.  Similarly, for our models to have relevance to other regions (e.g. South America, Africa), data will be required on how human contact and pathogen diversity patterns vary with land use change in these regions.  Data from DEEP FOREST Uganda and DEEP FOREST Brazil, as well as our IDRC-funded project in Southern Brazil, will be available to make these correlations.

Gender Specification

Men and women experience the risks and costs of infectious diseases differently.  This likely has specific relevance to land use change, especially with regards to extractive industries, with manual labor health costs, and the economic benefits of work largely falling to men and social and environmental costs falling to women. In many regions, gender also determines one’s access to resources, particularly land. The DEEP FOREST Human Contact (DFHC) surveys are providing information we can use to assess gender specific risks and costs of disease along a land-use change gradient. These surveys were designed as part of a collaborative project between EPT PREDICT and PREVENT and are being rolled out at our DEEP FOREST sites in Sabah, Brazil and (in the first year of this project) in Uganda.  In Sabah, we hypothesize that the specific costs of disease to individuals, as well as to the economy, will be gender-specific. For example, although men and women often work in the same places, women are often concentrated in distinct sectors or are responsible for distinct activities exposing them to different risks compared to men. Division of labor, recreational activities and occupations related to animals (hunting, butchering, caring for domestic animals, etc.) are also influenced by social factors. Similarly, men are often engaged in manual labor activities in areas away from urban centers. For example, in Sabah there is a strong bias towards male workers in oil palm plantations, which may expose them to specific hazards associated with this form of land-use change.

Our working hypothesis will be that men and women have different rates of exposure to diseases that may be attributable to gender-specific roles in society. To address gender issues effectively, we will solicit the direct participation of stakeholders including women to clarify gender roles and their implications in project activities. Quantitative data collected from the contact surveys will be disaggregated by gender to highlight the differences in traditional roles and learned behaviors of men versus women based on gender attributes. Gender-specific analyses will also take into account other variables including income, race, ethnicity, and other social characteristics, as well as explicitly address the specific differences between young girls and boys, and adult women and men. To assess the effect of both gender and age on relative risk of infectious disease emergence, the following sub-groups have been chosen to survey as part of the DEEP FOREST project: Adult women (age 18 and older); Adult men (age 18 and older); Boys (age 10-14); Girls (age 10-14).  We will liaise closely with the USAID EPT PREVENT team that is conducting this work collaboratively with EHA in Borneo.

Using gender-relevant information from the DEEP FOREST surveys, we will examine: Knowledge, beliefs, and perceptions; what beliefs and perceptions shape gender identities and norms; human practices and distribution of labor – what are the gender roles that dictate the activities in which men and women participate; how men and women engage in different activities relevant to land use change and rates of exposure to different animals; and time and space – how women and men spend their time. Understanding the role of gender in disease risks and costs will be fundamental in planning the prevention, detection and treatment of illness.

In addition to the gender specified data collected from the human contact surveys, additional data will be collected from stakeholders and used to inform the gender-sensitive health impacts toolkit to be produced. Additional data may include: local legal and cultural frameworks with regard to land ownership, community leadership; possible impact on local gender relations; barriers and facilitators of gender sensitive data collection; and levels of female participation in decision-making structures. Additional data collection methods may include community mapping, stakeholder analysis, focus groups, and key informant interviews with women, local government, and representatives from the private industry.

Outreach

Stakeholder engagement

We will develop a stakeholder engagement program around the principle that decisions on land use management that minimize EID spillover risk can contribute to widely distributed health savings.  These occur due to averted disease control and containment costs; avoided costs of individual health care; avoided costs to livestock health and productivity, trade and tourism status, financial markets stability; and the preservation of individual, gender-sensitive livelihoods and earnings potential.  Our engagement will build upon 1) existing partnerships established in Malaysia (and Sabah in particular) through EHA’s work with our DEEP FOREST project, the USAID EPT PREDICT program, and our 11-year partnership with the Malaysian Govt. and other agencies; 2) the organizations we have identified and contacted for the purposes of developing this proposal, and 3) organizations working with the above agencies and partners on other related programs.  Stakeholders will include government agencies (both Sabah State and Federal) for wildlife, forestry, agriculture, development, tourism, public health, and social development.  Para-governmental and Non-governmental organizational stakeholders will include Yayasan Sabah (Sabah Foundation), the Malaysian Palm Oil Council, Forest Research Centre Sabah, Sabah Women's Action-Resource Group, and the Sabah Tourism Association, The LEAF (Lowering Emissions in Asia’s Forests) Program and its relevant partners such as The Centre for People and Forests. Additional private sector stakeholders will be identified by existing partners, their industry organizations (such as above) and those working in communities surrounding project activity sites (e.g. tourism companies, logging companies, plantation managers and owners, livestock and small-holder farmers, health clinics, shop owners, restaurant owners, lodging and logistics, etc.). University stakeholders will include Universiti Malaysia Sabah and the members of the Malaysia One Health University Network (MYOHUN).

The goal of our stakeholder engagement will be (in both phases of the project) to improve relevant data (knowledge) acquisition and to establish target audiences and users of the project so that we can disseminate data and findings, models, tool kits and handbooks, organizational platforms, and other deliverables. Early in Phase 1 of the project, stakeholders will be identified, briefed on project goals and invited to participate.  In partnership with the Sabah Wildlife Department, following the release of the RFI, we have already held an initial informational meeting to identify interested parties and discuss the concept of the center of excellence. This has allowed us to better understand the stakeholder landscape and to identify potential sources of data for use in our modeling activities.  If funded, we will organize our first formal meeting(s) of stakeholders within 4 months of project initiation, and schedule regular (quarterly) meetings and sub-group meetings out of that initial gathering. Stakeholder identification and inclusion will continue through the life of the project.  We will use facilities at the Universiti Malaysia, Sabah to arrange and hold stakeholder meetings (see Center of Excellence).

Table of partner organizations in Sabah

| Organization Name | Role | Key contacts / names |
| --- | --- | --- |
| Sabah Wildlife Department | Provide data on biodiversity, land use, DEEP FOREST | Dr. Laurentius Ambu (Director), Dr. Sen Nathan, Puan Jumrafiah |
| Department of Agriculture | Data on land conversion, crop production | Director |
| Sabah Forestry Department | Data on Forest cover and historically cleared land | Director |
| Sabah Parks | Data on protected land | Director |
| Yayasan Sabah | Timber concession data and educational outreach expertise | Dr. Waidi |
| Malaysian Palm Oil Council | Coalition of large-scale Oil Palm Plantations | Dr. Kalyana, Sundram. Deputy Chief Executive Officer and Director, Science & Environment |
| Malaysia Palm Oil Board | Malaysian Govt. Agency overseeing Oil Palm industry | Director |
| School of Business and Economics, University of Malaysia, Sabah | Center for Development and Health | Assoc. Prof. Dr. Hih. Arsiah Bahron (Dean of SBE), Dr. Sarma Aralas, Dr. Zakariya Belkhamza |
| SEDIA (Sabah Economic and Development Investment Authority) | State agency responsible for development and economic growth | Director |
| World Wildlife Fund - Malaysia | Conservation NGO | Dr. K. Yoganand |
| HUTAN | Conservation and social responsibility NGO | Dr. Marc Ancrenaz |

Public-Private partnerships

We plan to develop a powerful public-private partnership that produces multiple initiatives of mutual benefit – whereby industry advises our model building on the details of land-use change projects, and we advise industry and our government agency and other private partners on risk of disease outbreaks and emergence. EHA has extensive experience working in exactly this role in the region and we have developed working or growing relationships with government authorities, academia, the private sector (e.g. the Malaysian Palm Oil Council http://www.mpoc.org.my/, and the relevant regulatory/watch-dog groups, such as the Roundtable on Sustainable Palm Oil http://www.rspo.org/) and local government agencies such as the Sabah Department of Health and the new Sabah Wildlife Department Health Unit, which EHA helped build in 2012. We will leverage these partnerships in both Phase 1 and Phase 2 of the project and have garnered letters of support from our main partners.

Collaborating with the private sector is essential to any initiative that hopes to influence policy and community involvement.  It is particularly important in this project because government and industry partners are both involved in the activities that drive EIDs and also suffer from their impacts. Engaging industry partners such as the palm oil sector from the beginning will allow us to draw on their expertise and minimize potential conflicts as new activities and policies evolve. EcoHealth Alliance, in partnership with Chatham House and USAID, recently facilitated a roundtable discussion with key extractive industry stakeholders to present the current state of science linking natural resource industries and infectious disease emergence. We found that industry representatives were highly receptive to our characterization of disease emergence scenarios, in particular where they create health threats to their worker, and negative public perception of the industry. Similarly, our experience consulting for other global industry leaders including the food sector (e.g. Cargill, Mars, PepsiCo), the agricultural sector (e.g. Bayer Crop Science) and consultancy services (e.g. McKinsey & Co.) demonstrates that industry is a willing partner in initiatives that produce a fair evaluation of risk, particularly when we can advise companies directly on health threats to their workers, or threats to the public perception about their business.  We have used these experiences to develop our engagement strategy.  For this project, we will aim to garner financial support and in-kind contributions from the private sector to assist in the longterm sustainability of the project outreach.  At EHA, our approach to this has been to build a relationship with the companies, trade groups and other private sector institutions of relevance, and assist them in developing their corporate sustainability programs in a way that benefits people on-the-ground in regions where they have active production facilities.  This is the approach we have used previous with Bayer, PepsiCo, Exxon, Cargill and others, and our initial discussions with Malaysian Palm Oil Council have been encouraging about their financial support of projects that would fit under the IDEEAL program.

Utilizing the Center of Excellence in Sabah (discussed below) we will host regular roundtable events for key players in the region from major commercial agricultural industries such as palm oil (the Malaysian Oil Palm Council, IOI Corp, TH Group, Kwantas Corp and Selangor Agriculture Development Board) rubber, (the Rubber Industry Board, Rubber Settlement Scheme) and cocoa (Malaysian Cocoa Board, Tech Guan Cocoa company).  At these meetings, we will leverage relationships with our current partners including Mars, Cargill, PepsiCo and others that are active in Southeast Asia to develop projects that incorporate data on EID threats to their workers, and on their activities in the region.  We will mutually develop plans with private partners to trial out our toolkits, and develop small-scale on-the-ground tests of our approaches.  We envisage that this will include working with data on population exposure to wildlife at sites where individual partner companies are actively working and developing.  These partnerships will help ensure long-term sustainability of both data collection, research, and implementation of best practices, and the continued development or the proposed center of excellence.  We will also investigate in collaboration with key government and industry stakeholders the potential for leveraging other market-based initiatives that could strengthen the protection of carbon stocks, biodiversity, health and other social objectives (e.g., REDD+).

Center for Development and Health (CDH)

We will develop a center of excellence for economic analysis of land use change and health outcomes.  The Center for Development and Health (CDH) will be an international resource for the science and policy of land use change and the cost of disease emergence and will be based at the School of Business and Economics at the Universiti Malaysia Sabah (UMS).  The CDH will be a forum for a state-of-the-art multi-disciplinary think tank composed of experts from the fields of economics, disease ecology, agriculture, forestry, wildlife conservation, and health as well as industry experts involved in land development in Sabah.  Scientific experts and policy makers will hold roundtable discussions with industry leaders and discuss project findings and current land use practices in order to create guidelines on how to reduce the risks of disease emergence as a consequence of land use change and development.

By generating robust quantitative models of the cost of disease emergence and interventions and serving as a repository for data related to development and land use change, the Center will aim to establish a reputation for being an international leader on this subject.  In order to translate the findings of this project into actionable policy, the CDH will develop communication and outreach strategies, including a website and social media, and we will work with local public and private partners to disseminate project findings to stakeholders in Sabah.  We will create long-term sustainability by providing mechanisms for advanced multi-disciplinary training at UMS by offering short courses and seminars to graduate students and professionals related on the subjects of sustainable land use, conservation, disease ecology, economics, and global health.

Phase one of this project will entail establishing the center at UMS and identifying local stakeholders who will be engaged in center activities.  On May 14, 2013 EcoHealth Alliance and Sabah Wildlife Department convened a meeting of potential stakeholders in Kota Kinabalu (see table of potential stakeholders).  In attendance were representatives from Sabah state government such as the Department of Veterinary Services, the Sabah Wildlife Department, and the Department of Health.  Also in attendance were members of academia and local NGOs including the University of Malaysia, Sabah School of Business and Economics, HUTAN, WWF Malaysia, LEAP (Land Empowerment, Animals, People) and the Danau Girang Field Center.  We are currently working with the Dean and several faculty members of the Business school to link the modeling team from EcoHealth Alliance with faculty to construct economic models based on a scenarios approach of disease emergence.  We will also work with UMS and Sabah Wildlife Department to identify and regularly convene relevant stakeholders from Sabah who will participate in the meetings held at the CDH.  We have also engaged the Malaysian Palm Oil Council and SEDIA (Sabah Economic and Development Investment Authority) to ensure that we include private sector and business interests that are driving land use change in Sabah.  Phase 1 will also include data acquisition from available government and academic sources as well as the USAID PREDICT DEEP FOREST project.   We have begun to compile a list of available data and will continue to identify data sources during the first few months of this program.  Graduate students from the Business school will be identified to participate in model development.

Phase II will include the establishment of regular meetings at the CDH for stakeholders to synthesize project findings and generate public and policy outreach material.  We expect that the center will grow over the 3-year timeline to include scientists and other experts from Sabah and the international community who wish to learn spatial analysis or economic modeling via short courses and student projects.  The Center will be open to both male and female students and community members from Sabah. We will engage graduate students from UMS and staff from SWD to train in the Center in order to develop local capacity and create long-term sustainability for the Center’s activities.

Our proposed outreach will build on EHA’s extensive experience producing policy-relevant analyses aimed at guidelines on best practice, as well as innovative tools that can be used in capacity-building programs and training. For this project, we will introduce innovative tools to the private sector in Malaysia which will include a risk assessment tool to audit industry practices with respect to the risk of negative health outcomes.  These tools will give detailed instructions to private sector Environment, Health and Safety (EHS) Officers to ensure that the industry is aware of emerging infectious disease hazards in their facility or surrounding environment.  It will then recommend specific mitigation and control strategies should the industry not already have specific measures in place.  We will also aim to provide supplemental information to the International Finance Corporation’s (IFC) guidelines on health impact assessments (HIA).

Included in the gender-sensitive health impacts toolkit, we will identify opportunities to promote women’s leadership, communication propensity and community/familial participation in mitigating disease risks. We will produce printed and web-based materials and other educational outreach material on infectious disease risk in collaboration with the Malaysian Ministry of Health to be distributed to private partners, government agencies and other institutions.  We will organize workshops for worker populations drawing on expertise from EHA, public entities (Department of Health) and private industries.  The aim of these will be to improve understanding of and access to healthcare services and strengthen the skillset of the healthcare workforce. These workshops and interactions will provide iterative opportunities to refine and strengthen the toolkit throughout the life of the project, as well as to identify additional audiences that will benefit from the toolkit.

Data from the DFHC survey will provide private partners with information on relative risk of outbreaks and disease emergence, as well as cost of infection in men, women and children.  Data from this survey could be used by private partners in collaboration with the Department of Health to inform the design of interventions to reduce the transmission of zoonoses by 1) providing standard estimates of rates of human contact with different animal species, 2) identifying populations and sub-groups with particularly high rates of contact, 3) determining which human activities are associated with particularly high rates of contact and 4) specifying other environmental and social issues that place people at increased risk of disease transmission.

References:

Barbier, E. B. (2007). "Valuing ecosystem services as productive inputs." Economic Policy 22(49): 177-229.

Barbier, E. B. (2009). Ecosystems as natural assets, Now Publishers Inc.

Burnside, W. R., et al. (2012). "Human macroecology: linking pattern and process in big-picture human ecology." Biological Reviews 87(1): 194-208.

Groot, R. D., et al. (2010). "Integrating the ecological and economic dimensions in biodiversity and ecosystem service valuation." The Economics of Ecosystems and Biodiversity (TEEB): Ecological and Economic Foundations

Jones, K. E., et al. (2008). "Global trends in emerging infectious diseases." Nature 451: 990-994.

Keesing, F., et al. (2010). "Impacts of biodiversity on the emergence and transmission of infectious diseases." Nature 468: 647-652.

Murray, K. A. and P. Daszak (2013). "Human ecology in pathogenic landscapes: two hypotheses on how land use change drives viral emergence." Current opinion in virology 3(1): 79-83.

Norris, D. (2004). "Mosquito-borne Diseases as a Consequence of Land Use Change." Ecohealth 1(1): 19-24.

Olson, S. H., et al. (2010). "Deforestation and malaria in Mancio Lima county, Brazil." Emerging Infectious Diseases 16: 1108-1115.

Patz, J. A., Daszak, P. et al. (2004). "Unhealthy landscapes: Policy recommendations on land use change and infectious disease emergence." Environmental Health Perspectives 112(10): 1092-1098.

Patz, J. A. and S. H. Olson (2006). "Malaria risk and temperature: Influences from global climate change and local land use practices." Proceedings of the National Academy of Sciences 103(15): 5635-5636.

Taylor, L. H., et al. (2001). "Risk factors for human disease emergence." Philosophical Transactions of the Royal Society of London Series B-Biological Sciences 356(1411): 983-989.

Woolhouse, M. E. J. and S. Gowtage-Sequeria (2005). "Host range and emerging and re-emerging pathogens." Emerging Infectious Diseases 11: 1842-1847

Section B - Proposed Outcomes/Results

The overall project outcome will be the development of an evidence-based model that values emerging infectious disease avoidance as a function of land use, and application of this model in real-world land use decision contexts to reduce risk of emerging infectious diseases and to mitigate climate change toward climate-resistant low emissions development. To achieve this, EcoHealth Alliance and its partners will generate two Intermediate Results and five associated Sub-Intermediate Results:

Intermediate results

Intermediate Result 1: Availability of field-trialed quantitative models capturing gender sensitive EID-related health savings as a function of land use. This will result will be generated through two sub-intermediate results:

Sub-IR 1.2: Data gathering required to run the quantitative model

Sub-IR 1.1: Development of quantitative algorithm assessing EID spillover likelihood and cost as function of land use.

Intermediate Result 2: Improved multi-channel availability of EID-focused quantitative resources amongst civil society advocates and government policy makers. This will result will be generated through three sub-intermediate results:

Sub-IR: 2.1. Establishment of a center of excellence (the Center for Development and Health (CDH)) for additional research, analysis, and cross-disciplinary partnerships

Sub-IR 2.2: Development of a gender sensitive tool kit for communicating the health impacts of differing land use options

Sub-IR 2.3: Improved outreach and communication of translated, quantitative resources to policy makers and civil society advocates.

The full objectives and sub-objectives, activities, measurable outcome or indicator, time frame, and responsible party are listed on the “Monitoring and Evaluation” table in Annex A.

At the end of the project period, we will have produced four main deliverables that satisfy the proposed IRs and sub-IRs (see Annex A). They are: 1) quantitative models of land use change and disease emergence to use in local and regional decision making and that can be generalized or modified for other applications (described in Section A of Narrative above, sub-IR 1.1 and sub-IR 1.2), 2) the Center for Development and Health at UMS to serve as a permanent Center of Excellence and platform for continued research and training, stakeholder engagement, and as a regional and national source of information on the economic relationships of land use change, disease emergence, and subject area gender-related issues (sub-IR 2.1), 3) gender-sensitive health impacts toolkits for promoting best practice approaches and translate project findings to ensure gender equality benefits (sub-IR 2.2), and 4) scientific translation communications toolkits that translate research and modeling results to be useful for policy makers, private companies and government organizations, and civil society stakeholders (sub-IR 2.3).

The final products of the modeling components have been previously described in Section A of the Narrative.

The creation of the Center for Development and Health (CDH) at UMS will sustain the Project’s impacts beyond the project period. The CDH will provide an environment for experts to continually update data, refine models, and sustainably understand the impact of land use change on economic parameters. The Center operationalizes concepts developed by EcoHealth Alliance and its partners under the One Health approach, bringing together a multidisciplinary team to discover new information about the intersection of human and animal health, disease risk assessment, and ecology. By creating the Center within the Business School at UMS, we promote collaboration and innovation across disciplines and the formation of effective non-traditional partnerships.

The team at EcoHealth Alliance will work with the Center for Development and Health to develop communications toolkits and strategies for disseminating scientific findings to policymakers and key partners in industry, government and the public.  The aim of these strategies is to translate the our scientific analyses into actionable policies and practices for decision makers so that they can more formally integrate infectious disease and economic considerations into land use change planning and decision-making. One example of a near-term opportunity that our team will take if this proposal is successful, is to provide input to the Sabah Economic Development and Investment Authority which has developed a blueprint for development called the Sabah Development Corridor (SDC) – coordinated multi-sectoral development roadmap through 2025.  SEDIA has made a commitment to responsible development, and has called for public input into the SDC. We would have an opportunity during the first year of this program, to provide input to SEDIA for the SDC regarding considerations of the cost of health impacts of land alteration.  As we develop our models, we would continue to provide information to SEDIA regarding the costs associated with potential disease outbreaks.

In addition to working with Sabah government, we will develop outreach materials for the public, focusing on gender-specific health and economic impacts of land conversion relevant to local communities where land use change activities are planned or are currently underway.  Our local partners such as SWD, UMS, LEAP (Land Empowerment, Animals, People), and HUTAN have a long history of working with local communities on conservation and social welfare issues, and we will leverage their expertise and relationships with local communities to implement educational outreach strategies.  This outreach strategy will significantly enhance the scientific knowledge base around ecosystem services valuation of benefits derived from intact ecosystems, especially with regard to disease risk assessment. Thus, the generation of knowledge in this area will allow for communication of evidence-based findings and actions.  The policy and public outreach materials generated through the Center for Development and Health will be generalizable and adaptable to Malaysia-wide or regional policy considerations related to land use decisions.

The gender sensitive health impacts toolkit will include practical “how-to” methodologies, tools, and guides designed to facilitate the integration of gender issues into health policies and programs. It is designed for government policymakers, private industry, program managers, and community health workers to explore different strategies, media, and messages about gender and to communicate the EID-related human health impacts and economic implications of potential land use decisions.

The toolkit will provide a roadmap for translating the results of the quantitative model into actionable practices and policies. It will be designed to communicate disease risk assessment results effectively, with specific attention to unique considerations of women and their disease exposure risks. It will enable such diverse groups as civil society advocates, private industry, and government policymakers, to operationalize gender sensitive policy communication strategies. Finally, because mainstreaming gender falls under the third Millennium Goal of gender equality, and aligns with USAID goals and policies, the toolkit will highlight the importance of incorporating women into leadership and planning capacities related to land use change decisions.

The scientific translation communications toolkits for scientific findings will disseminate and translate scientific findings into actionable policies and practices for decision makers to more formally integrate infectious disease and economic considerations into land use change planning and decision-making. This outreach strategy will tie into the generation of the findings from the models, which will drastically enhance the scientific knowledge base around ecosystem services valuation of benefits derived from intact ecosystems, especially with regard to disease risk assessment. Thus, the generation of knowledge in this area will allow for communication of evidence-based findings and actions.  Toolkits and/or outreach materials will be tailored to the various stakeholder audiences described above in Section A of the Narrative. Tools will also be generalized and adapted for integration in landscape land use decisions regionally and globally.

Section C - Management Plan and Key Personnel

Management Plan

EcoHealth Alliance, by charter, is structured as an alliance of partner organizations and agencies collaborating to achieve multi-disciplinary and mutually agreed upon outcome.  As such, EHA’s standard operational approaches are particularly well suited for managing this program.  To significantly reduce both start-up time and project costs, EHA will assign current key staff and utilize existing partnerships in the region to manage and implement the project.  During the course of the project, additional local staff and partners will be identified and added with the goal of a local, sustainable center of excellence being functional by the end of the project.

Project oversight and administrative management will be provided by the EHA home office in New York and implementation of Malaysia-based activities will be managed by the Deputy Chief of Party and their team based in Kuala Lumpur and Kota Kinabalu, Malaysia.  As the project will be based on a Cooperative Agreement, we envision that USAID/RDMA would also serve in providing advice and guidance to the project oversight and management team.

To facilitate this exchange of ideas, we are proposing a minimum of 1) 6-monthly in-person meetings between key project personnel and partners and USAID/RDMA staff to be held either in Bangkok or in Kota Kinabalu, 2) quarterly written reports to USAID/RDMA, and 3) monthly conference calls.  These communication vehicles will also serve to augment monitoring and evaluation.

Proposed Key Personnel and their project duties are listed below.  Resumes and references are provided in Annex B.

Chief of Party (CoP):

Project Responsibilities (Job Description):  The CoP will provide overall management and coordination of program vision, direction and functional successes; and is responsible for the administration and integration of the entire program. To guarantee fiscal responsibility and responsiveness to the needs of the program, the CoP will review and approve budgets to ensure they are in line with the work proposed, consistent with applicable rules and guidelines and committing sufficient effort for project participants. The CoP will conduct periodic reviews with the Administrative Coordinator to assess ongoing budgetary needs and will call and lead meetings with the Senior Management Team (CoP, Deputy CoP, Stakeholder and Partners Lead, Policy Lead, and Administrative Coordinator) to assess the program’s productivity and accomplishments with respect to its goals. He/she will request and conduct site visits as needed.  The CoP will also directly oversee the Modeling Team and be responsible for ensuring modeling activities and products are integrated with other project components.

Proposed Individual:  Dr. Peter Daszak is President of EcoHealth Alliance, a US-based organization that conducts research and outreach programs on global health, conservation and international development. Dr. Daszak’s research has been instrumental in modeling, analyzing and predicting the origin and economic impact of emerging diseases. His achievements include producing the first ever global emerging disease ‘hotspots’ map, the design and implementation of the DEEP FOREST Project, identification of the wildlife reservoir of SARS, identifying the causes of Nipah and Hendra virus emergence, and coining the term ‘pathogen pollution’. He has 20 years’ experience managing international research and outreach projects, including directing the Consortium for Conservation Medicine for 8 years, establishing EHA’s formal partnership with the Malaysian Govt. 15 years ago (HERG), and launching the One Health Alliance of South Asia in 2008. Currently, Dr. Daszak leads the modeling team for the USAID EPT PREDICT program.

Deputy Chief of Party (DCoP):

Project Responsibilities (Job Description):  The day-to-day management of the project in Malaysia will be the overall responsibility of the DCoP, performed with regular communications and assistance of the other key personnel, the administrative staff from the home office, the Center of Excellence in Sabah and other key partners.  The DCoP will serve as the most frequent Point of Contact for USAID RDMA for programmatic matters, the Center of Excellence and key partners in Malaysia.  The DCoP will divide his/her time between Sabah, peninsula Malaysia and Bangkok as needed to interact with partners and supervise activities.

Proposed Individual:  Tom Hughes is currently the Malaysian Project Coordinator at EcoHealth Alliance. His responsibilities include setting up and running the Study of Zoonotic Infections among Persons Exposed to Wild Animals, a collaborative research project with Global Viral and the Malaysian Government. In Malaysia, Tom has worked closely with partners from the Ministry of Health, the Department of Wildlife and National Parks, and the Department of Veterinary Services, over the last 8 years to develop personnel and laboratory capacity and establish sustainable disease surveillance systems for wildlife and people with high exposure to wildlife. In the last two years Tom has established the EHA Deep Forest Project in Sabah, a study of the effects of land use change on viral diversity. In 2010, Tom became the PREDICT Malaysia country coordinator for USAID's Emerging Pandemic Threats program. The aim of this research is to integrate wildlife disease surveillance into the public health infrastructure in order to create an early warning system for potential zoonotic disease spillover into domestic animals and humans. In Malaysia, Tom is working closely with partners from the Ministry of Health, the Department of Wildlife and National Parks, the Department of Veterinary Services, Sabah Wildlife Department and local universities.

Stakeholder Coordination Lead (SCL):

Project Responsibilities (Job Description):  The SCL will work with Malaysian National and State government authorities and private sector parties to identify, engage and maintain working relationships with relevant stakeholders throughout the life of the project.  The SCL will ensure high level integration of project activities and products with stakeholder and partner needs and priorities, help develop and implement workshops with the DCOP and the Center for Development and Health, provide consistency in approaches across the project, and provide the oversight for sustainable transition of relevant activities to partners by the end of the project.

Proposed Individual:  Dr. Jonathan Epstein is the Associate Vice President of Conservation Medicine at EcoHealth Alliance where he has managed projects on the emergence of Nipah and Ebola virus, SARS, MERS, and other zoonotic diseases within Asia and Africa.  Dr. Epstein has directed US government-funded EHA programs in Malaysia since 2003 including a study of the ecology of Nipah virus, and is currently the Asia Regional Coordinator for PREDICT.  He has brought together diverse stakeholders, including government agencies, universities and NGO’s across multiple countries in South Asia to lead the One Health Association of South Asia, and currently directs two other multi-disciplinary and multi-stakeholder groups, EcoHealth Net and the Consortium for Conservation Medicine.

Policy Leader (PL):

Project Responsibilities (Job Description):  The PL will be responsible for identifying opportunities and strategies for program outcomes to serve as guidance for policy and best practices among government and non-governmental stakeholders in Sabah, Malaysia, and regionally as appropriate.  The SL will meet with high-level government agency representatives to share finding and discuss opportunities for policy engagement.  The SL will also share findings and policy opportunities with international and inter-governmental organizations and agencies such as the World Bank, WHO, FAO, OIE, CGIAR, and bi-lateral aid agencies

Proposed Individual:  Dr. William Karesh is the Executive Vice President for Health and Policy at EcoHealth Alliance. He has over 25 years of international policy experience and has worked with the Sabah government since 1988.  Dr. Karesh serves on the World Health Organization's (WHO) International Health Regulations Roster of Experts focused on the human-animal interface and wildlife health. He also serves as the president of the World Animal Health Organization (OIE) Working Group on Wildlife Diseases and also chairs the International Union for the Conservation of Nature (IUCN) Wildlife Health Specialist Group, a network of wildlife and health experts around the world. Currently, Dr. Karesh is the Technical Director for the USAID Emerging Pandemic Threats PREDICT program.

Proposed Key Technical Personnel

Center of Excellence Director: Dr. Sarma B. Aralas is a professor of Economics at the School of Business and Economics at the Universiti of Malaysia Sabah.  She will work with Senior Personnel and local partners to establish the Center for Development and Health at UMS.  She will also facilitate workshops and mentor graduate students working under this project.

Center of Excellence Associate: Dr. Zakariya Belkhamza is a professor of information technology and data management at the School of Business and Economics at UMS.  He will work with Dr. Sarma to develop workshops and facilitate stakeholder meetings at the university.  He will also mentor graduate students from the business school and staff from partner agencies that work under this project.

Sabah Wildlife Department Chief Liaison to IDEEAL: Datuk Dr Laurentius N. Ambu is the Director of Sabah Wildlife Department, a position he has held since 2007. Prior to that, he was the Deputy Director from 1991. Datuk Dr Laurentius holds a BSc Degree (Zoology) from Southern Illinois University, USA, a post-graduate Diploma in Protected Landscape Management from Aberystwyth University, Wales, UK, and a PhD in Wildlife Management from Oxford University, United Kingdom. He also holds a professional post‐graduate Diploma in Edible-Nest Swiftlet Conservation and Management from Cambridge Academy of Management (FCAM). He serves as the Head of CITES (Convention of International Trade of Endangered Species of Wild Flora and Fauna) Management Authority for the Sabah Government and an expert member of the IUCN Species Survival Commission (SSC) for Asian Rhinoceros, Bovidae, Crocodile, Asian Elephant, Primate and Swiftlet Specialist Groups.

Economic Modeler:  Sarah Elwood investigates the economic costs associated with disease emergence.  Her research includes benefit cost analyses of disease emergence in the wildlife trade, valuation of a proposed tax on internationally traded meat to generate revenue for global zoonotic disease surveillance and the integration of economic theory with epidemiological models to study how the decisions people make affect the spread of infectious diseases.

Social Science Lead: Elizabeth Loh is an anthropologist and conservation biologist by training, and studies how human activities contribute to ecological changes and disease emergence.  Her current work examines the effects of forest fragmentation on human, mammal and viral communities, investigates the role of human behavior in disease risk, and she is a lead social scientist on EHA’s DEEP FOREST projects in Brazil and Malaysia.

DEEP FOREST Liaison: Dr. Kris Murray is disease ecologist and conservation biologist with broad interests in biodiversity, evolution, behavior, and infectious diseases.  Current projects include the roles of biodiversity, land-use change, climate change and other socio-economic, demographic and environmental drivers in disease emergence and conservation.  Dr. Murray is a lead scientist on EHA’s DEEP FOREST projects in Brazil and Malaysia.

Senior Modeler: Carlos Zambrana-Torrelio is a mathematical modeler and statistician with experience in demography and biogeography.  He is currently working on ecological niche modeling and applications of Geographic Information Systems (GIS) technology for biodiversity research and conservation.  He leads the GIS and modeling team for EHA’s DEEP FOREST projects in Brazil and Malaysia.

Program Coordinator for Health and Policy:  Catherine Machalaba works with conservation, public health and medical communities to find synergies and opportunities to promote science-driven policy.  Trained in public health, her work supports EHA collaborations with policy stakeholders at the international, national, and local level.  Current projects include policies to consider health threats to biodiversity and practice-based prevention of EIDs.

ANNEX A:  Implementation Work Plan, Monitoring and Evaluation plan and Time Line

We will use the proposed (and negotiated) monitoring and evaluation (M&E) plan to provide the structure for project management oversight and determining adherence to timelines for activities and deliverables. In designing the M&E plan for this project, EHA and partners based in Sabah, Malaysia have combined relevant USAID agency indicators with our experience working on disease and economic modeling projects, as well as long-term stakeholder engagement in the state, to develop project indicators that quantitatively (employing numerical indicators, as well as binary classifications where appropriate) demonstrate how the proposed work plan will contribute to the two intermediate results, five sub-intermediate results, and the overall project outcome. The proposed performance-based M&E plan aims to be consistent with the evaluation requirement features outlined in the USAID Evaluation Policy. EHA will deliver a draft Performance Management Plan within sixty days following the award, during which it will work with USAID/RDMA to further refine the proposed M&E plan. The M&E plan will be revised as necessary with RDMA through the annual work plan development to ensure consistency with any changes to standard indicators.

EcoHealth Alliance will oversee M&E activities for the project. Monitoring systems will be established that enable regular tracking of indicators and will include compilation of information from quarterly reports of project activities and employment of project management systems to pair activities and indicators with timelines. Each activity will also be assigned a lead point of contact responsible for tracking the progress of the activity and helping to proactively identify and respond to any situations that could cause potential delays in meeting planned time frames. The project’s Primary Investigators will also conduct monthly meetings with project personnel for updates on the progress of each activity. In addition, EcoHealth Alliance will submit quarterly reports to RDMA, and will provide verbal updates at semi-annual meetings at RDMA headquarters or at facility site visits. These opportunities will assist in providing additional assessment of progress towards meeting intermediary and overall objectives. All evaluation data generated from the project will be provided to USAID monitoring and evaluation systems as directed by the Agreement Officer’s Technical Representative (AOTR).

| IDEEAL Work Plan and Time Line |  |  |  | Time line |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective / Result | Activity | Measurable Outcome or Indicator | Responsible Party | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2 Q1 | Y2 Q2 | Y2 Q3 | Y2 Q4 | Y3 Q1 | Y3 Q2 | Y3 Q3 | Y3 Q4 |
| Structure project and establish management capacity | 0.1 Secure core management staff | All Management staff hired and assigned to duty | EHA | X |  |  |  |  |  |  |  |  |  |  |  |
|  | 0.2 Identify and secure core administrative staff | All Administrative staff hired and assigned to duty | EHA | X |  |  |  |  |  |  |  |  |  |  |  |
|  | 0.3 Finalize and establish approved monitoring and evaluation plan with RDMA | Monitoring and evaluation plan approved and finalized | EHA | X |  |  |  |  |  |  |  |  |  |  |  |
|  | 0.4 Set up of financial management systems | Accounts created with mechanisms for tracking expenditures |  | X |  |  |  |  |  |  |  |  |  |  |  |
|  | 0.5 Quarterly reporting of overall program activities | On-time submission of reports | EHA | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 0.6 Semi-annual review of program activities and progress at RDMA or during site visits to Sabah | Completion at RDMA headquarters or site visit | RDMA and EHA |  | X |  | X |  | X |  | X |  | X |  | X |
| Sub-IR 1.2: Required data gathered to run the quantitative model | 1.2.1 Meet with relevant partners to identify data availability | Meeting held; list of available data assembled | EHA | X | X | X | X |  |  |  |  |  |  |  |  |
|  | 1.2.2 Obtain available temporal, geospatial data of land use/land-cover and disease data | a. Temporal, geospatial land-use/land-cover data obtained | EHA | X | X | X | X |  |  |  |  |  |  |  |  |
|  |  | b. Disease data obtained | EHA | X | X | X | X |  |  |  |  |  |  |  |  |
|  | 1.2.3 Obtain available demographic and land planning data from relevant government sources and partners | Available demographic and land planning data obtained | EHA |  |  | X | X |  |  |  |  |  |  |  |  |
|  | 1.2.4 Obtain available economic parameter/indicator data | Available economic parameter/indicator data obtained | EHA | X | X | X | X |  |  |  |  |  |  |  |  |
|  | 1.2.5 Identify and obtain data to correct for reporting bias | Data to correct for reporting bias identified and obtained | EHA | X | X | X | X |  |  |  |  |  |  |  |  |
|  | 1.2.6 Obtain new data, including DEEP FOREST human contact and disease data | New data obtained | EHA | X | X | X | X |  |  |  |  |  |  |  |  |
|  | 1.2.7 Ensure gender-specified data is included in activities 1.2.2-1.2.6 | Gender-specified data is included | EHA | X | X | X | X |  |  |  |  |  |  |  |  |
| Sub-IR 1.1: Development of quantitative algorithm assessing EID spillover likelihood and cost as function of land use | 1.1.1 Estimate the likelihood of EID outbreaks | Bayesian, count-data models for different temporal and spatial scales developed | EHA |  | X | X | X | X |  |  |  |  |  |  |  |
|  | 1.1.2 Determine the value of avoided damages from past EID events | Value of avoided damages determined | EHA |  | X | X | X | X |  |  |  |  |  |  |  |
|  | 1.1.3 Create a model to predict expected damages of future disease events | Model to predict damages created | EHA |  |  | X | X | X |  |  |  |  |  |  |  |
|  | 1.1.4.a. Determine rates of land-use/land cover change under 3 different scenarios—Business as Usual (BAU), Increased land-use change, halted land-use change | Three scenario models created | EHA |  |  | X | X | X | X |  |  |  |  |  |  |
|  | 1.1.4.b. Use expected damages function to predict damages under deforestation scenarios | Expected damages under deforestation scenarios predicted | EHA |  |  | X | X | X | X | X |  |  |  |  |  |
|  | 1.1.5 Investigate incorporation of avoided damages into total ecosystem services model | Integration with total ecosystem services model explored | EHA |  |  |  |  |  | X | X | X | X | X |  |  |
|  | 1.1.6 Produce actionable model outputs and analyses for application in promoting reduced-impact land utilization | Models produced and scientific translation communications toolkit produced (see 2.3.2) | EHA |  |  |  |  | X | X | X | X | X | X |  |  |
| Sub-IR 2.1: Establishment of a center of excellence, for additional research, analysis, and crossdisciplinary partnerships | 2.1.1 Establish Center for Development and Health (CDH) at the School of Economics and Business at University Malaysia, Sabah | a. Concept developed and agreed upon | UMS and EHA | X |  |  |  |  |  |  |  |  |  |  |  |
|  |  | b. CDH established | UMS and EHA | X | X |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.2 Select local or regional graduate students for involvement | Graduated students selected | UMS/CDH |  |  | X |  | X |  |  |  | X |  |  |  |
|  | 2.1.3 Develop and oversee student projects to promote use of spatial analysis, health outcome and economic models | Completed student projects submitted to the CDH / UMS faculty | UMS/CDH and EHA |  |  |  | X |  | X |  | X |  | X |  | X |
|  | 2.1.4 Develop short-courses around LUCDEP themes | Short-course developed | UMS/CDH and EHA |  |  |  |  |  |  | X | X | X | X | X | X |
|  | 2.1.5 Identify stakeholders for participation in the Center with help from UMS and SWD | Stakeholders identified | UMS/CDH, SWD and EHA | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 2.1.6 Establish regular meetings, including quarterly roundtables at the CDH for stakeholders for public dissemination of materials and information | a. Meetings held | UMS/CDH |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | b. Meeting schedule established | UMS/CDH | X | X | X | X | X | X | X | X | X | X | X | X |
| Sub-IR 2.2: Development of a gender sensitive tool kit for communicating the health impacts of differing land use options | 2.2.1 Conduct survey of differential gendered disease risk exposure pathways to inform toolkit development and dissemination strategies | Survey(s) conducted | UMS/CDH and EHA |  | X | X | X |  |  |  |  |  |  |  |  |
|  | 2.2.2 Integrate findings from quantitative models and additional data |  | UMS/CDH and EHA |  |  |  |  |  | X | X | X | X | X |  |  |
|  | 2.2.3 Generate draft toolkit | Draft toolkit developed | UMS/CDH and EHA |  |  |  |  |  |  | X | X |  |  |  |  |
|  | 2.2.4 Conduct external review of toolkit by stakeholder representatives, including focus group involvement to generate feedback on gender sensitivity and utility to stakeholders | External review conducted and feedback compiled into broad themes and actionable modifications | UMS/CDH and EHA |  |  |  |  |  |  |  | X |  |  |  |  |
|  | 2.2.5 Finalize tookit | Incorporate feedback into tookit to generate final version | UMS/CDH and EHA |  |  |  |  |  |  |  | X |  |  |  |  |
|  | 2.2.6 Develop an outreach plan to share gender-sensitive health impacts toolkit with the public as well as with government agencies, civil society, and the private sector (link to sub-IR 2.3) | Outreach plan developed | UMS/CDH and EHA |  |  |  |  |  |  | X | X |  |  |  |  |
| Sub-IR 2.3: Improved outreach and communication of translated, quantitative resources to policy makers and civil society advocates | 2.3.1 Establish regular meetings, including quarterly roundtables at the CDH for stakeholders engagement in design and production of outreach materials | a. Meetings held | UMS/CDH | X | X | X | X | X | X | X | X | X | X | X | X |
|  |  | b. Number of unique stakeholder organizations | UMS/CDH | X | X | X | X | X | X | X | X | X | X | X | X |
|  |  | c. Number of individual sectors | UMS/CDH | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 2.3.2 Develop printed and web-based materials for dissemination to community leaders, industry leaders, and government partners | Scientific translation communications toolkit produced | EHA, UMS/CDH, SWD |  |  |  |  |  |  | X | X |  |  |  |  |
|  | 2.3.3 Develop dissemination strategy for outreach materials including scientific translation communications toolkit in consultation with stakeholders | Dissemination strategy developed | EHA, UMS/CDH, SWD |  |  |  |  |  |  | X | X |  |  |  |  |
|  | 2.3.4 Disseminate outreach materials and toolkits to community leaders | a. Outreach materials and toolkits disseminated to communities | EHA, UMS/CDH, SWD |  |  |  |  |  |  |  |  | X | X | X | X |
|  |  | b. Town hall meeting public fora held | EHA, UMS/CDH, SWD |  |  |  |  |  |  |  |  | X | X | X | X |
|  | 2.3.5 Develop website and social media platforms | Platforms developed; usage monitored by visits/followers | UMS/CDH and EHA |  |  | X | X | X | X | X | X | X | X | X | X |
|  | 2.3.6 Design and deliver short-term training programs (in person and/or online) to address immediate needs of existing professionals to increase their knowledge and capacity in the area of land use change | Per-session person counts (in-person counts, or IP address counts for online training) | UMS/CDH and EHA |  |  |  |  |  |  | X | X | X | X | X | X |
|  | 2.3.7 Conduct workshops for SWD and other relevant local gove't staff in use of toolkits and other outreach materials | Number of workshop attendees | UMS/CDH and EHA |  |  |  |  |  |  | X | X | X | X | X | X |
|  | 2.3.8 Evaluate stakeholder awareness of issues of land use change, risk of disease emergence, and gender implications | Baseline and follow-up surveys conducted | UMS/CDH and EHA | X |  |  |  |  |  |  |  |  |  | X |  |

| IDEEAL Monitoring and Evaluation Plan |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective/Result | Sub-IR | Activity | Measurable Outcome or Indicator | Time frame | Responsible Party |
| Structure project and establish management capacity |  | 0.1 Secure core management staff | All Management staff hired and assigned to duty | Y1 Q1 | EHA |
|  |  | 0.2 Identify and secure core administrative staff | All Administrative staff hired and assigned to duty | Y1 Q1 | EHA |
|  |  | 0.3 Finalize and establish approved monitoring and evaluation plan with RDMA | Monitoring and evaluation plan approved and finalized | 60 days after award | EHA |
|  |  | 0.4 Set up of financial management systems | Accounts created with mechanisms for tracking expenditures | Y1 Q1 |  |
|  |  | 0.5 Quarterly reporting of overall program activities | On-time submission of reports | Quarterly | EHA |
|  |  | 0.6 Semi-annual review of program activities and progress at RDMA or during site visits to Sabah | Completion at RDMA headquarters or site visit | Semi-annually | RDMA and EHA |
| Objective 1: Creation of field-trialed quantitative models capturing gender sensitive EID-related health savings as a function of land use | Sub-IR 1.2: Required data gathered to run the quantitative model | 1.2.1 Meet with relevant partners to identify data availability | Meeting held; list of available data assembled | Y1 | EHA |
|  |  | 1.2.2 Obtain available temporal, geospatial data of land use/land-cover and disease data | a. Temporal, geospatial land-use/land-cover data obtained | Y1 | EHA |
|  |  |  | b. Disease data obtained | Y1 | EHA |
|  |  | 1.2.3 Obtain available demographic and land planning data from relevant government sources and partners | Available demographic and land planning data obtained | Y1 Q3 - Q4 | EHA |
|  |  | 1.2.4 Obtain available economic parameter/indicator data | Available economic parameter/indicator data obtained | Y1 | EHA |
|  |  | 1.2.5 Identify and obtain data to correct for reporting bias | Data to correct for reporting bias identified and obtained | Y1 | EHA |
|  |  | 1.2.6 Obtain new data, including DEEP FOREST human contact and disease data | New data obtained | Y1 | EHA |
|  |  | 1.2.7 Ensure gender-specified data is included in activities 1.2.2-1.2.6 | Gender-specified data is included | Y1 | EHA |
|  | Sub-IR 1.1: Development of quantitative algorithm assessing EID spillover likelihood and cost as function of land use | 1.1.1 Estimate the likelihood of EID outbreaks | Bayesian, count-data models for different temporal and spatial scales developed | Y1 Q2 - Y2 Q1 | EHA |
|  |  | 1.1.2 Determine the value of avoided damages from past EID events | Value of avoided damages determined | Y1 Q2 - Y2 Q1 | EHA |
|  |  | 1.1.3 Create a model to predict expected damages of future disease events | Model to predict damages created | Y1 Q3 - Y2 Q1 | EHA |
|  |  | 1.1.4.a. Determine rates of land-use/land cover change under 3 different scenarios—Business as Usual (BAU), Increased land-use change, halted land-use change | Three scenario models created | Y1 Q3 - Y2 Q2 | EHA |
|  |  | 1.1.4.b. Use expected damages function to predict damages under deforestation scenarios | Expected damages under deforestation scenarios predicted | Y1 Q3 - Y2 Q3 | EHA |
|  |  | 1.1.5 Investigate incorporation of avoided damages into total ecosystem services model | Integration with total ecosystem services model explored | Y2 Q2 - Y3 Q2 | EHA |
|  |  | 1.1.6 Produce actionable model outputs and analyses for application in promoting reduced-impact land utilization | Models produced and scientific translation communications toolkit produced (see 2.3.2) | Y2 Q1 - Y3 Q2 | EHA |
| Objective 2: Improved multi-channel availability of EID-focused quantitative resources amongst civil society advocates and government policy makers | Sub-IR 2.1: Establishment of a center of excellence, for additional research, analysis, and crossdisciplinary partnerships | 2.1.1 Establish Center for Development and Health (CDH) at the School of Economics and Business at University Malaysia, Sabah | a. Concept developed and agreed upon | Y1 Q1 | UMS and EHA |
|  |  |  | b. CDH established | Y1 Q1 - Q2 | UMS and EHA |
|  |  | 2.1.2 Select local or regional graduate students for involvement | Graduated students selected | Y1 Q 3 | UMS/CDH |
|  |  | 2.1.3 Develop and oversee student projects to promote use of spatial analysis, health outcome and economic models | Completed student projects submitted to the CDH / UMS faculty | Y1 Q3 - Y3 | UMS/CDH and EHA |
|  |  | 2.1.4 Develop short-courses around LUCDEP themes | Short-course developed | Y2 Q3 - Y3 | UMS/CDH and EHA |
|  |  | 2.1.5 Identify stakeholders for participation in the Center with help from UMS and SWD | Stakeholders identified | Ongoing | UMS/CDH, SWD and EHA |
|  |  | 2.1.6 Establish regular meetings, including quarterly roundtables at the CDH for stakeholders for public dissemination of materials and information | a. Meetings held |  | UMS/CDH |
|  |  |  | b. Meeting schedule established | Quarterly | UMS/CDH |
|  | Sub-IR 2.2: Development of a gender sensitive tool kit for communicating the health impacts of differing land use options | 2.2.1 Conduct survey of differential gendered disease risk exposure pathways to inform toolkit development and dissemination strategies | Survey(s) conducted | Y1 Q2 - Q4 | UMS/CDH and EHA |
|  |  | 2.2.2 Integrate findings from quantitative models and additional data | see next step | Y2 Q2 - Y3 Q2 | UMS/CDH and EHA |
|  |  | 2.2.3 Generate draft toolkit | Draft toolkit developed | Y2 Q3 - Q4 | UMS/CDH and EHA |
|  |  | 2.2.4 Conduct external review of toolkit by stakeholder representatives, including focus group involvement to generate feedback on gender sensitivity and utility to stakeholders | External review conducted and feedback compiled into broad themes and actionable modifications | Y2 Q4 | UMS/CDH and EHA |
|  |  | 2.2.5 Finalize tookit | Incorporate feedback into tookit to generate final version | Y2 Q4 | UMS/CDH and EHA |
|  |  | 2.2.6 Develop an outreach plan to share gender-sensitive health impacts toolkit with the public as well as with government agencies, civil society, and the private sector (link to sub-IR 2.3) | Outreach plan developed | Y2 Q3 - Q4 | UMS/CDH and EHA |
|  | Sub-IR 2.3: Improved outreach and communication of translated, quantitative resources to policy makers and civil society advocates | 2.3.1 Establish regular meetings, including quarterly roundtables at the CDH for stakeholders engagement in design and production of outreach materials | a. Meetings held | Quarterly | UMS/CDH |
|  |  |  | b. Number of unique stakeholder organizations | Quarterly | UMS/CDH |
|  |  |  | c. Number of individual sectors | Quarterly | UMS/CDH |
|  |  | 2.3.2 Develop printed and web-based materials for dissemination to community leaders, industry leaders, and government partners | Scientific translation communications toolkit produced | Y2 Q3 - Q4 | EHA, UMS/CDH, SWD |
|  |  | 2.3.3 Develop dissemination strategy for outreach materials including scientific translation communications toolkit in consultation with stakeholders | Dissemination strategy developed | Y2 Q3 - Q4 | EHA, UMS/CDH, SWD |
|  |  | 2.3.4 Disseminate outreach materials and toolkits to community leaders | a. Outreach materials and toolkits disseminated to communities | Y3 Q1 - Q4 | EHA, UMS/CDH, SWD |
|  |  |  | b. Town hall meeting public fora held | Y3 Q1 - Q4 | EHA, UMS/CDH, SWD |
|  |  | 2.3.5 Develop website and social media platforms | Platforms developed; usage monitored by visits/followers | Y1 Q3 | UMS/CDH and EHA |
|  |  | 2.3.6 Design and deliver short-term training programs (in person and/or online) to address immediate needs of existing professionals to increase their knowledge and capacity in the area of land use change | Per-session person counts (in-person counts, or IP address counts for online training) | Y2 Q3 - Y3 Q4 | UMS/CDH and EHA |
|  |  | 2.3.7 Conduct workshops for SWD and other relevant local gove't staff in use of toolkits and other outreach materials | Number of workshop attendees | Y2 Q3 - Y3 Q4 | UMS/CDH and EHA |
|  |  | 2.3.8 Evaluate stakeholder awareness of issues of land use change, risk of disease emergence, and gender implications | Baseline and follow-up surveys conducted | Y1 Q1 and Y3 Q3 | UMS/CDH and EHA |

ANNEX B:  PERSONNEL

Peter Daszak

EcoHealth Alliance, 460 W. 34th St. New York, NY 10001

daszak@ecohealthalliance.org

Dr. Peter Daszak is President of EcoHealth Alliance, a US-based organization which conducts research and outreach programs on global health, conservation and international development.  Dr. Daszak’s research has been instrumental in identifying and predicting the impact of emerging diseases across the globe.  His achievements include producing the first ever global emerging disease ‘hotspots’ map, the design and implementation of the DEEP FOREST Project, identification of the wildlife reservoir of SARS, identifying the causes of Nipah and Hendra virus emergence, and coining the term ‘pathogen pollution’. He has 20 years’ experience managing international research and outreach projects, including directing the Consortium for Conservation Medicine for 8 years, establishing EHA’s formal partnership with the Malaysian Govt. 15 years ago (HERG), and launching the One Health Alliance of South Asia in 2008. Currently, Dr. Daszak leads the modeling team for the USAID EPT PREDICT program. Dr Daszak is a member of the Institute of Medicine’s Forum on Microbial Threats, and served on the IOM Committee on global surveillance for emerging zoonoses, the NRC committee on the future of veterinary research, the International Standing Advisory Board of the Australian Biosecurity CRC.  He has briefed White House National Security Staff twice on global health issues.  Dr Daszak won the 2000 CSIRO medal for collaborative research on the discovery of amphibian chytridiomycosis and is Editor-in-Chief of the journal Ecohealth.  He has authored over 190 scientific papers, and his work has been the focus of extensive media coverage, ranging from popular press articles to television appearances.

Education

Bangor University, UK 		Zoology 		BSc (honors) 		1988

Univ. of East London, UK 		Parasitology		Ph.D			1994

Work Experience

President, EcoHealth Alliance							2009 - present

- Chief Executive Officer and Member of the Board of Directors of a 501 (c) 3 organization focused on Health, Environment and Capacity Building globally

- Managing headquarters staff of 35 (development, finance, field and scientific research) and global staff of 100+ incl. permanent and associated field staff

- Reporting to a 20+ member Board of Directors (social entrepreneurs and leaders from financial, chemical and service industries, academia, philanthropy and conservation)

Lead, Modeling Team, USAID EPT PREDICT					2010 - present

- Originated vision, design and implementation of ‘DEEP FOREST’ program

- Designed and produced global cost-benefit model for economics of pandemics

- Managing all analytical and mathematical modeling teams for USAID EPT PREDICT; producing scientific papers and reports for EPT and liaison with other USG agencies

- Generating Version II of the Global EID ‘Hotspots’ model

Executive Director, Consortium for Conservation Medicine				2001 - 2009

- Directing the CCM’s mission in research, education, policy and conservation

- Coordinating research on emerging diseases among 6 leading US institutions

- Managing a budget of $2.5 Million p.a.

- Seven core staff, 12 staff at partner institutions and 40 field staff in the USA, Latin America, Malaysia, China, Australia, Bangladesh

Faculty Research Scientist, University of Georgia					1999 - 2001

- Research on emerging infectious diseases of Wildlife (Daszak et al. Science, 2000)

Guest Researcher, Centers for Disease Control and Prevention (CDC)    		1999

- Worked in Dr. Sherif Zaki’s Pathology Activity during Nipah virus outbreak

- Processing outbreak samples for SEM and TEM

Faculty Research Scientist, Kingston University, UK     				1993 - 1998

Research Assistant, University of East London, UK 					1989 - 1992

Synergistic Activities

Awards, citations, honors

Hsu-Li Distinguished Lectureship in Epidemiology 2013; Elected member of Cosmos Club 2012; ISI ‘Most highly cited paper’ 2009; NIH Director’s Pioneer Award Finalist 2007; Debate panelist Australian Parliament 2007; Zayed Prize (Millennium Ecosystem Assessment) 2006; ‘Editor’s Choice’ Science 2006,311:1675; CSIRO Silver Medal 2000; Meritorious service award, CDC 1999; Honored by the naming of a new species of centipede (Cryptops daszaki, Lewis 2001) and a parasite (Isospora daszaki, Ball, Brown & Snow 2012).

Panel Membership

Sr. Research Fellow, UCLA Ctr Tropical Res. 2012-; Scientific Advisory Board, Ctr. Ecological Forecasting, Univ. Oklahoma 2011-; IOM Forum on Microbial Threats 2010-; Org. Comm., 1st Intl. One Health Congr. Australia 2010-11; Council of Advisors, One Health Commission 2010-; Organizing Committee FAO-OIE-WHO Joint Technical Consultation on Influenza and Other Emerging Zoonoses 2009; Steering Committee NIAID workshop on bat viruses 2009; Scientific Adv. Board, NIAID Center of Excellence, avian influenza 2008; IOM Committee on global capacity for EID surveillance and response 2008-9; IOM workshop on Microbial Evolution and co-Adaptation 2008; IUCN CBD Expert workshop on pre-import screening for invasive species 2008; Scientific Advisory Board, Treasurer DIVERSITAS 2003-10; Board member, then Treasurer, International EcoHealth Association 2005-11; International Advisory Standing Comm. Australian Biosecurity CRC 2004-9; NIAID Steering Comm. workshop on zoonotic viral emergence 2005; NRC Committee member, National Needs for Research in Veterinary Science 2004-5; 2004; Lead Author human health, Millennium Ecosystem Assessment 2002-5.

Invited talks

White House briefing on emerging diseases, 2013; Briefing to White House National Security Staff Director for Medical Preparedness Policy 2010; TEDMED 2010; Keynote speaker, European CDC 2008; Intelligence Community Briefing 2008; Congressional Briefing, EIDs 2001.

Grant Review

NIH, ZRG1 IRAP-Q review panel ARRA Challenge grants 2009; CDC review panel ZCD1 SGI, 09PAR07-231 2007; NIAID, study section ZRG1 IRAP-Q 2005-6; NIH: ZRG1 IDM-G 90 Topics in Virology 2003-4; Regular reviewer for NSF, IDRC, USDA, EU, Wellcome, BBSRC (UK).

Editorial Boards

Editor-in-Chief EcoHealth; Editorial Board, Conservation Biology; Regular reviewer for Nature, Science, PNAS, PLoS Biology, EID and others.

Publications (out of over 190); * = corresponding author

Five most closely related to proposed project

Daszak P, Cunningham AA, Hyatt AD (2000).   Emerging infectious diseases of wildlife - threats to biodiversity and human health.   Science 287: 443-449

Patz JA, Daszak P, Tabor GM, Aguirre AA, Pearl M, Epstein J, Wolfe ND, Kilpatrick AM, Foufopoulos J, Molyneux D, Bradley DJ & Members of the Working Group Land Use Change and Disease Emergence (2004).  Unhealthy Landscapes:  Policy Recommendations on Land Use Change and Disease Emergence.  Environmental Health Perspectives 112: 1092-1098

Jones KE, Patel NG, Levy MA, Storeygard A, Balk D, Gittleman JL, Daszak P* (2008). Global trends in emerging infectious diseases. Nature 451:990-994.

Murray KA, Daszak P. (2013). Human ecology in pathogenic landscapes: Two hypotheses on how land use change drives viral emergence. Current Opinion in Virology 3: 79-83.

Pike J, Bogich TL, Finnoff DC, Daszak P. Economic optimization of a global strategy to reduce the pandemic threat. Nature in review

Five other significant publications

Li W, Shi Z, Yu M, Ren W, Smith C, Epstein JH, Wang H, Crameri G, Hu Z, Zhang H, Zhang J, McEachern J, Field H, Daszak P, Eaton BT, Zhang S, Wang L-F. (2005). Bats are natural reservoirs of SARS-like coronaviruses. Science 310: 676-679.

Rodríguez JP, Taber AB, Daszak P, Sukumar R, Valladares-Padua C, Padua S, Aguirre LF, Medellin R, Acosta M, Aguirre AA, Bonacic C, Bordino P, Bruschini J, Buchori D, Gonzálalez S, Mathew T, Mendez M, Mugijca L, Pacheco LF, Dobson AP, Pearl M (2007).  Policy Forum: The globalization of conservation: A view from the South.  Science 317: 755-756.

Smith KF, Behrens M, Schloegel LM, Marano N, Burgiel S & Daszak P* (2009). Policy Forum: Reducing the risks of the wildlife trade.  Science, 324: 594-595.

Keesing F, Belden LK, Daszak P, Dobson A, Harvell CD, Holt RD, Hudson P, Jolles A, Jones KE, Mitchell CE, Myers SS, Bogich T, Ostfeld RS. (2010). Impacts of biodiversity on the emergence and transmission of infectious diseases.  Nature 468:647-652.

Daszak P, Zambrana-Torellio C, Bogich TL, Fernandez M, Epstein JH, Murray KA, Hamilton H (2013). Interdisciplinary approaches to understanding disease emergence: The past, present and future drivers of Nipah virus emergence.  PNAS 110: 3681-3688

Tom Hughes

EcoHealth Alliance

## E-mail: tom.hughes@ecohealthalliance.org

Tom Hughes is currently the Malaysian Project Coordinator at EcoHealth Alliance. His responsibilities include setting up and running the Study of Zoonotic Infections among Persons Exposed to Wild Animals, a collaborative research project with Global Viral and the Malaysian Government. In Malaysia, Tom has worked closely with partners from the Ministry of Health, the Department of Wildlife and National Parks, and the Department of Veterinary Services, over the last 8 years to develop personnel and laboratory capacity and establish sustainable disease surveillance systems for wildlife and people with high exposure to wildlife. In the last two years Tom has established the EHA Deep Forest Project in Sabah, a study of the effects of land use change on viral diversity. In 2010, Tom became the PREDICT Malaysia country coordinator for USAID's Emerging Pandemic Threats program. The aim of this research is to integrate wildlife disease surveillance into the public health infrastructure in order to create an early warning system for potential zoonotic disease spillover into domestic animals and humans. In Malaysia, Tom is working closely with partners from the Ministry of Health, the Department of Wildlife and National Parks, the Department of Veterinary Services, Sabah Wildlife Department and local universities.

Education

University of East Anglia 	Development Studies 	BSc (honors)		2002

& Natural Resources

Capel Manor College	Amenity Horticulture 	City & Guilds (Distinction)    	2003

Phase 2 in Arboriculture

London Sch. Hygiene 	Post Graduate Diploma 				2009

& Trop. Medicine.

Work Experience

Deep Forest Country Coordinator, Sabah, EcoHealth Alliance			        2012 - present

- Set up and coordinate Wildlife Health Unit with Dr Sen Nathan Assistant Director Sabah Wildlife Department

- Coordination of Deep Forest project in Sabah including hiring personnel and management of project team (9 people) and regular communication with in-state partners Sabah Wildlife Department and Department of State Health Sabah

- Set up the Wildlife Health, Genetic and Forensic Laboratory at the Wildlife Health Unit and developed protocols for lab and sample management and good work flow similar to the protocols developed at the other two PREDICT labs VRI and PERHILITAN

PREDICT Country Coordinator Malaysia, EcoHealth Alliance 		       2010 - present

- Fiscal management of all funds associated with this contract; Track project expenditures to ensure fiscal responsibility; develop and manage budgets (> 250,000/yr) and prepare financial data for reporting

- Coordinating laboratory analysis of biological samples collected under PREDICT and Deep Forest at partner labs (VRI, PERHILITAN, and Sabah Wildlife Dept.)

- Training 110 field and laboratory personnel in accordance with PREDICT protocols

Study of Zoonotic Infections among Persons Exposed to Wild Animals Project Coordinator Malaysia, EcoHealth Alliance 		        2007 - present

- Coordinating sample collection from people with high exposure to wildlife, bats, rodents and primates with PERHILITAN, DVS and MOH in Peninsular Malaysia

- Coordinate meetings and communicate with government partners (MOH, PERHILITAN and DVS) to facilitate the approval of the MOU among the Malaysian government, EHA, and GVF, and to share results and findings from this study

Field Officer, Ecology of Nipah virus in Malaysia, EcoHealth Alliance 			 2005 - 2007

- Monitoring the population size and movement of Pteropus bats and collecting biological samples.

Arborist. The Tree Company (London) Ltd.      			2003 - 2005

Expedition Leader. Tropical Forest Project. Perhentian Islands Malaysia. Coral Cay Conservation. (Collaborative research project with PERHILITAN)        			2004 - 2004

Synergistic Activities

Reviewer

EcoHealth Journal.

Public Education

Worked at the village school and with businesses on The Perhentian Islands to educate school children, residents and tourists on the terrestrial flora and fauna of the islands, the importance of conserving this environment and its value to the livelihood of residents; Worked at the school on Tioman Island to educate students, teachers and parents on the ecological and economical importance of the Flying Fox in an attempt to raise awareness of the importance of this species.

# Professional Affiliations & Activities

# Member, Henipavirus Ecology Research Group.

# Publications

# Five most closely related to proposed project

Daszak P, Plowright R, Epstein JH, Pulliam J, Rahman SA, Field HE, Smith CS, Olival KJ, Luby S, Halpin K, Hyatt AD, Henipavirus Ecology Research Group, Hughes T. (2006). The Emergence of Nipah and Hendra virus: pathogen dynamics across a wildlife-livestock-human continuum. Disease Ecology: Community Structure and Pathogen Dynamics 186-201. doi:10.1093/acprof:oso/9780198567080.003.0013.

Halpin, K, Hyatt, AD, Plowright RK, Epstein, JH, Daszak P, Field HE, Wang, L, Daniels P, Henipavirus Ecology Research Group, Hughes T. (2007). Emerging viruses - coming in on a wrinkled wing and a prayer. Clinical Infectious Diseases. 44(5): 711-17.

Halpin K, Hyatt AD, Fogarty R, Middleton D, Bingham J, Epstein JH, Rahman SA, Hughes T, Smith C, Field HE, Daszak P, Henipavirus Ecology Research Group. (2011). Pteropid Bats are Confirmed as the Reservoir Hosts of Henipaviruses: A Comprehensive Experimental Study of Virus Transmission. American Journal of Tropical Medicine and Hygiene. 85(5), 2011, pp. 946–951.

Pulliam JRC, Epstein JH, Dushoff J, Rahman SA, Bunning M, Jamaluddin AA, Hyatt AD, Field HE, Dobson AP, Daszak P, Henipavirus Ecology Research Group, Hughes T. (2012). Agricultural intensiﬁcation, priming for persistence and the emergence of Nipah virus: a lethal bat-borne zoonosis. Journal of the Royal Society Interface. Jan: 9, 89-101.

Rahman SA, Hassan L, Epstein JH, Hassan SS, Arshad S, Hughes T, et al. (2013). Risk factors for Nipah virus infection among pteropid bats, Peninsular Malaysia. Emerging Infectious Diseases. http://dx.doi.org/10.3201/eid1901.120221.

Five other relevant publications

Pulliam J, Field H, Olival KJ, Henipavirus Ecology Research Group, Hughes T. (2005). An alternative Explanation of Nipah virus strain variation. Emerging Infectious Diseases 11: 1978-1979.

Epstein, JH, Olival KJ, Pulliam JRC, Smith C, Westrum J, Hughes T, Dobson AP, Zubaid A, Rahman SA, Basir MM, Field HE, Daszak P. (2009). Pteropus vampyrus, a hunted migratory species with a multinational home-range and a need for regional management. Journal of Applied Ecology. 46: 991-1002.

Rahman SA, Hassan SS, Olival KJ, Mohamed M, Chang LY, Hassan L, Saad NM, Shohaimi SA, Mamat ZC, Naim MS, Epstein JH, Suri AS, Field HE, Daszak P, Henipavirus Ecology Research Group, Hughes T. (2010). Characterization of Nipah virus from naturally infected Pteropus vampyrus bats, Malaysia. Emerging Infectious Diseases.16(12):1990-3.

Sohayati AR, Hassan L, Sharifah SH, Lazarus K, Zaini CM, Epstein JH, Shamsyul NN, Field HE, Arshad SS, Abdul AJ, Daszak P, Henipavirus Ecology Research Group, Hughes T. (2011). Evidence for Nipah virus recrudescence and serological patterns of captive Pteropus vampyrus.  Epidemiololgy and Infection. 139(10):1580.

Lee M, Rostal M, Hughes T, Griffiths A, Harden M, Rovie-Ryan J, Sitam F, Basir M, Epstein JE, Wolfe N, Daszak P. Evaluation of B virus shedding in long-tailed macaques PLoS Pathogens. In review.

Jonathan H. Epstein

EcoHealth Alliance, 460 W. 34th St. New York, NY 10001

E-mail:epstein@ecohealthalliance.org

Dr. Epstein is a veterinary epidemiologist and Associate Vice President of Conservation Medicine at EcoHealth Alliance.  He is the Asia Regional Coordinator for USAID EPT PREDICT.  He has worked with the government of Malaysia for over 10 years, studying the ecology of Nipah virus, and now working with the Wildlife Department, Ministry of Health, and Department of Veterinary Services to establish disease surveillance systems for wildlife and people with high exposure to wildlife.  He has also worked with the Sabah Wildlife Department for the last two years on the Deep Forest project, a study of the effects of land use change on viral diversity.  Dr. Epstein directs the One Health Alliance of South Asia (OHASA), a multi-lateral science and policy network with members from India, Pakistan, Bangladesh, and Nepal, focused on the control and prevention of trans-boundary zoonotic diseases.  His current research activities are focused on understanding the ecology of emerging zoonotic viruses such as Nipah virus in Bangladesh, Ebola and SARS CoV; and the newly discovered MERS CoV.  His work has been published in leading scientific journals including Science, PNAS and Emerging Infectious Diseases and Dr. Epstein holds academic appointments at Columbia University, Tufts University, and Mt. Sinai School of Medicine.

Education and Training

Brandeis University				Biology		BA 	 		1996

Tufts University Sch. Vet. Med.		Vet Med		D.V.M			2002

Tufts University Sch. Vet. Med.		Vet Med		Intl. Cert.		2002

Tufts University Sch. Vet. Med.		Public Health		M.P.H			2002

Research and Professional Experience

Associate Vice President, EcoHealth Alliance					2008 - present

- Manage and develop research programs on emerging zoonoses (e.g. Nipah virus, SARS/MERS CoV)

- Direct NSF-funded EcoHealthNet cross-disciplinary graduate training program

- Direct One Health Alliance of South Asia, a regional disease science and policy network

EHA Asia Regional Coordinator, USAID EPT PREDICT				2010 - present

- Coordinate PREDICT programs in India, Bangladesh, Thailand, Malaysia (Peninsular Malaysia and Sabah), Indonesia, and China

- Member of Global Surveillance Team - develop overall PREDICT surveillance strategy

- Member, Molecular Diagnostic Team - provide technical input to lab diagnostic tools

- Meet with government officials in each country to maintain PREDICT work

Executive Director, The Consortium for Conservation Medicine			2009 - present

- Coordinate interdisciplinary research and graduate training opportunities among five US institutions including Johns Hopkins Bloomberg School of Public Health, Tufts Veterinary School, University of Wisconsin Nelson Institute for the Environment, the USGS National Wildlife Health Center, and University Pittsburgh School of Public Health

Visiting Research Fellow; The Center for Infection and Immunity, NY		2007 - 2011

- Molecular virology; pathogen discovery (discovered bat Pegivirus GBV-D)

- Nipah virus serology and molecular epidemiology

Senior Research Scientist, Wildlife Trust, NY					2003 - 2008

Veterinary Intern, Ocean State Veterinary Specialists				2002 - 2003

Synergistic Activities

Awards, citations, honors

Tufts University Young Alumni Achievement Award 2012, selected from all university alumni who graduated within the last ten years; Tufts Cummings School of Veterinary Medicine Outstanding Alumnus Award 2007; Delta Omega Honor Society, Tufts University School of Medicine Alpha Rho Chapter, Graduate Programs in Public Health (1st alumni inductee; 1st keynote speaker) 2006; Tufts University School of Veterinary Medicine Certificate in International Veterinary Medicine (1st recipient) 2002; Sylvia Mainzer Public Health Award, for outstanding achievement in the field of public health 2002; Hill’s “Buddy” Award for Excellence in Clinical Nutrition, for excellence in clinical veterinary nutrition 2002.  Journal of the Royal Society, Interface most cited article of 2012 (Pulliam, Epstein et al.).

Panel Membership

Planning Board, American Society of Microbiology Microbial Threats 2014; Executive Board, International Association of Ecology and Health 2013 -; Admissions Committee, Tufts University Masters in Conservation Medicine program 2012 -; Scientific Advisory Board, Lubee Bat Conservancy 2012 -; Member, IUCN Wildlife Health Specialist Group 2003 -; Veterinary Specialist, IUCN Bat Specialist Group 2006 -.

Invited talks

Testified, Institute of Medicine/National Research Council Committee on Global Surveillance of Emerging Zoonoses 2008; University Malaya Nipah virus colloquium 2008; Nipah virus symposium, Amer. Soc. Trop. Med. & Hyg. 2008; WHO/OIE/FAO joint workshop on Nipah, Hendra, and Ebola Reston viruses 2009; International Bat Research Conference, Prague, Czech Republic; Wuhan Institute of Virology, 2010, Wuhan, China; Testified at Congressional briefing for National Wildlife Health Center 2012; ISID IMED talks on Nipah virus and MERS CoV 2012; Institute of Medicine forum on Microbial threats (MERS CoV) 2013.

Editorial Boards

Review Editor, EcoHealth; Reviewer for Science, Emerging Infectious Diseases, New England Journal of Medicine, Journal of Infectious Diseases, International Journal of Infectious Diseases, Journal of Zoonotic and Vector-borne Diseases; Conservation Biology, Biological Conservation, PLoS Pathogens and others.

Professional Affiliations

- Adjunct Professor: Tufts University (School of Medicine and Cummings School of Veterinary Medicine); Columbia University (Mailman School of Public Health and Department of Ecology, Evolution, and Environmental Biology); Mt. Sinai School of Medicine  (current)

- Am. Vet. Med. Assoc.; Wildlife Disease Association; NY Academy of Sciences; Intl Assoc. of Ecology & Health; Int’l Soc. Inf. Dis.; American Society of Tropical Medicine & Hygiene

Publications

Five most closely related to proposed project

Patz J, Daszak P, Tabor GM, Aguirre A, Pearl M, Epstein JH, Wolfe N, Foufopoulos J, Molyneux D, Bradley D, Members of the Working Group Land Use Change and Disease Emergence.  (2004) Environmental Health Perspectives. Vol. 112, No.10: 1092-1098.

#### Epstein JH, Quan PL, Briese T, Street C, Jabado O, et al. (2010) Identification of GBV-D, a Novel GB-like Flavivirus from Old World Frugivorous Bats (Pteropus giganteus) in Bangladesh. PLoS Pathogens 6(7): e1000972. doi:10.1371/journal.ppat.1000972.

#### Daszak P, Zambrana-Torrelio C, Bogich TL, Fernandez M, Epstein JH, Murray KA, Hamilton H. (2012). Interdisciplinary approaches to understanding disease emergence: The past, present and future drivers of Nipah virus emergence. PNAS 110: 3681-3688.

#### Pulliam JR, Epstein JH, Dushoff J, Rahman SA, Meehan G, Bunning M, HERG, Jamaluddin AA, Hyatt AD, Field HE, Dobson AP, Daszak P.  Agricultural intensification, priming for persistence, and the emergence of Nipah virus:  a lethal bat-borne zoonoses. (2011) Journal of the Royal Society. Doi:10.1098/rsif.2011.0223 (journal’s most cited article in 2012).

#### Rahman SA, Hassan L, Epstein JH, Hassan SS, Arshad S, Hughes T, et al. Risk factors for Nipah virus infection among pteropid bats, Peninsular Malaysia. (2013) Emerging Infectious Diseases. Vol. 19, No. 1, January.

Five other relevant publications

Li W, Shi Z, Yu M, Ren W, Smith C, Epstein JH, Wang H, Crameri G, Hu Z, Zhang H, Zhang J,  McEachern J, Field H, Daszak P, Eaton BT, Zhang S, Wang LF. (2005). Bats are natural reservoirs of SARS-like coronaviruses.  Science 310: 676-679.

Epstein JH, Prakash V, Smith CS, Daszak P, McLaughlin, AB, Meehan G, Field HE, Cunningham, AA. (2008). Evidence for Henipavirus infection in Indian Pteropus giganteus (Chiroptera; Pteropodidae) fruit bats. Emerging Infectious Diseases. 14(8):1309-11.

Wood JLN, Leach M, Waldman L, MacGregor H, Fooks AR, Jones K, Restif O, Dechmann D, Hayman DTS, Baker KS, Peel AJ, Kamins AO, Ntiamoa-Baidu Y, Suu-Ire R, Breiman R, Epstein JH, Cunningham AA. (2012)  A framework for the study of zoonotic disease emergence and its drivers: spillover of bat pathogens as a case study. Phil. Trans. R. Soc. B 367: 2881-2892; doi:10.1098/rstb.2012.0228.

Quan, PL, Firth C, Conte J M, Williams SH, Zambrana-Torrelio C, Anthony SJ, Ellison JA, Gilbert AT, Kuzmin IV, Niezgoda M, Osinubi MOV, Recuenco S, Markotter W, Breiman RF, Kalemba L, Malekani J, Lindblade KA, Rostal MK, Ojeda-Flores R, Suzan, G, Lora B, Blau, DM, Ogunkoya AB, Alvarez C, Danilo A, Moran D, Ngam S, Akaibe D, Agwanda B, Briese T, Epstein JH, Daszak, P, Rupprecht CE, Holmes EC, Lipkin WI.  Bats are a major natural reservoir for hepaciviruses and pegiviruses. (2013). PNAS. doi:10.1073/pnas.1303037110.

Levinson J, Bogich TL, Olival KJ, Epstein JH, Johnson CK, Karesh W, et al. Targeting surveillance for zoonotic virus discovery. (2013). Emerging Infectious Diseases. doi:10.3201/eid1905.121042.

William B. Karesh

EcoHealth Alliance, 460 W. 34th St. New York, NY 10001

karesh@ecohealthalliance.org

Dr. William Karesh is the Executive Vice President for Health and Policy for EcoHealth Alliance. He serves as president of the World Animal Health Organization (OIE) Working Group on Wildlife Diseases and chairs the IUCN SSC Wildlife Health Specialist Group, a network of wildlife and health experts around the world. Currently, Dr. Karesh is the Technical Director for the USAID Emerging Pandemic Threats PREDICT program. Dr. Karesh has pioneered initiatives focusing attention and resources to solving One Health problems raised by the interactions among wildlife, people, and their animals. He has directed international programs in Africa, Asia, South and North America, including programs in the Congo Basin to reduce the impact of diseases such as Ebola, measles, and tuberculosis on humans and endangered species such as gorillas and chimpanzees, and global surveillance systems for emerging diseases. Dr. Karesh has also worked for the USDA, DOD, DOI and the FAO and has been named to the WHO International Health Regulation Roster of Experts for Wildlife Health at the Human-Animal Interface. He is internationally recognized as an authority on One Health. He has also published over one hundred and fifty scientific papers.

Education

Clemson University, SC		Biology		B.S.			1977

University of Georgia, GA		Veterinary Medicine	D.V.M.			1982

Zoological Society of San Diego	Residency  		Wildlife Health		1982 - 1984

Work Experience

Executive Vice President for Health and Policy, EcoHealth Alliance    	         2010 - Present

- Build and strengthen EHA partnerships with mission-critical government agencies, international NGOs, and private sector businesses to provide guidance and sound policy development to protect the health of human and animal populations.

- Represent organization to federal, state, and city government personnel and elected officials, as well as foreign governments and multi-lateral agencies.

Technical Director, PREDICT, USAID EPT PREDICT        	                      	         2009 - Present

- Built a coalition of organizations, university scientists, foreign government agencies and laboratories to enhance capacity for surveillance of emerging human pathogens of wildlife origin, predictive modeling and information sharing for developing countries.

- Provide leadership across the program and liaise with management teams of other EPT programs including oversight on the Deep Forest program.

- Oversee and coordinate surveillance activities in twenty developing countries.

President, OIE Working Group on Wildlife Diseases      		      	           2008 - Present

- Lead team of international scientists and policy experts to inform and advise the OIE on disease problems (emerging, zoonotic, livestock and wildlife).

- Review and advise on international health standards and regulations used by the World Trade Organization and bilateral trade negotiations on animal and animal product movement, vaccine standards and diagnostic test standards.

Co-Chair, Wildlife Health Specialist Group, IUCN   		               	           2004 - Present

- Built and now lead team of over 450 international scientists and health experts to inform and advise the IUCN, sovereign governments, organizations and on disease prevention and control (emerging, zoonotic, livestock and wildlife).

- Created open access, web-based database of members searchable by geographic location, areas of subject matter expertise, etc. to provide knowledge network of experts for emergency response, advice and other services.

- Led strategic planning, mission development, 4-year work planning and reporting efforts.

VP and Director of Global Health Program, Wildlife Conservation Society   	   2008 - 2010

- Led multi-million dollar international projects and grant giving programs in 45 countries focused on the disease control and prevention for people, domestic animals and wildlife.

- Lead contact with government agencies, international NGOs, and private sector to provide guidance and policy development to protect human and animal health.

- Developed working agreements (Memoranda of Understanding, Letters of Agreement, and Cooperative Agreements) with organizations and agencies such as USAID’s Global Health Bureau, U.S. Centers for Disease Control and Prevention, U.S. Department of Agriculture, Food and Agriculture Organization of the U.N., World Bank, U.S. Geologic Survey, and foreign governments.

Chief of Party, Global Avian Influenza Network for Surveillance of Wild Birds (GAINS)2006 -9

- Designed, organized and managed the implementation of wildlife disease surveillance network operating in 34 countries and involving dozens of government agencies, NGOs, universities and private businesses around the world.

- Created first open access database on influenza in wildlife with results from sampling tens of thousands of wild birds, denominator data on over one hundred million wild birds.

- Oversaw funding and budgeting from USAID, NIH, USDA, and private industry.

# Director, International Field Programs, Wildlife Conservation Society	    	1989 - 2007

- Developed and led multi-million dollar international projects and grant giving programs focused on the health of wildlife, domestic animals and people.

- Led a team of approximately 75 health professionals and management staff to provide project development guidance, veterinary services and technical consultations for field projects being established or conducted by government agencies and NGOs globally.

- Designed transformational approaches to disease control and prevention programs that have been adopted by numerous organizations and professionals around the world.

Synergistic Activities

Building Collaborative Networks

Network among US NIH, USAMRIID, CDC, Public Health Agency of Canada, and L'Institut de Recherche pour le Développement (IRD) to deliver new diagnostic techniques for Ebola Hemorrhagic Fever. As CoP for USAID GAINS, managed the implementation of $8M wildlife disease surveillance network operating in 34 countries. As Co-Chair for the IUCN’s Wildlife Health Specialist Group I help manage our global resource network of over 400 wildlife disease experts in over 80 countries to effectively respond to issues pertinent to wildlife health. Developed MOUs for collaboration with USDA, US CDC, USGS NWHC, UN FAO, and foreign governments. Appointed to the WHO International Health Regulation Roster of Experts on Wildlife Health at the Human-Animal Interface.

Grants and Program Management

Organized collaborators for USAID PREDICT project ($75M) and serve as Technical Director for the project.  Developed and oversaw over $15M in grant-giving programs at WCS to foreign scientists and organizations focused on the health of wildlife, domestic animals and people. Worked directly with government agencies and international non-governmental organizations to provide project development guidance and technical consultations for field projects being established or conducted in 45 countries.

Policy Development for public and private organizations

Office of the President, USAID, DHS, CDC, UNEP, IUCN, UN FAO, WHO, OIE, European Union, Public Health Agency of Canada, Health and Forestry Ministries - Republic of Congo, Forest Ministry - Republic of Indonesia, Glaxo-Smith-Kline, Cargill Corporation, Bio-ERA.

Invited Lectures/Presentations

Office of the President, NAS/IOM, U.S. Congress, DoD, CDC, NIH Grand Rounds, EPA, US State Department, USAID, FDA, World Health Organization, UN FAO, UNEP, UN CBD, OIE, Asia Pacific Economic Cooperation, African Union, Chinese Centers for Disease Control, Public Health Agency of Canada, International Meeting on Emerging Diseases, AAAS, International Risk Governance Council, International Society for Disease Surveillance.

Reviewer/commentator

EID, Vector-Borne and Zoonotic Diseases, Journal of Wildlife Diseases, IOM Forum on Microbial Threats, ProMED, WHO Strategy for Managing Public Health Risks at the Human-Animal Interface. Member of Editorial Board, EcoHealth.

Publications (out of over 170)

Five most closely related to proposed project

Wolfe ND, Kilbourn AM, Rahman HA, Bosi EJ, Cropp BC, Andau M, Karesh WB, Spielman, A, Gubler, DJ. (2001) Sylvatic Transmission of Arboviruses among Bornean Orangutans. American Journal of Tropical Medicine and Hygiene 64: 310-316.

Leroy EM, Rouquet P, Formenty P, Souquiere S, Kilbourn A, Froment JM, Bermejo M, Smit S, Karesh WB, Swanepoel R, Zaki SR, Rollin PE. (2004) Multiple Ebola Virus Transmission Events and Rapid Decline of Central African Wildlife. Science 303: 387-390.

Karesh WB, Cook RA. (2005). The Human-Animal Link, One World-One Health. Foreign Affairs 84:38-50.

Karesh WB, Cook RA. (2009). One World-One Health. Clinical Medicine 9(3): 259-260.

Karesh WB, Dobson A, Lloyd-Smith J, Lubroth J, Dixon MA, Bennett M, Aldrich S, Harrington T, Formenty P, Loh L, Machalaba CC, Thomas MJ, Heymann DL. (2012). The Ecology of Zoonoses: Their Natural and Unnatural Histories. The Lancet 380: 1936-45.

Five others of relevance

Wolfe ND, Karesh WB, Kilbourn AM, Cox-Singh J, Bosi EJ, Rahman HA, Singh B, Andau M, Spielman A. (2002) The Impact of Ecological Change on the Prevalence of Malaria among Orangutans. Vector Borne and Zoonotic Disease 2(2): 97-103.

Nyamsuren D, Joly DO, Enkhtuvshin S, Odonkhuu D, Olson KA, Draisma M, Karesh WB. (2006) Exposure of Mongolian gazelles (Procapra gutturosa) to foot and mouth disease virus. Journal of Wildlife Diseases. 42:1.

Olson SH, Reed P, Cameron KN, Ssebide BJ, Johnson CK, Morse SS, Karesh WB, et al.  (2012). Dead or Alive: animal sampling during Ebola hemorrhagic fever outbreaks in humans. Emerging Health Threats Journal. 5: 2012. doi: 10.3402/ehtj.v5i0.9134.

Morse SS, Mazet JAK, Woolhouse M, Parrish CR, Carroll D, Karesh WB, Zambrana-Torrelio C, Lipkin WI, Daszak P. (2012). Prediction and prevention of the next pandemic zoonosis. The Lancet 380:1956-65.

Smith KM, Anthony SJ, Switzer WM, Epstein JH, Seimon T, Jia H, Karesh WB, et al. (2012) Zoonotic viruses associated with illegally imported wildlife products. PLOS One 7(1): e29505.

Sarma B. Aralas

Universiti Malaysia Sabah, Jalan UMS, 88400 Kota Kinabalu, Sabah, Malaysia

miasarma@ums.edu.my

Sarma Aralas is a senior lecturer and researcher at Universiti Malaysia Sabah. Her fields of interest include environmental and resource economics, international trade, international development economics and econometrics. She has conducted research in the areas of international economic development, environment, and government fiscal programs. Her current research investigates the relationship between natural resource endowment and international trade specialization. Her research projects include a study on firm-level environmental management systems and practices to ascertain the link between environmental performance and financial achievement of firms in Malaysia.

Education

University of Houston			Economics			BSc	1998 – 2002

University of Houston		 	Economics 			MA	2003 – 2004

Michigan State University	 	Agricultural Economics	PhD	2004 – 2010

Work Experience

Lecturer									 1996 - present

Sekolah Perniagaan dan Ekonomi, Universiti Malaysia Sabah

- Teach economics courses including international trade and macroeconomics, on average 2 courses per semester.

- Engage in research including acquisition of grants from sources such as IRPA. Research includes theoretical and field research works.

- Supervise research students at undergraduate and graduate levels.

- Supervise undergraduate students on project-assignments as part of course requirements, at least 40 student project papers per semester.

- Undertake consultation work including for the Ministry of Science and Environment, Malaysia.

Postdoctoral Research Fellow 				January 2010 - December 2010

Department of Agricultural Economics, Michigan State University

- Worked on United States Agency for International Development (USAID) data on socioeconomic and poverty issues of USAID recipients in the African state of Kenya, primarily to assess policy effectiveness.

- Quantified the benefits of USAID programs at various levels namely, at the village, province, regional and state levels.

- Constructed poverty indicators to evaluate program benefits including by gender, education and household types.

- Analyzed macro-sized dataset using both descriptive and regression-based econometrics techniques. Data encompassed 3,000 aid recipients, 8 years of policy implementation and 6 types of poverty-alleviating programs.

- Liaised with American counterparts of USAID and Michigan State University consultants.

- Co-authored reports and working paper on the impact of USAID programs in Kenya.

Acting Dean										2000 - 2001

Sekolah Perniagaan dan Ekonomi (SPE), Universiti Malaysia Sabah

- Managed and supervised 45 personnel, including faculty and administrative staffs.

- Initiated and authored 2 working papers to propose new programs at school level, including the postgraduate program of Masters in Economics (by coursework).

- Undertook steps to increase academic achievements in terms of research and publications among faculty. By 2001, SPE increased publications by 80 percent, increased conference participation by lecturers by 90 percent, and increased research applications by 60 percent.

- Member of various university-level committees to proposed and implemented university-level and school-level policies.

Deputy Dean 										1998 - 2000

Sekolah Perniagaan dan Ekonomi, Universiti Malaysia Sabah

- Oversaw the practical implementation of academic policies at the school level.

- Worked to ensure students’ welfare in the fulfillment of academic requirements and advisory needs.

- Represented the university and the school to working-committees at national level.

Research Assistant									2008 - 2009

Department of Agricultural and Resource Economics, Michigan State University

- Analyzed data on public pensions plan.

- Reviewed literature on public pensions and economies of scale.

- Formulate possible research hypotheses to propose for consultancy project.

- Present descriptive analysis and initial funding estimations.

- Compiled and analyzed data on public projects on road constructions.

Teaching/Research Assistant								2005 - 2009

Department of Agricultural and Resource Economics, Michigan State University

- Teaching Assistant for four semesters for the following courses.

Research Assistant									 2006 - 2007

Land Policy Institute, Michigan State University

- Research and analysis in the area governmental consolidation, exploring the economies of scale in the provision of services of public/government agencies.

- Analyzed survey data on the use of 911emergency services for government agencies in Michigan, USA.

Synergistic Activities

Conferences and presentations

Presenter and Session Chair, The 5th International Borneo Business Conference (IBBC), Tawau, Sabah 2012; Presenter and Moderator, Agricultural and Applied Economics Association (AAEA), Denver, Colorado 2010; Presenter, Fourth World Congress of Environmental and Resource Economists (WCERE) 2010; Participant, Department of Agricultural, Food and Resource Economics, ‘Environmental  Management in Michigan: The Quest for a New Path’ 2009; Invited Speaker, Albion College, Michigan, ‘The Impact of International Trade on  the Environment’ 2008; Participant, Michigan State University, ‘Intergovernmental Cooperation Conference’ 2007; Department of Agricultural Economics, Michigan State University, ‘Graduate Student Research Symposium’ 2007; Participant, Michigan State University Center for Environmental Journalism, ‘Risk Perception: Why Our Fears Don't Match the Facts’ 2006; Participant, The Kellogg Center, Michigan State University, ‘Securing Academic Positions at Two- and Four-Year Institutions’ 2006; Participant, Department of Agricultural Economics, Michigan State University, ‘Water  Shortages, Water Allocation and Economic Growth: The Case of China’ 2006; APEC Study Center Consortium Conference, Kuala Lumpur, Malaysia 2001; Labuan International Conference, Malaysia 2000; Postgraduate National Seminar, UMS, Kota Kinabalu, Malaysia 1999.

Awards

Excellence in Service Award. Universiti Malaysia Sabah 1998, 2000, 2011 and 2012.

Editorial Boards

BIMP-EAGA Journal for Sustainable Tourism Development, 2011 -; Jurnal Kinabalu, Universiti Malaysia Sabah (UMS), 2011 -; Deputy Editor, Jurnal Kinabalu, Universiti Malaysia Sabah (UMS) 1999 – 2001.

Publications

Five most closely related to proposed project

Wong Hock Tsen, Sarma B. Aralas. (1997) Perdagangan Intra-industri Sabah di BIMP-EAGA. Jurnal Kinabalu. 3,1997.

Sarma B. Aralas. (2000) Perdagangan Antarabangsa dan Analisis Perkembangan Intra-industri Sabah di BIMP- EAGA. Jurnal Kinabalu. 6, 2000.

Sarma B. Aralas, Arsiah Bahron. (2000) Kes Perniagaan Sabah (Sabah Business Cases), ed. Kota Kinabalu: Universiti Malaysia Sabah.

Sarma B. Aralas. (2007) Economies of Scale in the Provision of 911 Emergency Services. Land Policy Institute, Michigan State University.

Public Pension Plans in Michigan. Are There Economies of Scale? (2009). MSU Extension, Department of Agricultural, Food and Resource Economics, Michigan State University. Working Paper.

Five other significant publications

Wong Hock Tsen, Sarma B. Aralas, James Oehmke, Thomas Jayne, Mary Mathenge. Impacts of USAID/Kenya Supported Agricultural Productivity Interventions on Household Income and Poverty Reduction. Working Paper, Tegemeo Institute of Agricultural Policy and Development: Nairobi Kenya, October 2010.

Sarma B. Aralas, Intraindustry Trade and the Environment: Is There a Selection Effect? Journal of  International Economics.  In review.

Sarma B. Aralas. How Does Intraindustry Trade Affect the Environment? In review.

Sarma B. Aralas. Monopolistic Competition, Environmental Policy and Intraindustry Trade. In review.

Sarma B. Aralas. Firm-level Heterogeneity, Abatement and Trade: Is the Cleaner Firm the Exporting Firm? In review.

Zakariya Belkhamza

Universiti Malaysia Sabah, Teluk Likas, 88999, Kota Kinabalu, Sabah, Malaysia

zakariya@ums.edu.my

Dr. Belkhamza is an Economist with experience in the economics of agricultural trade, IT and the financial sector within Malaysia and the Southeast Asian region. He leads research into the economics of e-commerce and holds high-level positions within the OIC.  At UMS, he heads up a research group and leads course programs on economics at the School of Business and Economics.

Education

Universite Saad Dahlab Blida, Algeria	Economics		BA(Econ) 	1997 - 2001

Universiti Malaysia Sabah 			Business.		MSc.	    	2003 - 2006

Universiti Malaysia Sabah			Business & 		PhD	    	2006 - 2010

Economics

Work Experience

Senior Lecturer 								2011 - present

School of Business & Economics, Universiti Malaysia Sabah

Academic Director								2006 - 2010

AlmaCrest International College, Kota Kinabalu Sabah

Part Time Lecturer 								July 2008 - Dec. 2008

School of Business & Economics

Synergistic Activities

Conferences and presentations

Presenter: International Meeting of the OIC Task Force on SMEs For Exports and Related Products. Bangkok, Thailand 2005; International Meeting of the OIC Task Force on SMEs, Istanbul, Turkey 2006; Spring School Conference of Informatics, National School of Informatics, Algiers, Algeria; International Borneo Business Conference, Kuching, Sarawak 2006-10; International Conference on Applied Asian Academy Business, Hat Yai, Thailand 2007; International Postgraduate Research Colloqium, Srinakarinwirot University, Bangkok, Thailand 2007; National Conference on Marketing, Melaka 2007; Applied International Business Conference, Labuan, Malaysia 2008; International Conference on Business & Management Education, Bangkok, Thailand 2010; IEEE International Symposium of Computers and Informamtics, Kuala Lumpur, Malaysia 2011; Taibah University International Conference on Computing and Information Technology, Medinah, Saudi Arabia 2012; BIMP-EAGA Conference, Kota Kinabalu, Sabah 2012.

Other Activities and Memberships

Member, Association of Information Systems (AIS), USA 2005; Member, Organizing Committee  OIC Human Capital Management Conference, Kota Kinabalu 2006; Chairperson, for Strategic  Management  Session in the 3rd International Conference on Applied Asian Academy Business Thailand; Member of Scientific and Technical Committee and Editorial Review Board. World Academy of Science Engineering and Technology (Waset); Member of Editorial Review Board of IEEE Symposium on Computers and Informatics 2011; Founder and President of the Postgraduate Students’ Association (PSA), Universiti Malaysia Sabah 2006 - 2009; Member of the Organizing Committee of Majlis Sambutan Maulidur rasul Peringkat, Universiti Malaysia Sabah 2012.

Editorial Review

Editor, Journal of Asian Academy of Applied Business.

Awards

Best Paper Award: ‘System Behavioural Success Model (SBS): Information Systems Success from the Organizational Perspective,’ The 4th International Conference on Postgraduate Education, Universiti Kebangsaan Malaysia (UKM) Kuala Lumpur, 2010; Silver Medal Award, PEREKA, Universiti Malaysia Sabah 2012.

Publications

Five most closely related to proposed project

Belkhamza, Z, Syed Azizi Wafa. (2012). Measuring Organizational Information Systems Success: New Technologies and Practices. IGI Global Feb. 2012.

Belkhamza, Z,  Syed Azizi Wafa. (2008). Technical Factors Affecting the Ease of Use of E-commerce in the Tourism Organizations in Sabah and Sarawak. Readings on Business.

Belkhamza, Z,  Syed  Azizi Wafa. (2009). Cultural Interpretation of e-Commerce Acceptance  in Developing Countries: Empirical Evidence from Malaysia and Algeria. Emerging Markets     and E- Commerce in Developing Economies. 199-216. IGI Global.

Belkhamza, Z, Syed Azizi Wafa. (2009). The Effect of Perceived Risk on the Intention to use E-commerce: The Case of Algeria. Journal of Internet Banking and Commerce, April 2009, vol. 14, no.1.

Belkhamza, Z, Syed Azizi Wafa. Validating the Organizational Context Measure for Quality Manageent: A Managerial Action Perspective. The Learning Organization.  In review.

Datuk Laurentius N. Ambu

Sabah Wildlife Department, 5TH Fl., Block B, Wisma Muis, 88100 Kota Kinabalu,

Sabah, Malaysia

Laurentius.Yambu@sabah.gov.my

Datuk Dr Laurentius N. Ambu is the Director of Sabah Wildlife Department, a position he has held since 2007. Prior to that, he was the Deputy Director from 1991. Datuk Dr Laurentius holds a BSc Degree (Zoology) from Southern Illinois University, USA, a post-graduate

Diploma in Protected Landscape Management from Aberystwyth University, Wales, UK, and a PhD in Wildlife Management from Oxford University, United Kingdom. He also holds a professional post‐graduate Diploma in Edible-Nest Swiftlet Conservation and Management from Cambridge Academy of Management (FCAM). He serves as the Head of CITES (Convention of International Trade of Endangered Species of Wild Flora and Fauna) Management Authority for the Sabah Government and an expert member of the IUCN Species Survival Commission (SSC) for Asian Rhinoceros, Bovidae, Crocodile, Asian Elephant,

Primate and Swiftlet Specialist Groups. Datuk Dr Laurentius is a pioneer and an avid advocate for swiftlet propagation/farming, focusing on the introduction of the translocation method in establishing nucleus population in a newly established man-made swiftlet house. Today, he is considered as one of the leading authorities and a reference expert in swiftlet conservation and farming in Malaysia and the region.

Education

Southern Illinois University, USA	Zoology					BSc	1986

The University of Wales, UK	Protected Landscape Management 		MSc	1998

Oxford University, UK		   	Philosophy in Wildlife Management 		PhD	2009

Work Experience

Director, of Sabah Wildlife Department (SWD)					2007 - present

Deputy Director, Sabah Wildlife Department						1991 - 2007

Wildlife Officer, West Coast Wildlife District Sabah Wildlife Department		1988 - 1991

Research Officer, Worldwide Fund (WWF) Malaysia				1987 - 1988

Conservation Officer, Sabah Foundation, Sabah Malaysia				1986 - 1987

Traffic Officer, Malaysian Airline (MAS) Sabah Malaysia				1980 - 1982

Customs Officer, Royal Customs and Excise Department Sabah Malaysia		1978 - 1979

Synergistic Activities

Professional contributions

State level: Secretary, Board of Trustee, Borneo Conservation Trust; Board Director, Sabah Tourism Board; Board Director, Tabin Wildlife Holidaya Sdn. Bhd. 2008 -; Officer in-charge, Bird’s Nests Conservation and Management; Species Manager for big mammals; Development Officer for the establishment of Sipadan Island, Tabin Wildlife Reserve, Orang Utan Rehabilitation Centre, State Wildlife Park, Lok Kawi; Chairman, SWD’s Tender Committee; Chairman, SWD’s Workers’ Union (MBJ); Chairman, SWD’s Housing Committee; Chairman, SWD’s Sports and Recreation Committee; Officer responsible for the implementation of International Convention - CITES, CBD, RAMSAR, WCPA; Security Officer, SWD; Project Director, UNDP project 1989 - 1993, DANIDA Project 1994 -1998, JICA (BBEC) Project 2002 - 2006; Management Representative for the Implementation of SWD’s ISO 9000; Senior Prosecutor, SWD.

National level: Board Director, Malaysian Wetlands Society; State Representative, Malaysian Timber Certification Council (MTCC); National Zoo and Aquarium Committee; National Committee on the Convention of the International Trade on Endangered Species of Wild Flora and Fauna (CITES); National Committee on the Convention on Biological Diversity (CBD);

World Commission on Protected Areas (WCPA); National Committee on RAMSAR; National Committee on the International Union for the Conservation Nature and Natural Resources; National Committee on the Wildlife Conservation and Management, Malaysia.

Memberships

Fellow, Cambridge Association of Managers; Member and Malaysian Representative, IUCN/SSC Asian Rhino Specialist Group; IUCN/SSC Bovidae Specialist Group; IUCN/SSC Crocodile Specialist Group; Representative, ASEAN Taskforce on swiftlet; Convention on International Trade in Endangered species of Wild Flora and Fauna (CITES); Malaysian

Representative, World Commission on Protected Areas (WCPA); Convention on Biological Diversity; International Union for the Conservation of Nature and Natural Resources (IUCN); Southeast Asian Zoos and Aquarium (SEAZA).

Publications (out of 21 since 2009)

Five most closely related to proposed project

Ancrenaz, M., L. Ambu, I. Sunjoto, E. Ahmad, K. Manokaran, E. Meijaard, and I. Lackman. (2010). Recent Surveys in the Forests of Ulu Segama Malua, Sabah, Malaysia, Show That Orang-utans (Pongo pongo morio) Can Be Maintained in Slightly Logged Forests. PLoS ONE 5.

Muehlenbein, M., L. A. Martinez, A. Lemke, L. Ambu, S. Nathan, S. Alsisto, and R. Sakong. (2010). Risk assessment of potential anthropozoonotic pathogen transmission from ecotourists to wildlife populations in Borneo. International Journal of Infectious Diseases 14:E140-E140.

Muehlenbein, M. P., L. A. Martinez, A. A. Lemke, L. Ambu, S. Nathan, S. Alsisto, and R. Sakong. (2010). Unhealthy travelers present challenges to sustainable primate ecotourism. Travel Medicine and Infectious Disease 8:169-175.

Estes, J. G., N. Othman, S. Ismail, M. Ancrenaz, B. Goossens, L. N. Ambu, A. B. Estes, and P. A. Palmiotto. (2012). Quantity and Configuration of Available Elephant Habitat and Related Conservation Concerns in the Lower Kinabatangan Floodplain of Sabah, Malaysia. PLoS ONE 7.

Gregory, S. D., B. W. Brook, B. Goossens, M. Ancrenaz, R. Alfred, L. N. Ambu, and D. A. Fordham. (2012). Long-Term Field Data and Climate-Habitat Models Show That Orangutan Persistence Depends on Effective Forest Management and Greenhouse Gas Mitigation. PLoS ONE 7.

Five other significant publications

Rajaratnam, R., M. Sunquist, L. Rajaratnam, and L. Ambu. (2007). Diet and habitat selection of the leopard cat (Prionailurus bengalensis borneoensis) in an agricultural landscape in Sabah, Malaysian Borneo. Journal of Tropical Ecology 23:209-217.

Clements, R., D. M. Rayan, A. W. A. Zafir, A. Venkataraman, R. Alfred, J. Payne, L. Ambu, and D. S. K. Sharma. (2010). Trio under threat: can we secure the future of rhinos, elephants and tigers in Malaysia? Biodiversity and Conservation 19:1115-1136.

Wilting, A., A. Mohamed, L. N. Ambu, P. Lagan, S. Mannan, H. Hofer, and R. Sollmann. (2012). Density of the Vulnerable Sunda clouded leopard Neofelis diardi in two commercial forest reserves in Sabah, Malaysian Borneo. Oryx 46:423-426.

Alfred, R., A. H. Ahmad, J. Payne, C. Williams, L. N. Ambu, P. M. How, and B. Goossens. (2012). Home Range and Ranging Behaviour of Bornean Elephant (Elephas maximus borneensis) Females. PLoS ONE 7.

Mohamed, A., R. Sollmann, H. Bernard, L. N. Ambu, P. Lagan, S. Mannan, H. Hofer, and A. Wilting. (2013). Density and habitat use of the leopard cat (Prionailurus bengalensis) in three commercial forest reserves in Sabah, Malaysian Borneo. Journal of Mammalogy 94:82-89.

Sarah E. Elwood

EcoHealth Alliance, 460 W. 34th St. New York, NY 10001

elwood@ecohealthalliance.org

Sarah Elwood is an economist with public health training.  She works on the integration of economic theory with epidemiological models, and determining the optimal allocation of resources to address the pandemic threat.  Her projects with EcoHealth Alliance seek to quantify the economic burdens of disease, determine on whom those burdens fall, and analyze the cost-effectiveness of policy approaches on minimizing the damages from outbreaks of disease.

Education

College of William and Mary			Economics 		BA (Honors)	2007

Columbia University Mailman School of 	Epidemiology		MPH		2012

Public Health

Work Experience

Research Economist, EcoHealth Alliance						2012 - present

- Collaborate with research scientists on interdisciplinary research, analysis, and manuscript preparation

- Supervise economic interns: development of work plans, guidance through research process, provision of technical and manuscript writing support

- Manage grants and assist with grant proposals

Systems Mapping Internship in Northern Uganda,

Child Protection in Crisis Learning Network	Summer 2011

- Designed research tools in collaboration with local NGOs

- Trained local researchers and supervised systems mapping research pilot

- Adapted research tools and recommended changes to data collection process based on lessons learned during research pilot

Accountant/Program Officer with the BundiNutrition Program,

World Harvest Mission, Bundibugyo, Uganda 	2007 - 2009

- Managed personnel and accounting aspects of inpatient and outpatient feeding programs

- Partnered with community leaders and extension workers to facilitate dairy goat distributions and community nutrition trainings

Primary/Secondary School Teacher 	2007 - 2009

- Taught multiple classes for students at various levels including United States History, World History, 1st - 6th Grade Mathematics, Algebra II and Pre-calculus

Economist/Business Analyst, The MITRE Corporation	Summer 2006 and Summer 2007

- Analyzed longitudinal data to examine the effect of increased fuel prices on the demand for general aviation services

- Researched the utility of computable general-equilibrium models for analyzing the economic impacts of regulating aircraft CO2 emissions

- Mapped hub-and-spoke commercial airline networks with Arc-GIS

Synergistic Activities

Awards

Sydney Kark Award in Epidemiology 2012.

Policy Outreach

Outreach to state officials responsible for shaping daycare center regulations to disseminate information regarding the disease risks to young children associated with keeping reptiles in daycare centers 2012.

Education/Teaching

Teaching Assistant, for two semesters, in Columbia University’s Department of Biostatistics, fall 2011, spring 2013.

Publications

Springborn M, Keller R, Romagosa C, Elwood S, Zambrana-Torrelio C, Daszak P. Integrating 	risk assessment for invasion and disease risk in live animal trade. PNAS in review.

Elwood SE, Finnoff D, Oliver M, Pike J, Daszak P. Evaluating the feasibility of a levy on internationally traded meat to finance global disease surveillance. Emerging Infectious Diseases, in review.

Pike J, Bogich TL, Elwood S, Finnoff DC, Daszak P. Economic optimization of a global strategy to reduce the pandemic threat. Nature, in review.

Tutunjian C, Elwood SE, Murray KA, Loh EH, Daszak P. A credit trading system for pandemic prevention.  EcoHealth, in review.

Elizabeth Loh

EcoHealth Alliance, 460 W. 34th St. New York, NY 10001

loh@ecohealthalliance.org

Elizabeth Loh is an anthropologist and conservation biologist by training, and studies how human activities contribute to ecological changes and disease emergence.  Her current work examines the effects of forest fragmentation on human, mammal and viral communities, investigates the role of human behavior in disease risk, and she is a lead social scientist on EHA’s DEEP FOREST projects in Brazil and Malaysia.

Education

University of Kent, United Kingdom		MSc (Conservation Biology) 		      	2009

Durrell Institute of Conservation and Ecology,

University of Kentucky  			BSc (Biological Anthropology) 		2006

Work Experience

Research Scientist, EcoHealth Alliance										       	2010 - present

- Managing design and implementation of IDRC-funded project examining forest fragmentation, bat and viral diversity, and human risk behaviors in Southern Brazil.

- Managing Deep Forest contact surveys in Brazilian Amazon.

- Managing project development on transmission pathways of disease, and investigating the drivers of disease outbreaks; production of scientific papers, reports and translation of science.

Research Assistant, Wildlife Conservation Society, Iquitos, Peru      				2009 - 2010

- Examined mammal species, habitat diversity and dietary preferences.

- Identified niche and habitat overlaps.

- Conducted small mammal monitoring in the Peruvian Amazon.

Health Outreach Specialist, Bluegrass Farmworker Health Center					Summer 2009

- Supervised basic health assessments, referrals and follow-ups with migrant and seasonal farmworkers and their families.

- Developed outreach material including pamphlets, and newspaper advertisements

- Provided outreach, education, and HIV testing services to migrant and seasonal farmworkers.

- Conducted outreach in community setting in order to engage farmworker communities in neighborhood clinics, residential areas as well as non-traditional settings.

Wildlife Rehabilitation Intern, Wildlife Center of Virginia, VA, USA					Summer 2007

Refugee Mentor, Kentucky Refugee Ministry, Lexington, KY						2005 - 2007

Synergistic activities

Professional associations

Ecological Society of America (ESA); Society for Conservation Biology (SCB); International Association for Ecology and Health (EcoHealth); Wildlife Disease Association (WDA); American Anthropological Association (AAA).

### Volunteer service

### WCS, Iquitos, Peru; Buckley Wildlife Sanctuary, Frankfort, KY, USA; Wildwood Trust, Kent, UK; The Wildlife Center of Virginia, Waynesboro, Virginia; Coanil fundación, Valparaiso, Chile; Primate Rescue Center, Lexington, USA.

Publications

Five most closely related to proposed project

Karesh wb, Loh EH, Machalaba C. (2011) Food Safety: A view from the wild side. Institute

of Medicine summary report of the workshop on Improving Food Safety Through One Health. Institute of Medicine.Dec.13-14, 2011.

Karesh WB, Dobson A, Lloyd-Smith J, Lubroth J, Dixon M, Bennett M, Aldrich S, Harrington T, Loh EH, Machalaba C, Thomas M, Heymann D. (2012). The Ecology of Zoonoses: Their Natural and Unnatural Histories. The Lancet. 380: 1936-45.

Bogich T, Olival KJ, Hosseini P, Zambrana-Torrelio C, Loh EH, Funk S, Brito I, Epstein JH, Brownstein J, Jones K, Daszak P. (2012). Using Mathematical Models in a Unified Approach to Predicting the Next Emerging Infectious Disease. New Directions in Conservation Medicine: Applied Cases of Ecological Health. 2012: 607-618.

Loh EH, Murray K, Zambrana-Torrelio C, Hosseini P, Rostal M, Karesh WB, Daszak P. Ecological Approaches to Studying Zoonoses. One Health: People, Animals, and the Environment. American Society of Microbiology. In press.

Loh EH, Bogich T, Olival KJ, Johnson C, Mazet J, Karesh WB, Daszak P. Targeting emergence pathways for zoonotic disease surveillance and control. Journal of Zoonotic and Vectorborne diseases. In prep.

Five other significant publications

Rostal MK, Olival KJ, Loh EH, Karesh WB. (2012) Wildlife: The need to better understand the risks and linkages. Current Topics in Microbiology and Immunology PMID: 23117192  Nov 2. Epub ahead of print.

Loh EH, Zambrana-Torrelio C, Olival KJ, Levy M, Daszak P, Brownstein J. What drives infectious disease outbreaks? PLoS ONE. In prep.

Loh EH, Daszak P. Prospecting for Pathogens: Extractive Industries and Emerging Infectious Diseases. EcoHealth. In prep.

Smith K, Loh EH, Rostal M, Zambrana-Torrelio C, Daszak P. From Pathogens to Politics: Drivers of Honey Bee Colony Declines and Losses. EcoHealth. In review.

Tutunjian C, Elwood SE, Murray KA, Loh EH, Daszak P. A credit trading system for pandemic prevention.  EcoHealth, in review.

Kris A. Murray

EcoHealth Alliance, 460 W. 34th St. New York, NY 10001

daszak@ecohealthalliance.org

Dr. Kris Murray is disease ecologist and conservation biologist with broad interests in biodiversity, evolution, behavior, and infectious diseases.  Current projects include the roles of biodiversity, land-use change, climate change and other socio-economic, demographic and environmental drivers in disease emergence and conservation.  Dr. Murray is a lead scientist on EHA’s DEEP FOREST projects in Brazil and Malaysia.

Education

University of Queensland (Australia)		PhD (Ecology/Conservation) 			2010

Flinders University (Australia) 		BSc (Ecology) 				2002

Work Experience

Research Scientist, EcoHealth Alliance					       	2012 - present

- Ecological lead on multiple research projects, including USAID EPT PREDICT modeling program; producing scientific papers and reports and translating science.

- Managing design and inter-continental implementation of the Deep Forest program.

- Managing project development on quantifying the economic impact of EIDs, Version ii of the Global EID ‘Hotspots’ project, understanding EID emergence due to land use change and modeling extinction risk with threats for better conservation outcomes.

Postdoctoral Research Scientist, James Cook University, QLD, Australia	      2010 - 2011

- Preparing and publishing publications on 1) Health security risks, disease biogeography and biosecurity strategy, and 2) climate change and emerging infectious diseases.

- Managing collaborators, network development, research and writing.

Ecological Consultant (self employed), QLD, Australia						      2006 - 2012

- Provision of expert ecological and technical knowledge on a range of projects to a range of stakeholders, primarily relating to the natural resources industry and state and federal agencies.

- Provision of expertise for ecological surveys and reports for Environmental Impact Statements

- Provision of analysis expertise.

Adjunct Faculty, E3B, Columbia University, New York, USA 			2012 - present

University Tutor, University of Queensland, QLD, Australia				2006 - 2010

Science Editor/Writer, Canada, USA, Switzerland					2004 - 2006

Research Biologist, Flinders University, SA, Australia				2002 - 2004

Research Assistant, University of Adelaide, SA, Australia			    	2001 - 2002

Research Assistant, University of South Australia, SA, Australia		      2000 – 2002

Synergistic activities

Grant reviewer

BiodivERsA 2012-2013; Pan-European call for international research proposals on ‘Invasive species and biological invasions.’ BiodivERsA is a network of 21 public research funding organizations from 15 European countries supporting scientific research in the field of biodiversity. Total 2013 funding allocation of ~€7.7 million; individual project awards ~€1 million.

Reviewer/Editor

Ecology Letters, Ecology; J. Appl. Ecol.; Functional Ecology; Austral Ecology; Conservation Biology, Biological Conservation; Animal Conservation; Aquatic Conservation, Marine and Freshwater Ecosystems; PLoS One; New Zealand Journal of Zoology; Journal of Fish and Wildlife Management; Wildlife Research; Herp Review; Acta Herpetologica; Diseases of Aquatic Organisms; Infection Genetics and Evolution; EcoHealth.

Panels, working groups and consultancies

NCEAS working group member ‘Fungal pathogens and disease-induced extinctions;’ Advisor to Australian Government Department of Sustainability, Environment, Water, Populations and Communities (consultant report preparations); Advisor to Australian Wildlife Health Network (consultant report preparation).

Professional associations

Ecological Society of Australia (ESA); Australian Wildlife Health Network (AWHN); Wildlife Preservation Society of Queensland (WPSQ); Society for Conservation Biology (SCB); Wildlife Disease Association (WDA); Ecological Society of America (ESA); Australian Society for Parasitology (ASP).

Volunteer service

Ocean Wide Expeditions; Department of Environment and Heritage (DEH), South Australia; Nature Conservation Council of South Australia (NCSSA), South Australia; WWF; Forestry Research Institute (FRIM), Kuala Lumpur, Malaysia; Department of Primary Industries (PIRSA), Adelaide, South Australia; Natural Heritage Trust, Adelaide, South Australia; Wilderness Society, Adelaide, South Australia; Scientific Exploration Group (SEG), South Australia; South Australian Research and Development Institute (SARDI), Adelaide, South Australia.

Publications (out of 21 since 2009)

Five most closely related to proposed project

Murray KA, Skerratt LF, Speare R, Ritchie S, Smout F, Hedlefs R, and Lee J. (2012). Cooling off health security hot spots: getting on top of it down under. Environment International. 48 (1): 56-64.

Daszak P, Zambrana-Torrelio CM, Bogich TL, Fernandez M, Epstein JH, Murray KA, Hamilton H. (2012). Interdisciplinary approaches to understanding disease emergence: The past, present and future drivers of Nipah virus emergence. PNAS. 110 (S1): 3681-3688.

Zambrana-Torrelio, C, Murray, KA, Daszak, P. (2012) One Health and Hotspots of Food-borne EIDs. In: Improving Food Safety Through One Health. International Institute of Medicine Annual Workshop Summary Report. Institute of Medicine.

Murray KA, Daszak P. (2013). Human ecology in pathogenic landscapes: two hypotheses on how land use change drives viral emergence. Current Opinion in Virology. 3, 79-83

Anthony SJ, Epstein JH, Murray KA, Navarrete-Macias I, Zambrana-Torrelio CM, Solovyov A, Ojeda Flores R, Arrigo NC, Islam A, Ali Khan S, Hosseini P, Bogich TL, Olival KJ, Sanchez-Leon MD, Karesh WB, Goldstein T, Luby SP, Morse SS, Mazet JAK, Daszak P, Lipkin WI. Estimating viral diversity in bats. PNAS In review.

Five other significant publications

Murray KA, Skerratt LF, Speare R, McCallum H. (2009). Impact and dynamics of disease in species threatened by the amphibian chytrid fungus, Batrachochytrium dendrobatidis. Conservation Biology, 23, 1242-1252.

Murray KA, Retallick R, McDonald K, Mendez D, Aplin K, Kirkpatrick P, Berger L, Hunter D, Hines HB, Campbell R, Pauza M, Driessen M, Speare R, Richards SJ, Mahony M, Freeman A, Phillott AD, Hero JM, Kriger K, Driscoll D, Felton A, Puschendorf R, Skerratt LF. (2010). The distribution and host range of the pandemic disease chytridiomycosis in Australia spanning surveys from 1956 to 2007. Ecology. 91, 1557.

Murray KA, Rosauer D, McCallum H, Skerratt LF. (2011). Integrating species traits with extrinsic threats: closing the gap between predicting and preventing species declines. Proceedings of the Royal Society of London Series B, published online Oct. 27 2010.

Murray KA, Retallick RWR, Puschendorf R, Skerratt LF, Rosauer D, McCallum H, Berger L, Speare R, VanDerWal J. (2011). Assessing spatial patterns of disease risk to biodiversity: implications for the management of the amphibian pathogen, Batrachochytrium dendrobatidis. Journal of Applied Ecology, 48:1, 163-173.

Murray KA, Skerratt LF. (2012). Predicting wild hosts for amphibian chytridiomycosis: integrating host life-history traits with pathogen environmental requirements. Human and Ecological Risk Assessment. 18: 200-224, 2012.

Carlos Zambrana-Torrelio

EcoHealth Alliance, 460 W. 34th St. New York, NY 10001

zambrana@ecohealthalliance.org

Carlos Zambrana-Torrelio is a Research Scientist in EcoHealth Alliance's modeling team. Carlos’ research combines quantitative methods on spatial analysis and biodiversity. He has led projects on conservation and biogeography in Bolivia and demography in Puerto Rico.  He currently manages analytical and modeling research on the DEEP FOREST project and leads EHA’s work on the new IUCN Ecosystems’ Red List. This initiative models, measures and maps the impact of anthropogenic activities on ecosystem dynamics, biodiversity and ecohealth.

Education

Universidad Mayor de San Andres, Bolivia			Biology	Licenciate	2004

University of Puerto Rico					Ecology	M.Sc.		2009

Work Experience

Research Scientist, EcoHealth Alliance					2010 - Present

- Examine the roles of biodiversity, land use change, climate change, and other socio-economic, demographic, and environmental drivers on the dynamics and spread of pathogens in wildlife, humans and domestic animals.

Consultant, NatureServe, Arlington, VA					 	Spring 2006

- Andes-Amazon Endemic Species Mapping.

- Utilize statistical and databasing methods to analyze the geographic distribution of Andes-Amazon species.

Researcher, Herbario Nacional de Bolivia 						2005 - 2006

- Developed, managed and implemented spatial databases

Consultant, TROPICO Asociación Boliviana para la Conservación			Fall 2005

- Knowledge transfer to park rangers of the Carrasco National Park in Bolivia.

Researcher, Asociacion Armonia, Bolivia					 2003 - 2006

- Evaluated the conservation status of endangered species.

Researcher, Wildlife Conservation Society (WCS), Bolivia 			2002 - 2003

- Designed, developed and administered geospatial databases to support the creation of the Management Plan of the Madidi National Park in Bolivia.

Consultant, CARE International, Bolivia 					Summer 2002

- Constructed and developed spatial databases to support participatory rural diagnostics at the Madidi National Park in Bolivia.

Consultant, Instituto de Ecología, Centro de Análisis Espacial, Bolivia	 Fall 2001

- Implemented remote sensing techniques to produce detailed vegetation map of the Tunquini Biological Station in Bolivia.

Consultant, Instituto de Ecología - Centro de Análisis Espacial, Bolivia 	2000 - 2001

- Managed and developed spatial databases to evaluate wildlife and natural resources of the Tacana communal territory.

Synergistic Activities

Journal Review

Ecologia en Bolivia; EcoHealth; Ecological Modelling; Biosphere (ESA).

Memberships

Red List of Ecosystems Initiative; Diversitas EcoHealth; International Biogeography Society; Botanical Society of America; Asociacion Boliviana de Ecologia; Programa para la Conservacion de los Murcielagos de Bolivia; International Association for Ecology and Health

Grant Reviewer

Universidad Mayor de San Andres, Bolivia

Publications

Five most closely related to proposed project

Morse SS, Mazet JAK, Woolhouse M, Parrish CR, Carroll D, Karesh WB, Zambrana-Torrelio CM, Lipkin WI, Daszak P. (2012). Prediction and prevention of the next pandemic zoonosis. The Lancet 380:1956–1965.

Bogich TL, Olival KJ, Hosseini PR, Zambrana-Torrelio CM, Loh EH, Funk S, Brito IL, Epstein JH, Brownstein JS, Joly DO, Levy MA, Jones KE, Morse SS, Aguirre AA, Karesh WB, Mazet JAK, Daszak P. (2012). Using Mathematical Models in a Unified Approach to Predicting the Next Emerging Infectious Disease. New Directions in Conservation Medicine: Applied Cases of Ecological Health. 2012: 607-618.

Quan PL, Firth C, Conte JM, Williams SH, Zambrana-Torrelio CM, Anthony SJ, Ellison JA, Gilbert AT, Kuzmin IV, Niezgoda M, Osinubi MOV, Recuenco S, Markotter W, Breiman RF, Kalemba L, Malekani J, Lindblade KA, Rostal MK, Ojeda-Flores R, Suzán G, Davis LB, Blau DM, Ogunkoya AB, Alvarez Castillo DA, Moran D, Ngam S, Akaibe D, Agwanda B, Briese T, Epstein JH, Daszak P, Rupprecht CE, Holmes EC, Lipkin WI. (2013). Bats are a major natural reservoir for hepaciviruses and pegiviruses. Proceedings of the National Academy of Sciences.  doi/10.1073/pnas.1303037110

Anthony S, Ojeda-Flores R, Rico-Chávez O, Navarrete-Macias I, Zambrana-Torrelio CM, Rostal MK, Epstein JH, Tipps T, Liang E, Sanchez-Leon M, Sotomayor-Bonilla J, Aguirre AA, Ávila R, Medellin RA, Goldstein T, Suzán G, Daszak P, Lipkin WI. (2013). Coronaviruses in bats from Mexico. Journal of General Virology. doi:10.1099/vir.0.049759-0.

Daszak P, Zambrana-Torrelio CM, Bogich TL, Fernández M, Epstein JH, Murray KA, Hamilton H. (2013). Interdisciplinary approaches to understanding disease emergence: the past, present, and future drivers of Nipah virus emergence. Proceedings of the National Academy of Sciences.110:3681–3688.

Five other significant publications

Agnarsson I, Zambrana-Torrelio CM, Flores-Saldana NP, May-Collado LJ. (2011). A time-calibrated species-level phylogeny of bats (Chiroptera, Mammalia). PLoS Currents 3:RRN1212.

Daszak P, Zambrana-Torrelio CM, Bogich TL. (2011) Surveillance for emerging diseases in wildlife. Institute of Medicine workshop report, Emerging Fungal Pathogens.

Zambrana-Torrelio CM, Murray KA, Daszak P. (2012). One health and hotspots of food-borne EIDs. Improving Food Safety Through a One Health Approach: Workshop Summary. Institute of Medicine (US). Washington (DC): National Academies Press (US). 2012.

Simon JA, Epstein JH, Murra KA, Navarrete-Macias I, Zambrana-Torrelio CM, Solovyov A, Ojeda-Flores R, Arrigo N, Islam A, Khan SA, Hosseini PR, Bogich TL, Olival KJ, Sanchez-Leon M, Karesh WB, Goldstein T, Luby S, Morse SS, Mazet JAK, Daszak P, Lipkin WI. Estimating viral diversity in bats. Proceedings of the National Academy of Sciences. In review.

Asmussen M, Ferrer-Paris JR, Rodriguez-Clark KM, Bogich TL, Zambrana-Torrelio, CM, Rodriguez JP. The magnitude of illegal wildlife trade in the world. Nature. In submission.

Catherine Machalaba

EcoHealth Alliance, 460 W. 34th St. New York, NY 10001

machalaba@ecohealthalliance.org

Ms. Catherine Machalaba is the Program Coordinator for Health and Policy at EcoHealth Alliance. She focuses on engaging the conservation, public health and medical communities to find synergies and opportunities to promote science-driven policy.  Trained in public health, her work supports EHA collaborations with policy stakeholders at the international, national, and local level. Catherine's overall efforts involve strengthening the effectiveness of conservation efforts through the proactive consideration of health threats to biodiversity, as well as development and implementation of policy and practice-based prevention of emerging zoonotic diseases. She has prior experience in public health and policy analysis and outreach, healthcare quality improvement and health systems strengthening, program evaluation, and study of the social and environmental determinants of health.

Education

Wake Forest University, USA		Biology 		BA			2008

Dartmouth Medical School, USA	Public Health		MPH 			2009

Work Experience

Program Coordinator for Health and Policy, EcoHealth Alliance		            2010 - present

- Surveillance coordination and administrative support for USAID Emerging Pandemic Threats PREDICT program activities

- Policy strengthening and development of best practices around public health and conservation at regional, national and international scale

Program Officer, IUCN SSC Wildlife Health Specialist Group		           2010 - present

- Member communications and outreach efforts for 300+ expert network (website and membership database management, newsletter drafting, social media presence)

- Communications to external partners

- Development of wildlife disease information summaries, and guidelines

Fellow, Veterans Engineering Resource Center, VA Boston Healthcare System   2009 - 2010

- Led multidisciplinary teams based at the VA Boston Healthcare System on process redesign projects using systems engineering methodologies

- Process redesign leader for three teams enrolled in the VA national Cancer Care Collaborative (Boston, San Juan, and New York)

- Developed local and national VA healthcare system performance improvement metrics, and organized training seminars for hospital staff

Contributing Writer, Consumer Reports on Health				           2009 - present

- Monthly freelance writer for Consumer Reports on Health’s On Your Mind page

- Conducting literature reviews and synthesizing information into practical health advice

Tobacco Control Program Intern, Vermont Office of the Attorney General		2008 - 2009

- Conducted comparative policy research and generated evidence-based policy recommendations

- Collaborated with state and national stakeholders

- Drafted documents for tobacco bill education for legislators

Research Intern, Seal Laboratory, Wake Forest University School of Medicine	2006 - 2007

- Trained on and performed laboratory cellular and molecular biology approaches to cancer biology research (PCR, Western Blot and cloning)

Field Agent/Educator, Vermont Department of Health 			           2005 - 2006

- Created and distributed awareness and health-promotion materials for West Nile virus and Lyme Disease prevention and control

- Planned and delivered community presentations/events for high-risk populations

- Collected birds for West Nile virus surveillance

Synergistic Activities

Expert Group Membership and Roles

Newsletter Editor, American Public Health Association Veterinary Public Health Special Primary Interest Group; Member, IUCN SSC Policy Subcommittee.

Reviewer

EcoHealth (2012); IAEH EcoHealth Conference abstract review (2012); The Dartmouth Institute MPH Thesis review (2010); The Dartmouth Institute Root Cause Analysis Competition judge (2010); VA Quality Scholars project grant application review (2010).

Multidisciplinary Collaboration

Worked closely with hospital clinicians, financial department, researchers, and social workers to conduct a program evaluation of the Dartmouth Medical Center Bridge Program; Collaborated with the Vermont Law School Environmental Law Center to provide scientific research assistance for “Broad vs. OMYA”; Research collaboration with Innosight Institute on innovative approaches to healthcare systems strengthening.

Honors and Awards

2009 CLARION National Root Cause Analysis Championship finalist (team awarded $2,000); 2009 CLARION Dartmouth Root Cause Analysis Championship winning team. Inducted into the βeta βeta βeta National Biological Honor Society.

Publications

Five most closely related to proposed project

Karesh W, Loh L, Machalaba C. (2011). Food Safety: A View from the Wild Side. Institute

of Medicine summary report of the workshop on Improving Food Safety Through One Health. Dec. 13-14, 2011.

Karesh WB, Dobson A, Lloyd-Smith J, Lubroth J, Dixon MA, Bennett M, Aldrich S, Harrington T, Formenty P, Loh L, Machalaba CC, Thomas MJ, Heymann DL. (2012) The Ecology of Zoonoses: Their Natural and Unnatural Histories. The Lancet 380: 1936-45.

Machalaba C, Karesh WB. (2012). Other Relevant International Standards to the Control of

Rabies. Rabies Control Towards Sustainable Prevention at the Source. Compendium of the OIE Global Conference on Rabies Control. Published by the OIE.

Vora NM, Smith KM, Machalaba CC, Karesh WB. (2012) Reducing the risk of reptile- and

amphibian-associated salmonellosis within child-care centers. Emerging Infectious Diseases. 2012: 18(12).

Machalaba C, Karesh WB, Prieur-Richard AH. (2012) Integrating health concerns into

biodiversity planning. CBD Newsletter for Civil Society. October 2012:7.

Evelyn M. Luciano

EcoHealth Alliance, 460 W. 34th St. New York, NY 10001

Luciano@ecohealthalliance.org

Evelyn Luciano is the senior administrator for grants and programs at EcoHealth Alliance, where she acts as principal contract manager for USAID EPT PREDICT, providing administrative oversight and support for the project's financial management.  Evelyn Luciano has worked for over 10 years as an administrative assistant, manager and grants and contracts officer in a leading US University.  Her background is in international affairs, development and non-profit management.

Education
City College of the City of New York		International Affairs		BA		1995

Work Experience

Director, Federal Grants and Programs, EcoHealth Alliance		2010 - Present

- Oversee all aspects of Eco Health Alliance’s federal grants program. In coordination with the scientific team, senior administrators, program liaisons and other external personnel.

- Serve as point person on budget tracking and monitoring; ensure grant compliance, prepare and file quarterly reports, manage subcontractors, and related matters throughout the grant award period.

- Ensure that all government and institutional requirements and regulations regarding finance, employment, travel, reporting, and other relevant administrative processes are met and exceeded.

Center Administrator, Columbia University in the City of New York                1998 - 2008
Center for Environment, Economy and Society (CEES)
Center for Environmental Research and Conservation (CERC)

- Served as administrative manager of Center; primary liaison to students, faculty, and key administration.

- Provided troubleshooting expertise to Center operations and programs; assisted with all phases of special projects.

- Supervised administrative staff.

- Managed vendor contracts/relations, security, implementation of University-wide compliance systems for the Center’s contracts.

- Oversaw Center renovation and construction; worked with designers, architects, and foremen throughout six month project.

- Assisted with fundraising, alumni and donor outreach.

- Coordinated stewardship, cultivation, domestic, international, and special events for donors.

Development Associate, Covenant House					1995 - 1998

- Worked with CEO and senior development leadership; supported all phases of development and external relations for the nation’s largest youth social services agencies.

- Prepared donor reports; briefings and correspondence.

- Represented the organization at numerous employee-giving campaigns; made presentations; cultivated donor relationships and ensured proper donor recognition.

- Assisted with special events.

Research/Event Coordinator, Boy Scouts of America 			1991 -1995

- Supported eight-person team with research, writing and document production assistance for industry driven fundraising events.

- Primary organization contact for Fortune 100 honorees.

- Assisted with all phases of event fundraising from letter writing to event management.

Elizabeth I. Eckel

EcoHealth Alliance, 460 W. 34th St. New York, NY 10001

eckel@ecohealthalliance.org

Elizabeth I. Eckel, Program Assistant, supports activities related to the Consortium for Conservation Medicine, the One Health Alliance of South Asia, and the Sicki project at EcoHealth Alliance. Ms. Eckel specializes in gender issues in population health, and has a background in cultural anthropology. She is trained in quantitative and qualitative research and evaluation methods. Previously, she has investigated adolescent HIV infection among youth in Uganda with Columbia University’s Rakai Youth Project. Ms. Eckel brings over two years of experience managing activities under USAID’s Health Systems 20/20 project. She is interested in the intersection between population health and environment, socio-cultural issues in infectious disease research, and anthropological applications in public health research and programs.

Education

| Macalester College | Anthropology | BA | 2007 |
| --- | --- | --- | --- |
| Columbia University Mailman School of Public Health | Population and Family Health | MPH | 2012 |

Work Experience

Program Assistant, EcoHealth Alliance						2013 - present

- Support One Health Alliance of South Asia (OHASA) network activities, linking human, animal, and ecosystem health

- Manage grant proposals (USAID, NSF, NIH)

- Conduct research for development of comprehensive online encyclopedia of emerging infectious diseases under USAID-funded PREDICT project.

Research Assistant, Columbia University						2011 - 2012

- Analyzed, coded, and synthesized semi-structured interview transcripts from 66 respondents using Atlas.ti for NIH-funded study of adolescent HIV infection in Uganda, the Rakai Youth Project

- Developed study design and data collection instruments with Project Director for Phase II qualitative research

- Provided additional research support to senior scientists as needed

Program Evaluation Intern, Columbia University					2012 - 2012

- Contributed to official evaluation analysis and report on implementation of OASIS II workforce development eHealth and mHealth initiatives for the Earth Institute’s Millennium Villages Project sites

Field Practicum Intern, Rakai Health Sciences Program				2011 - 2011

- Implemented self-directed analysis of marital dissolution, young women, and HIV and developed journal manuscript for NIH-funded Rakai Youth Project

- Facilitated weekly capacity building discussion sessions with Qualitative Research Unit staff

Associate Analyst, Abt Associates, Inc.						2007 - 2010

- Coordinated multiple global teams for up to 20 concurrent health systems strengthening project activities and reproductive health research activities in sub-Saharan Africa for USAID-funded Health Systems 20/20 Project

- Oversaw and administered contracts and budgets to ensure USAID compliance and client satisfaction (up to $3.8 million portfolio)

- Supported leadership by contributing to work plans, facilitating performance monitoring, and managing communications

Patient Educator, Family Tree Clinic							2006 - 2007

- Educated clinic patients individually on birth control methods, STI testing, and pregnancy options

- Created clinic literature for patient use

Synergistic Activities

Professional Groups

Member, International AIDS Society (IAS) (2012-present)

Reviewer

AIDS and Behavior (2013)

Publications

Higgins J, Mathur S, Nakyanjo N, Eckel E, Kelley L, Sekamwa R, Namatovu J, Nalugoda F, Santelli JS. (2012) Contexts of HIV transmission among young adults in Rakai, Uganda: The importance of relationship dynamics. Presented at the APHA Annual Meeting. San Francisco, CA.

Mathur S, Santelli JS, Higgins J, Eckel E, Nakyanjo N, Nalugoda F. (2012) Young women’s self assessment of HIV risk and the desire for children in Rakai, Uganda. Presented at the XIX International AIDS Conference. Washington, DC.

May 21, 2013

To Whom it May Concern:

I, Peter Daszak, hereby confirm my availability to serve as Chief of Party (CoP) within the same day following awarding of the proposed project for the USAID/RDMA Program entitled “Land Use Change and Disease Emergence: Promoting Valuation of Environmental Services in Furtherance of Public Health and Sustainable Landscapes”. I intend to serve in this role for the entirety of the proposed project (three years following the start of the project). I agree to the compensation levels which correspond to the levels set forth in the cost application.

Sincerely,

Peter Daszak, PhD

President

EcoHealth Alliance

460 West 34th Street – 17th floor

New York, NY 10001

1.212.380.4473 (direct)

1.212.380.4465 (fax)

Daszak@ecohealthalliance.org

www.ecohealthalliance.org

EcoHealth Alliance integrates innovative science-based solutions and partnerships that increase capacity to achieve two interrelated goals: protecting global health by preventing the outbreak of emerging diseases and safeguarding ecosystems by promoting conservation.

EcoHealth Alliance			EcoHealthAlliance.org

460 West 34th Street, 17th Floor

New York, NY 10001-2320

212.380.4460

May 21, 2013

To Whom it May Concern:

I, Tom Hughes, hereby confirm my availability to serve as Deputy Chief of Party (DCoP) within the same day following awarding of the proposed project for the USAID/RDMA Program entitled “Land Use Change and Disease Emergence: Promoting Valuation of Environmental Services in Furtherance of Public Health and Sustainable Landscapes”. I intend to serve in this role for the entirety of the proposed project (three years following the start of the project). I agree to the compensation levels which correspond to the levels set forth in the cost application.

Sincerely,

Tom Hughes

Project Coordinator – Malaysia

EcoHealth Alliance

D203, Block D, Paradesa Tropika,

Persiaran Meranti,

Bandar Sri Damansara, 52200, Kuala Lumpur, Malaysia.

0060 (0)19 392 8307 (Mobile), 0060 (0)3 6157 6035 (Telephone), 0060 (0)3 6157 6035 (fax)

tom.hughes@ecohealthalliance.org 				www.ecohealthalliance.org

EcoHealth Alliance integrates innovative science-based solutions and partnerships that increase capacity to achieve two interrelated goals: protecting global health by preventing the outbreak of emerging diseases and safeguarding ecosystems by promoting conservation.

EcoHealth Alliance			EcoHealthAlliance.org

460 West 34th Street, 17th Floor

New York, NY 10001-2320

212.380.4460

May 21, 2013

To Whom it May Concern:

I, Jonathan Epstein, hereby confirm my availability to serve as Stakeholder Coordination Lead (SCL) within the same day following awarding of the proposed project for the USAID/RDMA Program entitled “Land Use Change and Disease Emergence: Promoting Valuation of Environmental Services in Furtherance of Public Health and Sustainable Landscapes”. I intend to serve in this role for the entirety of the proposed project (three years following the start of the project). I agree to the compensation levels which correspond to the levels set forth in the cost application.

Sincerely,

Jonathan H. Epstein DVM, MPH

Associate Vice President, Conservation Medicine

EcoHealth Alliance 460 West 34th Street – 17th floor

New York, NY 10001

1.212.380.4467 (direct), 1.917.385.5315 (mobile), 1.212.380.4465 (fax)

Epstein@ecohealthalliance.org

www.ecohealthalliance.org

EcoHealth Alliance integrates innovative science-based solutions and partnerships that increase capacity to achieve two interrelated goals: protecting global health by preventing the outbreak of emerging diseases and safeguarding ecosystems by promoting conservation.

EcoHealth Alliance			EcoHealthAlliance.org

460 West 34th Street, 17th Floor

New York, NY 10001-2320

212.380.4460

May 21, 2013

To Whom it May Concern:

I, William B. Karesh, hereby confirm my availability to serve as Policy Leader (PL) within the same day following awarding of the proposed project for the USAID/RDMA Program entitled “Land Use Change and Disease Emergence: Promoting Valuation of Environmental Services in Furtherance of Public Health and Sustainable Landscapes”. I intend to serve in this role for the entirety of the proposed project (three years following the start of the project). I agree to the compensation levels which correspond to the levels set forth in the cost application.

Sincerely,

William B. Karesh, D.V.M

Executive Vice President for Health and Policy

EcoHealth Alliance

460 West 34th Street - 17th Floor

New York, NY 10001 USA

+1.212.380.4463 (direct), +1.212.380.4465 (fax)

Karesh@ecohealthalliance.org

www.ecohealthalliance.org

EcoHealth Alliance integrates innovative science-based solutions and partnerships that increase capacity to achieve two interrelated goals: protecting global health by preventing the outbreak of emerging diseases and safeguarding ecosystems by promoting conservation.

EcoHealth Alliance			EcoHealthAlliance.org

460 West 34th Street, 17th Floor

New York, NY 10001-2320

212.380.4460

References for Key Personnel

Dr. Peter Daszak

- Dr. James M. Hughes, former head of CDC National Center for Infectious Diseases, Professor, Emory University School of Medicine, Atlanta, USA

Email: jmhughe@emory.edu

Phone: (404) 727-3113

- Dr. Dennis Carroll, Director, Pandemic Influenza and Other Emerging Threats Unit, Global Health, US Agency for International Development, Washington DC, USA

Email: dcarroll@usaid.gov

Phone: (202) 712-5009

Fax: (202) 216-3708

- Dr. Josh Rosenthal, Acting Division Director, NIH Fogarty International Center, Bethesda, Maryland, USA

Email: Joshua.Rosenthal@nih.gov

Phone: (301) 496-1653

Mr. Tom Hughes

- Datuk Dr. Laurentius Ambu, Director Sabah Wildlife Department,

Ministry for Tourism Development, Environment, Science and Technology, Sabah, Malaysia

Email: Laurentius.Yambu@sabah.gov.my

Phone: 006 088-211645 / 214515 / 215353

Fax: 006 088-222476

- Dato’ Dr. Abd. Aziz Jamaluddin, Director General, Department of Veterinary Services, Wisma Tani, Podium Block, Lot 4G1, Precinct 4, Federal Government Administration Centre, 62630 Putrajaya, Malaysia

Email: azizj@jph.gov.my or azizjam900@yahoo.com or kp@dvs.gov.my

Phone: (+60-3) 209 40077 ext. 101 or (+60-3) 8888 8170 or (+60-3) 8870 2201

Fax: (+60-3) 8888 6051

- Datuk Dr Lokman Hakim Sulaiman, Deputy Director General (Public Health),

Ministry of Health Malaysia.

Email: lokman.hakim@moh.gov.my

Phone: 0060 3 88832544

Fax: 0060 3 88895601

Dr. Jonathan Epstein

- Dr. Andrew Clements, Senior Technical Advisor, Global Health, US Agency for International Development, Washington DC, USA

Email: aclements@usaid.gov

Phone: (202) 712-4218

Fax: (202) 216-3708

- Ron Waldman, Professor of Global Health, Department of Global Health, George Washington University, 2175 K St., NW, Suite 200, Washington DC, USA

Email: ronwaldman@gwu.edu

Phone: (202) 994-3780

Fax: (202) 994-1955

- Dato’ Dr. Abd. Aziz Jamaluddin, Director General, Department of Veterinary Services, Wisma Tani, Podium Block, Lot 4G1, Precinct 4, Federal Government Administration Centre, 62630 Putrajaya, Malaysia

Email: azizj@jph.gov.my or azizjam900@yahoo.com or kp@dvs.gov.my

Phone: (+60-3) 209 40077 ext. 101 or (+60-3) 8888 8170 or (+60-3) 8870 2201

Fax: (+60-3) 8888 6051

Dr. William B. Karesh

- Alisa Pereira, Senior Public Health Advisor, Pandemic Influenza and Other Emerging Threats Unit, Global Health, US Agency for International Development, Washington DC, USA

Email: apereira@usaid.gov

Phone: (202) 712-5221

Fax: (202) 216-3708

- Dr. Alex Deghan, Science and Technology Advisor to the Administrator and Director, US Agency for International Development, Washington DC, USA

Email: adeghan@usaid.gov

Phone: (202) 712-4137

Fax:

- Dr. Andrew Clements, Senior Technical Advisor, Pandemic Influenza and Other Emerging Threats Unit, Global Health, US Agency for International Development, Washington DC, USA

Email: aclements@usaid.gov

Phone: (202) 712-4218

Fax: (202) 216-3708

ANNEX C – Institutional Capabilities/Partnerships

Project oversight and administrative management will be provided by the EHA home office in New York and implementation of Malaysia based activities will be managed by the Deputy Chief of Party and his/her team based in Kuala Lumpur and Kota Kinabalu.  As the project will be based on a Cooperative Agreement, we envision that USAID/RDMA would also serve in providing advice and guidance to the project oversight and management team.  Personnel Proposed and their project duties are listed below.  Resumes and references are provided in Appendix B.

Chief of Party:  Dr. Peter Daszak (16.6% time)

The CoP will provide overall management and coordination of program vision, direction and functional successes; and is responsible for the administration and integration of the entire program. To guarantee fiscal responsibility and responsiveness to the needs of the program, the CoP will review and approve budgets to ensure they are in line with the work proposed, consistent with applicable rules and guidelines and committing sufficient effort for project participants. The CoP will conduct periodic reviews with the Administrative Coordinator to assess ongoing budgetary needs and will call and lead meetings with the Senior Management Team (CoP, Deputy CoP, Stakeholder and Partners Lead, Policy Lead, and Administrative Coordinator) to assess the program’s productivity and accomplishments with respect to its goals. He will request and conduct site visits as needed.  The CoP will also directly oversee the Modeling Team and be responsible for ensuring modeling activities and products are integrated with other project components.

Dr. Peter Daszak is President of EcoHealth Alliance, a US-based organization that conducts research and outreach programs on global health, conservation and international development. Dr. Daszak’s research has been instrumental in modeling, analyzing and predicting the origin and economic impact of emerging diseases. His achievements include producing the first ever global emerging disease ‘hotspots’ map, the design and implementation of the DEEP FOREST Project, identification of the wildlife reservoir of SARS, identifying the causes of Nipah and Hendra virus emergence, and coining the term ‘pathogen pollution’. He has 20 years’ experience managing international research and outreach projects, including directing the Consortium for Conservation Medicine for 8 years, establishing EHA’s formal partnership with the Malaysian Govt. in 2001 (HERG), and launching the One Health Alliance of South Asia in 2008. Currently, Dr. Daszak leads the modeling team for the USAID EPT PREDICT program.

Deputy Chief of Party:  Tom Hughes (100% time or phased change-over from PREDICT duties as negotiated with USAID/RDMA)

The day-to-day management of the project in Malaysia will be the overall responsibility of the DCoP, performed with regular communications and assistance of the other key personnel, the administrative staff from the home office, the Center of Excellence in Sabah and other key partners.  The DCoP will serve as the most frequent Point of Contact for USAID RDMA for programmatic matters, the Center of Excellence and key partners in Malaysia.  The DCoP will divide his/her time between Sabah, peninsula Malaysia and Bangkok as needed to interact with partners and supervise activities.

Tom Hughes is currently the Malaysian Project Coordinator at EcoHealth Alliance. His responsibilities include setting up and running the Study of Zoonotic Infections among Persons Exposed to Wild Animals, a collaborative research project with Global Viral and the Malaysian Government. In Malaysia, Tom has worked closely with partners from the Ministry of Health, the Department of Wildlife and National Parks, and the Department of Veterinary Services, over the last 8 years to develop personnel and laboratory capacity and establish sustainable disease surveillance systems for wildlife and people with high exposure to wildlife. In the last two years Tom has established the EHA Deep Forest Project in Sabah, a study of the effects of land use change on viral diversity. In 2010, Tom became the PREDICT Malaysia country coordinator for USAID's Emerging Pandemic Threats program. The aim of this research is to integrate wildlife disease surveillance into the public health infrastructure in order to create an early warning system for potential zoonotic disease spillover into domestic animals and humans. In Malaysia, Tom is working closely with partners from the Ministry of Health, the Department of Wildlife and National Parks, the Department of Veterinary Services, Sabah Wildlife Department and local universities.

Stakeholder Coordination Lead (SCL): Dr. Jon Epstein (8.3%)

Project Responsibilities (Job Description):  The SCL will work with Malaysian National and State government authorities and private sector parties to identify, engage and maintain working relationships with relevant stakeholders throughout the life of the project.  The SCL will ensure high level integration of project activities and products with stakeholder and partner needs and priorities, help develop and implement workshops with the DCOP and the Center for Development and Health, provide consistency in approaches across the project, and provide the oversight for sustainable transition of relevant activities to partners by the end of the project.

Dr. Jonathan Epstein is the Associate Vice President of Conservation Medicine at EcoHealth Alliance where he has managed projects on the emergence of Nipah and Ebola virus, SARS, MERS, and other zoonotic diseases within Asia and Africa.  Dr. Epstein has directed US government-funded EHA programs in Malaysia since 2003 including a study of the ecology of Nipah virus, and is currently the Asia Regional Coordinator for PREDICT.  He has brought together diverse stakeholders, including government agencies, universities and NGO’s across multiple countries in South Asia to lead the One Health Association of South Asia, and currently directs two other multi-disciplinary and multi-stakeholder groups, EcoHealth Net and the Consortium for Conservation Medicine.

Policy Leader (PL):  Dr. William Karesh (8.3% time)

The PL will be responsible for identifying opportunities and strategies for program outcomes to serve as guidance for policy and best practices among government and non-governmental stakeholders in Sabah, Malaysia, and regionally as appropriate.  The SL will meet with high-level government agency representatives to share finding and discuss opportunities for policy engagement.  The SL will also share findings and policy opportunities at a broader scale with international and inter-governmental organizations and agencies such as the World Bank, WHO, FAO, OIE, CGIAR, and bi-lateral aid agencies

Dr. William Karesh is the Executive Vice President for Health and Policy at EcoHealth Alliance. He has over 25 years of international policy experience and has worked with the Sabah government since 1988.  Dr. Karesh serves on the World Health Organization's (WHO) International Health Regulations Roster of Experts focused on the human-animal interface and wildlife health. He also serves as the president of the World Animal Health Organization (OIE) Working Group on Wildlife Diseases and also chairs the International Union for the Conservation of Nature (IUCN) Wildlife Health Specialist Group, a network of wildlife and health experts around the world. Currently, Dr. Karesh is the Technical Director for the USAID Emerging Pandemic Threats PREDICT program.

Proposed Key Technical Personnel

Center of Excellence Director: Dr. Sarma B. Aralas is a professor of Economics at the School of Business and Economics at the Universiti of Malaysia Sabah.  Dr. Aralas will work with Senior Personnel and local partners to establish the Center for Development and Health at UMS.  She will also facilitate workshops and mentor graduate students working under this project.  Dr. Aralas is a professor of Economics at the School of Business and Economics at the Universiti of Malaysia Sabah.

Center of Excellence Associate: Dr. Zakariya Belkhamza is a professor of information technology and data management at the School of Business and Economics at UMS.  He will work with Dr. Sarma to develop workshops and facilitate stakeholder meetings at the university.  He will also mentor graduate students from the business school and staff from partner agencies that work under this project.

Sabah Wildlife Department Chief Liaison to IDEEAL: Datuk Dr Laurentius N. Ambu is the Director of Sabah Wildlife Department, a position he has held since 2007. Prior to that, he was the Deputy Director from 1991. Datuk Dr Laurentius holds a BSc Degree (Zoology) from Southern Illinois University, USA, a post-graduate Diploma in Protected Landscape Management from Aberystwyth University, Wales, UK, and a PhD in Wildlife Management from Oxford University, United Kingdom. He also holds a professional post‐graduate Diploma in Edible-Nest Swiftlet Conservation and Management from Cambridge Academy of Management (FCAM). He serves as the Head of CITES (Convention of International Trade of Endangered Species of Wild Flora and Fauna) Management Authority for the Sabah Government and an expert member of the IUCN Species Survival Commission (SSC) for Asian Rhinoceros, Bovidae, Crocodile, Asian Elephant, Primate and Swiftlet Specialist Groups.

Economic Modeler:  Sarah Elwood (75% time)

Sarah Elwood will work to develop the avoided costs model and participate in the associated data collection. Sarah will work closely with the other Research Scientists to ensure the successful integration of other model components. She will document the processes and information needed to adapt the model to other contexts and ensure generalizability of the tool.  Sarah Elwood investigates the economic costs associated with disease emergence.  Sarah is involved with multiple projects, including a benefit cost analysis to determine whether captive-bred or wild-caught animals are a more economical choice for the pet industry, and an evaluation of a proposed tax on internationally traded meat to generate revenue for global zoonotic disease surveillance.  She is interested in the integration of economic theory with epidemiological models to study how the decisions people make affect the spread of infectious diseases.

Economic Modeler:  TBD  (33% time)

The economic modeler will work closely with the rest of the modeling and analytical team to support their activities in developing our analytical work and outreach.  They will liaise closely with the DEEP FOREST team, and with partners in Sabah.

Social Science Lead: Elizabeth Loh (16.6% time)

Elizabeth Loh will work closely with the DCoP to assist in the supervision of the data collection, and connection of DEEP FOREST project data to the quantitative tools.  She will work towards the integration of gender sensitive data for the models, and assist in the interpretation of the differential disease risks to men and women based on their daily activities.

Elizabeth Loh brings a human dimension to EHA projects.  An anthropologist and conservation biologist by training, Elizabeth Loh works to understand how human activities may be contributing to ecological changes and disease emergence.  Her research interests lie within coupled social-ecological systems.  Her current work examines the effects of forest fragmentation on mammal and viral communities, investigates the role of human behavior in disease risk, and she is a lead scientist on EHA’s Deep Forest projects in Brazil and Malaysia.

DEEP FOREST Liaison: Kris Murray (16.6% time)

Kris Murray will oversee the execution of the modeling strategy, collaborating with the other scientists and actively communicating and discussing the model developments with the CoP.  Kris will also draw on the project DEEP FOREST data and other data sources to assist with scenario building to project disease risks for different levels of land use change, and clearly communicate these findings to key stakeholders. Dr Kris Murray is an ecologist and conservation biologist with broad interests in biodiversity, evolution, behavior, and disease ecology.  At EcoHealth Alliance, Kris brings a diverse skill set and experience relevant to exploring the roles of biodiversity, land-use change, climate change and other socio-economic, demographic and environmental drivers in disease emergence and conservation.  Dr. Murray is a lead scientist on EHA’s Deep Forest projects in Brazil and Malaysia and is responsible for the coordination and alignment of Deep Forest project goals and methods across all three continents (South America, Africa and Asia).

Senior Modeler: Carlos Zambrana-Torrelio (25% time)

Carlos Zambrana-Torrelio will manage the disease and land cover geodatabases with particular attention to the assurance of data quality.  The development of the statistical framework, and the use of Bayesian statistics to assess the likelihood of disease outbreak given differing levels of deforestation will be Carlos’s primary responsibility. Carlos Zambrana-Torrelio is part of EcoHealth Alliance's modeling team, where he combines quantitative methods, spatial data and fieldwork to investigate the emergence of infectious diseases. He is interested in ecological niche modeling and applications of Geographic Information Systems (GIS) technology for biodiversity research and conservation.  He leads the GIS and modeling team for EHA’s Deep Forest projects in Brazil and Malaysia.

Program Coordinator for Health and Policy:  Catherine Machalaba (16.6% time)

The Program Coordinator for Health and Policy will be actively involved in tracing the policy implications of the scientific findings.  She will provide programmatic support for the project's health communication and policy outreach activities, including considerations around the social determinants of health as well as the formation of collaborations with non-traditional partners. She will also provide program evaluation expertise to assist in tracking achievement of project objectives. Catherine Machalaba works with conservation, public health and medical communities to find synergies and opportunities to promote science-driven policy.  Trained in public health, her work supports EHA collaborations with policy stakeholders at the international, national, and local level.  Current projects include policies to consider health threats to biodiversity and practice-based prevention of EIDs.

Grants and Contracts Manager:  Evelyn Luciano (8.33% time)

The Grants and Contracts Manager will provide administrative oversight and support for the project's financial management, working closely with the CFO at EHA, and administrative staff funded through EHA core funds.  She will ensure efficient transfer of funds to subrecipients, and financial reporting on all aspects of the contract. Evelyn Luciano has worked for over 15 years as an administrative assistant, manager and grants and contracts officer in a leading US University, and for the last 5 years at EHA where she acts as principal contract manager for EcoHealth Alliance’s USAID EPT PREDICT subcontract.

PART 2. Institutional Capability.

EcoHealth Alliance (EHA) is a science-based organization incorporated over 40 years ago, now working with local partners in over 30 countries at the nexus of public health, biodiversity conservation and international development. EHA has a staff of 35 at headquarters office in New York, including administrative staff (development, finance, marketing & communications), science staff (modelers, economists, social scientists, veterinarians, ecologists, analysts, IT researchers etc), outreach staff (educators, researchers, communication staff). EHA also has international staff of in-country field scientists, social scientists, program managers and country leads based in around 30 countries, including Malaysia (both peninsular and Sabah). EHA has an extensive record of publishing high quality, peer-reviewed papers, journals, briefing documents and reports. Given that a primary indicator of success in this project is based on utilization of data and findings by decision makers, EHA’s demonstrated expertise in producing highly utilized and understandable science-based outputs will contribute significantly to achieving both project goals and provide objective methods for tracking project utilization of project findings.

Work experience with USAID EPT and DEEP FOREST

EHA is a core partner of the USAID EPT PREDICT project, and staff at EHA include the PREDICT Senior Technical Director (Dr. William Karesh), the lead for the modeling component of PREDICT (Dr. Peter Daszak), the DEEP FOREST project manager (Dr. Kris Murray), the majority of the PREDICT modeling staff, the regional lead for Asia (Dr. Jon Epstein), and country leads for Malaysia (Tom Hughes), Indonesia (Dr. William Karesh), and Thailand (Dr. Kevin Olival). EcoHealth Alliance formulated the concept and design of the PREDICT DEEP FOREST project, and is the implementation lead at our tropical forest sites along land use gradients in Sabah, Malaysia and Brazil.  At these sites, EHA staff are sampling high-risk wildlife, co-ordinating surveys of human contact and behavior (in collaboration with EPT PREVENT), and managing viral testing and capacity building.  The aims of DEEP FOREST have direct relevance to the current project, and are to understand how land-use change affects 1) patterns of biodiversity, 2) patterns of viral diversity and 3) patterns of human occupancy and behavior that influence contact rates with wildlife. The human behavioral data gathered includes gender-specific issues of relevance to EID risk, and, similarly, opportunities for gender empowerment and health savings. In addition, EHA scientists are currently working on the DEEP FOREST contact surveys, and other social science aspects of its projects such as our IDRC-supported ‘Pontal’ project in Brazil.

Work Experience in Modeling Land-use Change

EcoHealth Alliance is a leader in modeling and analyses of the emergence of new diseases.  EHA staff led the development of analytical tools and models resulting in the “Hotspots of Emerging Diseases”, have conducted extensive fieldwork on emerging diseases in tropical regions, and have led the thinking on the relationship of land-use change and disease emergence. Our portfolio of projects that model disease emergence risk, land-use change, and economic valuation is outlined in below.  EHA is a global leader in developing the science, analytical frameworks and field studies to understand the relationship between land use change and disease emergence; in applying spatial analyses to understand drivers of emergence; in the theory of the drivers of zoonotic EIDs; in climate change modeling with respect to public health; in valuing the economic damages associated with EIDs; in understanding and estimating the global wildlife trade and their impacts on public health; and in understanding the ecosystem services associated with EIDs.  EHA staff are members of the HEAL (Health and Ecosystems: Analysis and Linkages) project (www.onehealthcommission.org/en/resources/health__ecosystems_analysis_of_linkages_heal/);  Dr. Daszak leads the DIVERSITAS ecoHEALTH project (www.diversitas-international.org/activities/research/ecohealth), both of which have specific goals of understanding the ecosystem services related to zoonoses.

Work Experience Modeling Disease Emergence

The thrust of this RFA corresponds directly with the analytical and modeling work EHA is conducting on understanding and predicting disease emergence.  For example, EHA modelers have shown that the underlying drivers of disease emergence vary depending on region, but in the place where most zoonoses emerge (the Tropics, inclunding SE Asia) are primary land use change, agricultural intensification, or secondary factors associated with these (e.g. bushmeat), see Figure 1, below.

Figure 1:  EHA modeling staff have analyzed the underlying causes of all EIDs since 1940.  This figure shows that disease emergence in the Asian region, and the Tropics globally, is dominated by land use change, agricultural intensification, and secondary factors these lead to.

EcoHealth Alliance scientists are currently developing a new version of the EID ‘hotspots’ model, which is currently gridded to 1km2, and therefore will be useful in providing subnational information on the highest disease risk regions within SE Asia (see Figure 2, below).  This approach is based on an online Wikipedia-like project (Sicki) that provides far better data on the origins of EIDs than the scientific literature.

Figure 2:  High-resolution image of EID risk in Thailand.  Version 2 of the hotspot maps, currently being produced by EcoHealth Alliance, will significantly improve capacity to target surveillance based on wildlife diversity and risk of human contact with zoonotic reservoirs.

The best models require significant data inputs to parameterize.  In the DEEP FOREST sites in Borneo and Brazil (and the ‘Pontal’ project in Brazil), EHA is generating data of direct relevance to the work described in this RFA, including: the relative abundance and diversity of bats, primates, and rodents; the relative intensity of contact among humans and wildlife; and the diversity of known and unknown zoonoses.  The collection of these data is driven firstly by models and analyses that identify the most important issues to target.  For example, in regions such as SE Asia, where land use change brings people into contact with wildlife reservoirs, EHA has identified the most important transmission pathways that pathogens have previously used to spillover into people (Figure 3, below).

Figure 3:The most significant pathways that pathogens use to emerge in people in areas under intensive land-use change

Finally, EHA manages a portfolio of projects funded by NSF, NIH, DOD and other agencies which specifically analyze the risk of a range of zoonoses emerging in Tropical regions.  These include models of how spillover events develop from stuttering chains of zoonotic spillover, then chains of small clusters of human cases, to epidemic, then pandemic spread.  We are currently comparing models that involve direct wildlife to human exposure to models that involve domestic animals as intermediate hosts.  We are looking into this for henipaviruses, influenza viruses, coronaviruses and other critical zoonoses.

Figure 4: Map of Logging, tree crop and timber concessions in Indonesia.  EHA scientists are actively working on mapping these activities with respect to the emerging disease hotspots across tropical Asia, Africa and America.

Work Experience in Economic Modeling

EHA has a program to understand the economic incentives that might be used to mitigate against globally emerging pandemics.  Projects include modeling economic damages due to EIDs under different policy scenarios, the trade-offs between preserving ecosystems and the disease regulation services they provide, and cost-benefits of converting land for other productive activities.  EHA leads the DEEED (Diversity, Economics, EcoHealth and Emerging Diseases) project that is part of the UNESCO-ICSU DIVERSITAS cluster. This project is actively engaged in:

- Valuing the Ecosystem Services from forests within EID hotspots and comparing the benefits of preserving the ecosystem to those from converting the land for another productive purpose

- Valuing the damages associated with disease emergence

- Evaluating systems of “EcoHealth Credits” that might be traded alongside or integrated into the trading of carbon credits (e.g., as per biodiversity, REDD+).

- Using contingent valuation methodology—an approach that can also be applied to assign a value to ecosystem services—to gather data on individuals’ willingness-to-pay to avert a pandemic.

- Understanding the global relevance of the ‘Dilution Effect’ by which biodiversity conservation may help regulate zoonotic disease risk.

This and other associated work by members of our team has resulted in scientific papers that argue the case for preventive rather reactive responses to EID and other risks (Murray et al., 2012), use climate change (adaptation vs. mitigation) approaches to address pandemic threat (Pike et al., in review), evaluate strategies to tax livestock production as a way to reduce pandemic potential (Elwood et al., in review), and evaluate a credit trading system as a way to reduce the risk of pandemics (Tutunjian et al., in review).

Just like climate change, the risk of disease emergence from regions like Sabah can be viewed as a global commons issue (in this case a public ‘bad’, rather than a ‘good’), which can either be mitigated against, or adapted to.   Here mitigation involves dealing with underlying causes of EIDs at source (e.g. the proposed work in this RFI) and adaptation involves reliance on current global surveillance, and drug and vaccine development.  We have developed a stochastic dynamic model that examines the optimal timing in which to implement pandemic mitigation and/or adaptation policies (Figure 5, below). We used real options methodology, data on the incremental rise in EIDs and their associated damages, and the cost of current global health systems, to optimize the delivery of global policies to reduce the damages from EIDs.   Our model demonstrates that mitigation projects, which address the underlying causes of pandemics at source, more efficiently reduce the damages associated with pandemics than adaptation.  This experience and modeling approach has a direct application to valuing ecosystem services as not only the current value of services should be examined, but also the ability of the ecosystem to maintain these services over time.

Figure 5: Stopping model for pandemic prevention.  Y-axis: net present value of expected damages of an EID outbreak plus the cost, K, of a policy if implemented.   X-axis: expected damages/time.  Blue line: expected damages if policy is not implemented and the value of waiting (e.g. by more knowledge gained) is not considered.  Green line:  EID damages if a policy with cost, K, is implemented. If the value of waiting is ignored, D~ is the threshold at which a policy should be implemented.  The red line, known as the ‘continuation value’, illustrates the expected damages under business as usual.  The decision model simply takes the currently experienced damage, a point on the x-axis, and determines which of the three lines is lowest (has lowest expected present damages and costs).  For damages less than D* it is optimal to “continue” to wait.  For all damages above D* it is optimal to implement the policy.  D* is the optimal threshold.   Our results show that the waiting time to implement a global EID mitigation policy is between 4 and 24 years, after which it will be too costly to reduce the inexorable rise in EID emergence.

Work Experience in Ecosystem Services

The first step to a successful project that provides incentives to reduce, change or otherwise affect commercial activities such as logging, agricultural development and mining is to provide an industry-specific economically viable case.  EHA is currently involved in key activities of direct relevance to this RFA.  Via subcontract from PREVENT, EHA led the analysis and provided the scientific case for a white paper on reducing EID risk in the extractive industries.

Figure 6: Global EID risk map, overlaid with data on timber concessions and active logging, mining and other extractive industry activities

We also co-hosted a meeting at Chatham House that brought numerous stakeholders from the extractive industries together around the issue of EID risk.  This included producing global maps of EID risk and mining/logging concessions (Figure 6, above).

EHA staff members also sit on the EPT Extractive Industries Working Group.  This group has developed tools to incorporate zoonotic EIDs into Health Impact Assessments, and assess potential risk in sites with active extraction. These include developing measures for risk prevention and management that reduce likelihood of exposure to potential health hazards, strengthening of systems for monitoring and responding to disease-related risks, and engagement of local health officials in risk control. In addition, EHA has active projects with other leaders in the extractive industries, chemical industries, agriculture/livestock, and palm oil production, which can be harnessed for the work in this RFA.

Work Experience in Social Science and Surveys

EHA is working closely with EPT partner PREVENT to develop a standard survey approach to assess and quantify the types and frequencies of human-animal contact in each of our DEEP FOREST sites. These contact surveys are adapted to the country, sub-population and setting in which they are implemented. Already, EHA has piloted over 100 surveys in settlement communities in the Atlantic Forest, Brazil. In each site, these surveys are being used to quantify human contact with potential wildlife reservoirs with particular attention to bats, rodents, and primates as well as other types of wild and domestic animals to which people are frequently exposed. Results from intensive interviewing and behavioral characterization will determine how this fundamental but poorly quantified measure might vary with land-use practices and intensity of disturbance. Quantifying contact will also provide a basis for determining which populations are at higher risk and what types of behavior change might be needed for mitigation strategies.  In 2013, EHA will implement the DEEP FOREST human-contact survey in our sites in the Brazilian Amazon. In Sabah, PREVENT will collect human-wildlife contact data in close coordination with EHA, and in Uganda PREVENT will collect similar data in coordination with EHA and UCDavis. Data from both Brazil and Malaysia sites will generate critical information on key risk interfaces and the potential risk of spillover for each defined ecosystem. We also have access to active extraction sites, through our contact with the SAFE project (Stability of Altered Ecosystems), which is conducting one of the world’s largest ecological experiments to understand the ways in which logging, deforestation and forest fragmentation modify the functioning of tropical rainforests and impair their ability to deliver important ecosystem services.

Work Experience in REDD+ initiatives

EHA is engaged in a project to develop a trading system for ‘EcoHealth Credits’ that adapts to the features of REDD+. In its original form, REDD (Reducing Emissions from Deforestation and forest Degradation) was designed as a climate change mitigation tool based on the sale of carbon credits to encourage countries to reduce deforestation by selling the value of the carbon that would otherwise have been released.  REDD+ is a more recent development that broadens the scope to include additional co-benefits of protecting carbon stocks, e.g., protecting biodiversity and improving livelihoods, after it was recognized that carbon investments could be manipulated to better achieve numerous targets for traditionally resource-poor but deforestation-related issues (e.g., biodiversity protection, livelihood enhancements) without compromising the overall efficacy of the program for climate change mitigation. It has also been suggested that optimization procedures could minimize the conflicts with other development goals, such as agricultural production and logging. Our analyses suggest that health could conceivably be considered as one of these additional co-benefits, which could influence the way that REDD+ funds are allocated or influence the perception or relative valuation of potentially conflicting development goals.  The next step will be to develop ways that health benefits of intact forests can be integrated into a market-based instrument – something which is directly covered in this RFA, and which EHA has expertise in doing for EIDs.

Experience Implementing Projects in the Region

EHA has worked intensively in Malaysia since 1998, where it maintains an office. Our extensive partnerships and collaborations have led directly to implementation of a Zoonosis Technical Working Committee comprised of the Ministry of Health Malaysia, the Department of Veterinary Services, the Department of Wildlife and National Parks (PERHILITAN) and EHA as part of EPT PREDICT.  This committee reports directly to the Malaysian government on the control of zoonotic diseases.  In 2000, with our partners in the Dept. of Veterinary Services, the Veterinary Research Institute, Ministry of Agriculture, and the Department of Wildlife and National Parks (PERHLITAN) EHA scientists set up a large-scale international study on the ecology of Nipah virus. This has led to significant scientific outputs, changes to government regulations on pig farming, and regional approaches to zoonotic surveillance.

In 2012 we collaborated with our partners at Sabah Wildlife Department to create the Sabah Wildlife Health Unit that is dedicated to disease surveillance activities and to set up the Wildlife Health, Genetic and Forensic Laboratory. These partnerships have historically focused not only on scientific research, but capacity-building, training, and public outreach to communicate our science. In the past five years, we have expanded our collaboration to include the Ministry of Health and the National Public Health Laboratory (NPHL), under a program looking at the risk of zoonotic disease transmission to people highly exposed to wildlife.

EcoHealth Alliance has also continued to focus on conservation in Malaysia. EHA scientists have worked with PERHILITAN to reduce hunting pressures on flying foxes and to raise awareness of the importance of these animals. In order to preempt harassment of Pteropus hypomelanus bats due to their association with Nipah virus, an outreach strategy was developed for a local primary school, located near the site of EHA’s long-term bat surveillance Nipah virus study on Malaysia’s Tioman Island. The take home message from the talks, games and leaflet was that flying foxes play a crucial role in seed dispersal and the pollination of forest and commercial plants. Malaysian fruits including Durian (Durio spp.) and Petai (Parkia speciosa) depend on flying foxes for pollination as does much of the timber Malaysia exports, a fact of which many Malaysians were unaware.

In 2012, we partnered with the Malaysian Ministry of Health to develop outreach education material including fact sheets, and pamphlets on zoonotic infectious diseases to provide information on potential risks and biosafety measures, as well as common routes of disease exposure. We are also working closely with MOH to develop standard operating procedures for the Healthy Hunters program. To date, EcoHealth Alliance has trained over 110 members of the PREDICT team in Malaysia, including staff from PERHILITAN, VRI, several local universities and NGOs, and Sabah Wildlife Department. We have also transferred technologies to PERHILITAN, VRI, and SWD to run molecular diagnostic assays for viral family detection in wildlife samples as an initial screen for viruses with zoonotic potential.

Home-office backstopping and its purposes.

The finance department at EHA will manage the cash flow from USA to Malaysia. EHA is a certified USAID prime contractor and subject to federal audits, for which it is considered a low risk organization. The Sub-recipients for these funds – DCOP, Sabah Wildlife Department, University Malaysia Sabah, Department of Veterinary Services and Department of State Health Sabah are all know entities that EHA has worked with in the past. EHA will have their certified public accountant manage the project accounts with oversight from the Chief Financial Officer. The accounts for the project will be submitted for annual external audit. The EHA office will also be responsible for the scientific and technical review and will lead the modeling effort.

The DCOP Tom Hughes has 8 years’ experience managing large budgets and large field projects with multiple partners will receive funds from the EHA Finance Department. The DCOP will be responsible for the fiscal management of all funds in Malaysia associated with this contract to cover operating expenses and to support the activities of stakeholders involved in this project. The DCOP will track project expenditures to ensure fiscal responsibility and prepare financial data for reporting. For stakeholders who may require regular financial support, such as to fund the running of the Center of Excellence we will establish at University Malaysia Sabah, a contract would be signed between DCOP and the stakeholder.

Sub-recipient capabilities and expertise

Univesiti Malaysia Sabah (UMS)

UMS strives to be an innovative university of global standing UMS strives to achieve academic excellence and international recognition through its attention to learning and teaching, research and publications, social services and balance in knowledge specialization. The university also prioritizes the personal growth of its students, resulting in greater innovation and productivity for the benefit of society and the nation as a whole.  The School of Business and Economics, was established in 1995 with intention of fulfilling the country's need for managers and entrepreneurship in various areas of business to ensure that Malaysia achieves its objective to be an industrialized country by 2020. SBE seeks to ensure that its academic programs are update with the most recent research finding and by an understanding of contemporary business, government and management practices. As a result of its proactive policy, the school is capable of disseminating the recent development in knowledge in business and economics to its students and other audiences. The School has already earned recognition in providing quality MBA among profesional in the State and hopes to gain international recognition in the years to come.

UMS will be creating the Center for Development and Health under this project inline with it’s other existing Centers of Excellence such as the Institute for Tropical Biology and Conservation. The ITBC works at various sections of the society including the traditional communities, government agencies, non-governmental organizations and relevant ministries, ensuring a fair bit information exchange, technology transfer, assistance and smart-partnerships. The institute has developed a tradition of working with many partners both within and outside Malaysia.

The Sabah Wildlife Department (SWD)

The Sabah Wildlife Department works under the authority of the Sabah Ministry for Tourism Development, Environment, Science and Technology. The Wildlife Department has its headquarter in Kota Kinabalu and it has a number of district offices, centers and stations throughout the state.  Over 230 staff members work in the SWD. The department is responsible for implementation and administration of the Sabah Wildlife Conservation Enactment, 1997.  Under this Enactment the department conserves and regulates wildlife utilization in Sabah and it manages a number of protected areas. The department also implements the Convention on International Trade in Endangered Species of Wild Fauna and Flora (CITES) as well as contribute to the implementation of the international convention of Biological Diversity and to a number of other international, regional and bilateral agreements.  The objective of the SWD is to manage the State's wildlife resources for the benefit of the people of Malaysia in general and of Sabah in particular.  The SWD is the lead local partner for the USAID EPT program, working directly with both PREDICT and PREVENT.  As such, they are also the key implementation partner for the DEEP FOREST project.  For IDEEAL, SWD will serve to bring together relevant stakeholders to participate in the efforts of the UMS Center for Development and Health to strengthen the center of excellence platform.  SWD will also prove to be the key in liaising with other Sabah government departments for obtaining additional data and input for modeling and to engage in policy outreach efforts.

References for Annex C:

Elwood, S., et al. Evaluation of a levy on internationally traded meat to finance global disease surveillance. Emerging Infectious Diseases, in review.

Groot, R. D., et al. (2010). "Integrating the ecological and economic dimensions in biodiversity and ecosystem service valuation." The Economics of Ecosystems and Biodiversity (TEEB): Ecological and Economic Foundations

Murray, K. A., et al. (2012). "Cooling off health security hot spots: Getting on top of it down under." Environment International 48(0): 56-64.

Pike, J., et al. (2013). "Economic optimization of a global stategy to reduce the pandemic threat." Nature, in review.

Tutunjian, C., et al. A credit trading system for pandemic prevention.  EcoHealth, in review.

Letters of Support from Stakeholder Organizations

Peter Daszak

President, EcoHealth Alliance

460 West 34th Street – 17th floor
New York, NY 10001

USA

Dear Dr. Daszak,

This letter is to confirm that the Kinabatangan Orang-utan Conservation Programme run by the French NGO HUTAN will be very pleased to collaborate on the application being led by EcoHealth Alliance to implement the USAID Land Use Change and Disease Emergence program.

Should EcoHealth Alliance be successful in its application, I have agreed to participate in activities associated with this project including acting as a resource for information and insight, based on my expertise, including assisting in identifying and locating relevant and available data sets, to help achieve the aims of this project. I will also participate in occasional meetings at local partner institutions to discuss findings of this study, strategies for educational outreach and dissemination of findings, and advise or participate in graduate student training activities.

This letter conveys my interest and commitment to making this initiative a success. We are excited to be involved in this effort to develop evidence-based tools for utilization in reducing deforestation, associated carbon emissions, and risk of disease emergence. We look forward to working with EcoHealth Alliance, Sabah Wildlife Department, and USAID on this important project.

Sincerely,

Dr Marc Ancrenaz

KOCP, Director

Kota Kinabalu

15.05.2013

__________________________________________________________________________________

PO Box 17793, 88874 Kota Kinabalu, Sabah, Malaysia.

T: 6088 413 293      F: 6088 413 293      w: www.hutan.org.m

ANNEX D: Relevant Past Performance Information

PREDICT - Wildlife SMART Surveillance

PERFORMANCE REPORT - SHORT FORM

PART I: Award Information (to be completed by Prime)

1. Name of Awarding Entity: USDS AGENCY FOR INTERNATIONAL DEVELOPMENT (USAID)

2. Award Number: GHN-A-00-09-00010-00

3. Award Type: Grant

4a. Award Value (or subagreement value): $75M

4b. Annual amount received for each of last 3 years: $21,500,000; $17,663,000; $15,000,000

4c. Award beginning and end dates: 10/01/09-09/30/14

5. Problems: (if problems encountered on this award, explain corrective action taken): No significant problems encountered

6. Contacts: (Name, Address, Telephone Number and E-mail address)

6a. Agreement Officer: Bruce Baltas, 1201 Pennsylvania Ave., NW, Washington, DC 20004, 202-712-5279, bbaltas@usaid.gov

6b. Technical Officer (AOTR/COTR):

6c. Other:

7. Recipient: University of California-Davis/EcoHealth Alliance

8. Title/Brief Description of Product/Service Provided: PREDICT - Wildlife SMART Surveillance/PREDICT Project to pre-empt at the earlier stages possible, zoonotic diseases that impose significant threat to public health.

9. Information Provided in Response to RFA/RFP No.: USAID-RDMA-RFA-486-13-0000001 Land Use Change and Disease Emergence Program

10. Key project accomplishment and results to date: Analyzing and predicting disease emergence · Analyzed role of land use change as driver of disease emergence · Produced economic cost-benefit analysis of adaptation vs. mitigation to Pandemic Threats · Produced version 2 of EID Hotspots map · Developed online wiki for EID emergence data (“The Sicki Project”) · Designed and launched the DEEP FOREST Project to assess disease emergence across land use gradient · Characterized risk interfaces & human contact potential for transmission in different social and ecological contexts · Produced predictive maps of Pandemic risk based on air travel/trade Expanding the One Health Workforce · Trained over 1,600 people in surveillance, diagnostics & outbreak response · Coordinating with 59 ministries in 20 countries · Partnering with US agencies & foreign governments to establish regional networks for wildlife health and laboratory diagnostics Optimizing surveillance & response · Standardized animal sampling protocols to ensure safe wildlife handling · Improved cold chain access in remote areas · Established scientifically-justifiable & practically implementable sampling goals to identify new viruses and evaluate diversity in regions & hosts · Responded to deadly outbreaks incorporating animal & environmental best practices · Identified efficient diagnostic paradigm for mystery diseases Providing proof of concept · Sampled 35,000 animals · Discovered 200 viruses in genera or families known to cause zoonotic epidemics · Built capacity for diagnostic testing in 20 labs · Working toward sustainable improvements in 33 labs in total · Used new viral data to help assess risk & respond to outbreaks · Published 24 peer-reviewed scientific publications in high impact journals (PNAS, Nature, The Lancet etc.)

Risk of Viral Emergence from Bats

PERFORMANCE REPORT - SHORT FORM

PART I: Award Information (to be completed by Prime)

1. Name of Awarding Entity: NIAID Non-Biodefense Emerging Infectious Diseases

2. Award Number: 5R01AI079231

3. Award Type: Grant

4a. Award Value (or subagreement value): $2,687,394

4b. Annual amount received for each of last 3 years: $534,739, $534,968, $547,542

4c. Award beginning and end dates: 09/18/08-08/31/13

5. Problems: (if problems encountered on this award, explain corrective action taken): No significant problems encountered

6. Contacts: (Name, Address, Telephone Number and E-mail address)

6a. Agreement Officer: Eun-chung Park, NIAID, NIH; epark@niaid.nih.gov, 301-594-9875

6b. Technical Officer (AOTR/COTR):

6c. Other: Howard England, englandh@niaid.nih.gov, 301-496-7453

7. Recipient: EcoHealth Alliance

8. Title/Brief Description of Product/Service Provided: ‘Risk of Viral Emergence from Bats’/ Characterized the diversity of bat viruses globally; developed predictive models to look at areas of the globe at greatest risk from zoonotic bat viruses and identify the factors that drive cross-species transmission in bats; and estimating the unknown viral richness in bats globally.

9. Information Provided in Response to RFA/RFP No.: NIH PA-07-246

10. Key project accomplishment and results to date: Targeted sample collection for bat viral discovery - Collected over 2,200 samples from bats targeted by high-risk species and geography. - Globally, over 12,000 samples from ~100 bat species have been collected. 100s of novel viruses from 10 viral families have been identified. Bat Viral Discovery and ‘Deep Sampling’– Bangladesh Case Study - Ran over 16,000 PCR assays for 12 viral families, and discovered 63 putative novel viruses in Bangladesh alone. - Non-bat viruses were detected in fruit bats as part of this study, including both avian and bovine coronaviruses. Viral Discovery Curves – assessing total known and unknown viral diversity - Viral discovery curves used to estimate total diversity of mammal viruses. - 63 novel viruses that include 11 new Paramyxoviruses and 28 new Adenoviruses have been identified. Predicting risk of bat virus emergence - Identified significant host and virus traits that predict whether or not a virus will be shared among bat species. - Results showed that phylogenetic distance between bat host species is a strong predictor of viral sharing. - Primates, rodents, bats and lagomorphs have significantly higher proportions of viruses shared with humans than other mammal Orders. - Mapped global pandemic risk from the emergence of all direct- and vector- transmitted zoonotic viruses using airline travel data, zoonotic disease hotspot risk maps, and per capita health care. Training and outreach - Trained >230 people in-country in methods of bat capture, safe handling, species identification, proper use of Personal Protective Equipment (PPE), and minimally-invasive sample collection. - Held a large hands-on training in Central Thailand for 32 people, which included veterinary and forest students from three universities in Thailand, staff and veterinarians from the Department of National Parks Thailand. - EcoHealth Alliance with FAO co-edited and published a volume on best practices for investigating zoonoses from bats which is freely available online. - Over 20 peer-reviewed papers have been published under this award.

HSD: Collaborative Research: Human Related Factors Affecting Emerging Infectious Diseases.

PERFORMANCE REPORT - SHORT FORM

PART I: Award Information (to be completed by Prime)

1. Name of Awarding Entity: National Science Foundation (NSF)

2. Award Number: BCS-0826779

3. Award Type: Grant

4a. Award Value (or subagreement value): $468, 673

4b. Annual amount received for each of last 3 years: $158,673; $150,000; $150,000

4c. Award beginning and end dates: 10/01/08-01/31/12

5. Problems: (if problems encountered on this award, explain corrective action taken): No significant problems encountered

6. Contacts: (Name, Address, Telephone Number and E-mail address) Peter Daszak

6a. Agreement Officer: Tom Baerwald, NSF; tbaerwal@nsf.gov

6b. Technical Officer (AOTR/COTR):

6c. Other:

7. Recipient: EcoHealth Alliance

8. Title/Brief Description of Product/Service Provided: ‘HSD: Collaborative Research: Human Related Factors Affecting Emerging Infectious Diseases’/The goal of this project was to understand the process by which anthropogenic changes drive patterns of disease emergence globally, and the development of predictive models for disease emergence and pandemic spread.

9. Information Provided in Response to RFA/RFP No.: USAID-RDMA-RFA-486-13-0000001 Land Use Change and Disease Emergence Program

10. Key project accomplishment and results to date: - Produced first ever global disease hotspot map - Analyzed risk of disease emergence from agricultural production and food - Collated over 20 globally-gridded, largescale datasets on socio-economic factors involved in disease emergence - Published papers in Science, Nature and other high-impact journals.

EcoHealthNet: Ecology, Environmental Science and Health Research Network

PERFORMANCE REPORT - SHORT FORM

PART I: Award Information (to be completed by Prime)

1. Name of Awarding Entity: National Science Foundation (NSF)

2. Award Number: 0955897

3. Award Type: Grant

4a. Award Value (or subagreement value): $397,510

4b. Annual amount received for each of last 3 years: $98,673, $99,919, $98,992

4c. Award beginning and end dates: 07/01/10-08/31/15

5. Problems: (if problems encountered on this award, explain corrective action taken): No significant problems encountered

6. Contacts: (Name, Address, Telephone Number and E-mail address)

6a. Agreement Officer: Sam Scheiner, Div. Environmental Biol. (Rm. 635), 4201Wilson Blvd., Natl. Science Foundation, Arlington, VA 22230; Tel 703-292-7175; Email sscheine@nsf.gov

6b. Technical Officer (AOTR/COTR):

6c. Other: Barbara L. Brooks, 703-292-4802

7. Recipient: EcoHealth Alliance

8. Title/Brief Description of Product/Service Provided: ‘EcoHealthNet: Ecology, Environmental Science and Health Research Network’/Its aim is to provide multi-disciplinary training to graduate students and early career scientists from the US and abroad in the field of disease ecology.

9. Information Provided in Response to RFA/RFP No.: USAID-RDMA-RFA-486-13-0000001 Land Use Change and Disease Emergence Program

10. Key project accomplishment and results to date: - Bringing together experts from top academic, government, and non-governmental organization representing fields of ecology, veterinary medicine, medicine, GIS, mathematical modeling, and epidemiology together for a 1-week didactic and applied training workshop attended by 20 of the best and brightest graduate students competitively selected from programs around the world. - 10 funded applied research experiences for students each year which includes a mentored field placement for up to 3 months conducting research within a larger, funded ecohealth research project. - Trained over 100 students from more than 20 countries. - Workshops have included disease mapping and modeling, which was held at Johns Hopkins Bloomberg School of Public Health; Epidemiology and outbreak response co-hosted by the University of Wisconsin and the USGS National Wildlife Health Center, and this year will be at on Zoonoses and food safety at the University of Minnesota. - Past workshop attendees have stayed connected through an EcoHealthNet alumni network and many EcoHealth Net scholars have graduated and acquired jobs with science-based research organizations.

The Ecology, Emergence and Pandemic Potential of Nipah Virus in Bangladesh

PERFORMANCE REPORT - SHORT FORM

PART I: Award Information (to be completed by Prime)

1. Name of Awarding Entity: NIH-Fogarty International Center

2. Award Number: 2R01-TW005869

3. Award Type: Grant

4a. Award Value (or subagreement value): $2,501,550

4b. Annual amount received for each of last 3 years: $499,998; $499,449; $499,772

4c. Award beginning and end dates: 08/01/08-06/30/14

5. Problems: (if problems encountered on this award, explain corrective action taken): No significant problems encountered

6. Contacts: (Name, Address, Telephone Number and E-mail address)

6a. Agreement Officer: Kasima V. Brown, Email: kasima.brown@nih.gov, Phone: 301-584-1211

6b. Technical Officer (AOTR/COTR): Christine Jessup, Email: Christine.jessup@nih.gov, Phone: 301-496-1653

6c. Other: N/A

7. Recipient: EcoHealth Alliance

8. Title/Brief Description of Product/Service Provided: ‘The Ecology, Emergence and Pandemic Potential of Nipah Virus in Bangladesh’/Nipah virus is an emerging zoonotic virus carried by old world fruit bats that causes regular outbreaks of encephalitis with high mortality rates in people Bangladesh. This five-year program aims to study the dynamics of Nipah virus in its natural bat reservoir, as well as the spillover dynamics among bats, other animals, and people, in an effort to understand the risk of Nipah virus causing a global pandemic.

9. Information Provided in Response to RFA/RFP No.: USAID-RDMA-RFA-486-13-0000001 Land Use Change and Disease Emergence Program

10. Key project accomplishment and results to date: - Multidisciplinary collaboration set up among veterinarians, epidemiologists, physicians, anthropologists, ecologists and virologists at EcoHealth Alliance and ICDDR,B - Thousands of bats sampled across Bangladesh - Systematic study of viral and antibody prevalence in populations across Bangladesh. - Large-scale case-control study of people in villages across Bangladesh to characterize environmental and behavioral risk factors associated with human spillover. - Identified over 10 clusters of Nipah virus infection in people in Bangladesh - Published over 25 papers in high profile scientific journals